## SUMMARY
SAKARYA GAS FIELD DEVELOPMENT PROJECT PHASE 3 — DASHBOARD DATA
IQS S.r.l. Worldwide Inspection Company — Live Dashboard Data Source
KEY PERFORMANCE INDICATORS
Field | Value
Purchase Order (PO) Qty | 15462
Incoming Plates | 170
Pipes Accepted | 149
Pipes Rejected | 3
Repair / Rework | 4
Overall Pass Rate (%) | 87.65
Completion vs PO (%)
Report Date | 10/03/2026
ITP STEPS — PIPE PRODUCTION TRACKING
Seq. N° | ITP Step | Section | Count | Yield vs Input (%) | Loss vs Input | Cumul. Loss | Remarks
1 | Incoming Plate | Forming | 170 | 100 | 0 | 0
2 | Pipe Forming | Forming | 170 | 100 | 0 | 0
3 | Tack Welding | Forming | 170 | 100 | 0 | 0
4 | ID SAWL | Forming | 170 | 100 | 0 | 0
5 | OD SAWL | Forming | 170 | 100 | 0 | 0
6 | AUT1 | Welding & NDT | 170 | 100 | 0 | 0
7 | Fluoroscopic | Welding & NDT | 12 | 7.06 | 158 | 158
8 | Welding Repair | Welding & NDT | 4 | 2.35 | 4 | 4
9 | MCE1 | Mechanical | 164 | 96.47 | 6 | 6
10 | MCE2 | Mechanical | 0 | 0 | 0 | 0 | N/A
11 | MCE Inspection | Mechanical | 164 | 96.47 | 6 | 6
12 | Straightness Re-work | Mechanical | 6 | 3.53 | 0 | 0
13 | Hydro Test | Testing | 158 | 92.94 | 12 | 12
14 | AUT2 | Testing | 0 | 0 | 0 | 0 | N/A
15 | Phase Arr. | Testing | 158 | 92.94 | 12 | 12
16 | MUT | Testing | 158 | 92.94 | 12 | 12
17 | End UT | Testing | 157 | 92.35 | 13 | 13
18 | X-Ray | Testing | 156 | 91.76 | 14 | 14
19 | OoR Pipe Body | Dimensional & Final | 156 | 91.76 | 14 | 14
20 | Dimensional 1 | Dimensional & Final | 150 | 88.24 | 20 | 20
21 | Dimensional 2 | Dimensional & Final | 149 | 87.65 | 21 | 21
22 | MPI | Dimensional & Final | 149 | 87.65 | 21 | 21
23 | UT DHC | Dimensional & Final | 149 | 87.65 | 21 | 21
24 | Final Mark & Weigh | Dimensional & Final | 149 | 87.65 | 21 | 21

## DEFECTS_WELD
WELDING DEFECTS LOG — Add new rows below
Date (DD/MM/YYYY) | Shift | Pipe N° | Defect Description | Position (mm) | Extension (mm) | Remarks
11/02/2026 | 1 | 26.4.002089 | Weld high bead below specified | 1200 | 300
19/02/2026 | 1 | 26.4.002205 | OD Slag Inclusion | 1450 | 100
20/02/2026 | 1 | 26.4.002207 | OD Underfill | 5510 | 130
21/02/2026 | 1 | 26.4.002252 | ID Stop/Start | 2320 | 200

## DEFECTS_FINAL
FINAL INSPECTION DEFECTS LOG — Add new rows below
Date (DD/MM/YYYY) | Shift | Pipe N° | Defect | Remarks
11/02/2026 | 1 | 26.4.002095 | Burn Through | MPQT Pipe (NCR-001)
23/02/2026 | 1 | 26.4.002094 | Pore | 2350x50mm
23/02/2026 | 1 | 26.4.002250 | WT Below Spec | 8100x640mm

## HOW_TO_USE
HOW TO USE — Google Sheets Live Dashboard
Step | Action | Details
STEP 1 | Upload to Google Sheets | Go to sheets.google.com → File → Import → Upload this file
STEP 2 | Publish as Web App | File → Share → Publish to web → Select 'SUMMARY' sheet → CSV format → Publish
STEP 3 | Copy the URL | Copy the published CSV URL (ends in ...pub?gid=0&single=true&output=csv)
STEP 4 | Paste in Dashboard | Open dashboard HTML → find GOOGLE_SHEET_URL → replace with your URL
STEP 5 | Update data | Edit values in SUMMARY (yellow cells) → Dashboard auto-refreshes for all users
STEP 6 | Add defects | Add new rows to DEFECTS_WELD or DEFECTS_FINAL sheets → publish those too
NOTE | Refresh interval | Dashboard fetches new data every 5 minutes automatically
NOTE | Access control | Keep Google Sheet private — only the published CSV will be public