## Dashboard
SAKARYA PROJECT - INSPECTION & TEST PLAN — PIPE PRODUCTION TRACKING
Input | 170
Seq. n° | ITP Step | Section | Count | Yield vs Input | Loss vs Input | Cumul. Loss | Remarks
1 | Incoming Plate | Forming | 170 | 100% | 0 | 0
2 | Pipe Forming | Forming | 170 | 100% | 0 | 0
3 | Tack Welding | Forming | 170 | 100% | 0 | 0
4 | ID SAWL | Forming | 170 | 100% | 0 | 0
5 | OD SAWL | Forming | 170 | 100% | 0 | 0
6 | AUT1 | Welding & NDT | 170 | 100% | 0 | 0
7 | Fluoroscopic | Welding & NDT | 12 | 7.059% | 158 | 158
8 | Welding Repair | Welding & NDT | 4 | 2.353% | 4 | 4
9 | MCE1 | Mechanical | 164 | 96.47% | 6 | 6
10 | MCE2 | Mechanical | 0 | — | — | —
11 | MCE Inspection | Mechanical | 164 | 96.47% | 6 | 6
12 | Straightness Re-work | Mechanical | 6 | — | — | —
13 | Hydro Test | Testing | 158 | 92.94% | 12 | 12
14 | AUT2 | Testing | 0 | — | — | —
15 | Phase Arr. | Testing | 158 | 92.94% | 12 | 12
16 | MUT | Testing | 158 | 92.94% | 12 | 12
17 | End UT | Testing | 157 | 92.35% | 13 | 13
18 | X-Ray | Testing | 156 | 91.76% | 14 | 14
19 | OoR Pipe Body | Dimensional & Final | 156 | 91.76% | 14 | 14
20 | Dimensional 1 | Dimensional & Final | 150 | 88.24% | 20 | 20
21 | Dimensional 2 | Dimensional & Final | 149 | 87.65% | 21 | 21
22 | MPI | Dimensional & Final | 149 | 87.65% | 21 | 21
23 | UT DHC | Dimensional & Final | 147 | 86.47% | 23 | 23
24 | Final Mark & Weigh | Dimensional & Final | 149 | 87.65% | 21 | 21
SUMMARY
Total Pipes |  |  |  | 170
Total pipes Accepted |  |  |  | 149
Overall Status % |  |  |  | 87.65%
Welding Repair |  |  |  | 47

## MPQT - WPQT
Overview MPQT / WPQT SAWL Line Pipe - Lab Tests Control Table SAKARYA PROJECT
OD X WT (in X in) | WPS Nº | Pipe Nº | Heat N° | Tenaris Labs Report | Chemical Compos. Analysis |  | Tensile Tests | [8 empty] | Transversal Compression Test |  | BM CVN Impact Testing -30°C |  | CVN Impact Testing of the Weld Seam @ -30°C | [12 empty] | CVN Impact Testing Transition Curve Base Metal @ +20°C to -120°C |  | Drop Weight Tear Testing (DWTT) |  | CTOD (AF) |  |  | CTOD (AC) |  |  | Grain Size BM | Guided Bend Tests |  |  | VicKers Hardness Tests |  |  | Macrographic Test | Flux Humidity (Karl Fischer) | Ring Splitting Test |  | HIC |  | SSC |  | Remarks
[5 empty] | BM | WM | Longitudinal BM | Longitudinal BM (Coated) | Transversal BM | Transversal BM (Coated) | Transversal WM | Transversal WM (DNV) | Transversal WM (Coated) | ID and OD All Weld | All Weld (Coated) | Without Inline Heat Treatment | Inline Heat Treatment (Coated) | AF | Coated | OD Weld Metal | OD Weld FL | OD Weld FL +2mm | OD Weld FL +5mm | Root Weld Metal | Root Weld FL | Root Weld FL +2mm | Root Weld FL +5mm | ID Weld Metal | ID Weld FL | ID Weld FL +2mm | ID Weld FL +5mm | WM (Coated) | AF | AF (Aged) | AF | Transition Curve | BM | WM | HAZ | BM | WM | HAZ |  | OD | ID | Side | BM | HAZ | WM | Interpenetration | WPQT | AF | AC | BM | WM | BM | WM
[5 empty] | 1/Pipe |  | All | All | All | All | All | WPQT Pipes | All | All | All | All |  | All |  | All | [12 empty] | All |  | All |  | All |  |  | All |  |  | All | All |  |  | All |  |  | All |  | All | All | All
24 x 1.268 | 3973 | 26.4.002096 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Border Line *CVN ID Fusino Line Rejected with single results 26J. *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002097 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *CVN ID Fusino Line Rejected with single results 29J *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002098 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10
| 3974 | 26.4.002240 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *ReTest performed as per NCR-003 and approved
| 3973 | 26.4.002099 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002100 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A
| 3973 | 26.4.002101 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002243 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
Repair Qualification
24 x 1.268 (STOP/START) | WPS-3973 | 26.4. 2128 (INT) | 800232.V | [43 empty] | IR-18 | IR-18 | IR-18 | IR-18
|  | 26.4.2128 (EXT) | [44 empty] | IR-18 | IR-18 | IR-18 | IR-18
OD 24 x 1.268 (rWPS) | WPS-260 (SHALLOW) | 26.4. 2128
WPS-262 (DEEP)
ID 24 x 1.268 (rWPS) | WPS-260 (SHALLOW) | 26.4. 2205 | 800222.V
WPS-262 (DEEP)

## 24 X 1.268 OFF
SAKARYA PROJECT - Overview Mass Production for SAWL Line Pipe - Lab Tests Control Table
OD24in X WT1.268in
OD X WT | Pipe Nº | Heat Plate N° | Tenaris Labs Report | Chemical Compos. Analysis |  | Tensile Tests |  |  |  | Transversal Compression Test | BM CVN Impact Testing -30°C | CVN Impact Testing of the Weld Seam @ -30°C |  | Drop Weight Tear Testing (DWTT) | Grain Size BM | Guided Bend Tests |  | VicKers Hardness Tests |  |  | Macrographic Test | HIC |  | Remarks
|  |  |  | BM | BM | Longitudinal BM | Transversal BM | Transversal WM | Transversal WM (Coated) | Inline Heat Treatment | AF | Weld Metal | HAZ | BM |  | OD | ID | BM | HAZ | WM | Interpenetration | BM | WM
|  |  |  | 1/Pipe |  | 1/Heat | 1/Heat | 1/Heat | All | 4/Heat 20 1/Heat | 1/Heat | 1/Heat |  | 1/Heat | 1 / 5 Heats | 1/Heat |  | 1/Heat |  |  | 1/Shift | 1 /Heat (first five Heat, than 1 / 10)
36 x 0.406 | 11646 | 780325 |  | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 / IR-15 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at OD FL+2mm (NCR-004) - Re-test performed and approved
|  | 800222 |  | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 / IR-15 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio FL (NCR-004) - Re-test performed and approved
|  | 800229 |  | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 / IR-15 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersection, on the NCR-004 Tenaris have informed that the CVN specimen of Intersevtion WM, was with the notch on the wrong sectiom and it is a FL Re-test performed and approved
|  | 800232 |  | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08
|  | 800233 |  | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 IR-15 IR-17 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio ID and OD FL (NCR-004) - Re-test performed Rejected on the same pipe (26.4.2117). Retest Performed and approved in two addtional Pipes from the same Test unit and approved (26.4.2147 and 2152)
|  | 974062 |  | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08

## PO5021701
Totale | [7 empty] | 170 |  |  |  |  | 0 | 426 | 277 | 269 | 264 | 259 | 257 | 13 | 0 | 230 | 231 | 0 | 0 | 226 | 206 | 195 | 190 | 179 | 177 | 171 | 156 | 156 | 0
Seq. N° | Tenaris Batch | Pipe Dimensional | Pipe Std | Pipe Number | Heat Number | Plate Number | Pipe length | Total Pipes | Tenaris Lote | Pipe N° | Heat N° | Plate N° | Pipe length2 | Plate Entrance | Pipe Forming | Tack Welding | ID SAWL | OD SAWL | AUT1 in House | Fluoroscopic/TOFD In House | Repair | MCE 1 | MCE 2 | Straighness Re-work | Hydrostatic Test | Phase Array | MUT | Pipe End UT | X-Ray | OoR Pipe Body | Dimensional 1 | Dimensional 2 | MPI | UT DHC | Final Marking and Weighing | Coluna1
1 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002086 | 800229.V | 112430/2.V | 12350 | 1 | 5021601 | 26.4.002113 | 800229.V | 112429/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
2 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002211 | 800222.V | 112447/1.V | 12450 | 1 | 5021601 | 26.4.002090 | 800229.V | 112432/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
3 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002085 | 800229.V | 112426/2.V | 12380 | 1 | 5021601 | 26.4.002179 | 800223.V | 112461/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
4 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002089 | 800229.V | 112427/1.V | 12470 | 1 | 5021601 | 26.4.002170 | 780325.V | 112403/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
5 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002090 | 800229.V | 112432/1.V | 12360 | 1 | 5021601 | 26.4.002238 | 974058.V | 112416/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
6 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002147 | 800233.V | 112487/2.V | 12460 | 1 | 5021701 | 26.4.002091 | 800229.V | 112431/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
7 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002092 | 800229.V | 112424/1.V | 12360 | 1 | 5021701 | 26.4.002101 | 974058.V | 112412/1.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
8 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002088 | 800229.V | 112426/1.V | 12430 | 1 | 5021701 | 26.4.002088 | 800229.V | 112426/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
9 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002094 | 800229.V | 112430/1.V | 12470 | 1 | 5021701 | 26.4.002131 | 800232.V | 112438/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
10 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002095 | 974058.V | 112411/1.V | 12460 | 1 | 5021701 | 26.4.002105 | 800229.V | 112425/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
11 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002096 | 974058.V | 112412/2.V | 12470 | 1 | 5021701 | 26.4.002092 | 800229.V | 112424/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
12 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002097 | 800223.V | 112460/1.V | 12370 | 1 | 5021701 | 26.4.007775 | 801208.V | 122020/1A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
13 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002098 | 800223.V | 112459/2.V | 12370 | 1 | 5021701 | 26.4.002087 | 800229.V | 112432/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
14 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002115 | 800233.V | 112488/2.V | 12450 | 1 | 5021701 | 26.4.002119 | 800233.V | 112483/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
15 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002100 | 800223.V | 112460/2.V | 12470 | 1 | 5021701 | 26.4.002097 | 800223.V | 112460/1.V | 12300 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN
16 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002101 | 974058.V | 112412/1.V | 12460 | 1 | 5021701 | 26.4.002086 | 800229.V | 112430/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
17 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002102 | 974058.V | 112411/2.V | 12460 | 1 | 5021701 | 26.4.002098 | 800223.V | 112459/2.V | 12340 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN
18 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002103 | 800229.V | 112427/2.V | 12440 | 1 | 5021701 | 26.4.002099 | 800223.V | 112459/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
19 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002093 | 800229.V | 112425/2.V | 12440 | 1 | 5021701 | 26.4.002100 | 800223.V | 112460/2.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
20 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002105 | 800229.V | 112425/1.V | 12340 | 1 | 5021701 | 26.4.002127 | 800232.V | 112436/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
21 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002106 | 800229.V | 112422/2.V | 12320 | 1 | 5021701 | 26.4.002102 | 974058.V | 112411/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
22 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002107 | 800229.V | 112423/2.V | 12370 | 1 | 5021701 | 26.4.002186 | 800223.V | 112454/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
23 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002108 | 800229.V | 112424/2.V | 12330 | 1 | 5021701 | 26.4.002104 | 800229.V | 112429/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
24 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002109 | 800229.V | 112428/2.V | 12470 | 1 | 5021701 | 26.4.002135 | 800232.V | 112445/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
25 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002110 | 800229.V | 112423/1.V | 12300 | 1 | 5021701 | 26.4.002106 | 800229.V | 112422/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
26 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002111 | 800229.V | 112431/1.V | 12440 | 1 | 5021701 | 26.4.002107 | 800229.V | 112423/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
27 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002112 | 800229.V | 112428/1.V | 12440 | 1 | 5021701 | 26.4.002108 | 800229.V | 112424/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
28 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002113 | 800229.V | 112429/2.V | 12470 | 1 | 5021701 | 26.4.002096 | 974058.V | 112412/2.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN
29 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002114 | 800233.V | 112487/1.V | 12450 | 1 | 5021701 | 26.4.002114 | 800233.V | 112487/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
30 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002099 | 800223.V | 112459/1.V | 12460 | 1 | 5021701 | 26.4.002095 | 974058.V | 112411/1.V | 12460 | EC | PU | SEL | SI | SE | U1
31 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002116 | 800233.V | 112485/2.V | 12020 | 1 | 5021701 | 26.4.002085 | 800229.V | 112426/2.V | 12130 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
32 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002117 | 800233.V | 112490/1.V | 12020 | 1 | 5021701 | 26.4.002112 | 800229.V | 112428/1.V | 12040 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
33 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002118 | 800232.V | 112444/2.V | 12470 | 1 | 5021701 | 26.4.002115 | 800233.V | 112488/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
34 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002119 | 800233.V | 112483/1.V | 12450 | 1 | 5021701 | 26.4.002116 | 800233.V | 112485/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
35 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002120 | 800232.V | 112437/2.V | 12450 | 1 | 5021701 | 26.4.002118 | 800232.V | 112444/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
36 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002121 | 800232.V | 112441/2.V | 12450 | 1 | 5021701 | 26.4.002160 | 780325.V | 112397/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
37 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002122 | 800232.V | 112434/2.V | 12450 | 1 | 5021701 | 26.4.002120 | 800232.V | 112437/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
38 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002123 | 800232.V | 112437/1.V | 12450 | 1 | 5021701 | 26.4.002121 | 800232.V | 112441/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
39 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002124 | 800232.V | 112436/2.V | 12450 | 1 | 5021701 | 26.4.002122 | 800232.V | 112434/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
40 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002125 | 800232.V | 112442/1.V | 12450 | 1 | 5021701 | 26.4.002123 | 800232.V | 112437/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
41 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002104 | 800229.V | 112429/1.V | 12430 | 1 | 5021701 | 26.4.002124 | 800232.V | 112436/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
42 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002127 | 800232.V | 112436/1.V | 12450 | 1 | 5021701 | 26.4.002125 | 800232.V | 112442/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
43 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002128 | 800232.V | 112434/1.V | 12450 | 1 | 5021701 | 26.4.002126 | 800232.V | 112439/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
44 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002129 | 800232.V | 112433/2.V | 12450 | 1 | 5021701 | 26.4.002177 | 974062.V | 112481/2.V | 12440 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
45 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002130 | 800232.V | 112444/1.V | 12450 | 1 | 5021701 | 26.4.002128 | 800232.V | 112434/1.V | 12470 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA
46 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002131 | 800232.V | 112438/1.V | 12450 | 1 | 5021701 | 26.4.002129 | 800232.V | 112433/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
47 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002132 | 800232.V | 112440/2.V | 12450 | 1 | 5021701 | 26.4.002130 | 800232.V | 112444/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
48 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002133 | 800232.V | 112441/1.V | 12450 | 1 | 5021701 | 26.4.007768 | 801208.V | 122030/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
49 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002134 | 800232.V | 112443/2.V | 12450 | 1 | 5021701 | 26.4.002089 | 800229.V | 112427/1.V | 12470 | EC | PU | SEL | SI | SE | U1
50 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002135 | 800232.V | 112445/2.V | 12450 | 1 | 5021701 | 26.4.002133 | 800232.V | 112441/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
51 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002136 | 800232.V | 112435/1.V | 12450 | 1 | 5021701 | 26.4.002134 | 800232.V | 112443/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
52 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002137 | 800232.V | 112445/1.V | 12450 | 1 | 5021701 | 26.4.002194 | 780325.V | 112397/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
53 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002138 | 800232.V | 112440/1.V | 12450 | 1 | 5021701 | 26.4.002136 | 800232.V | 112435/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
54 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002139 | 800232.V | 112435/2.V | 12450 | 1 | 5021701 | 26.4.002137 | 800232.V | 112445/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
55 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002140 | 800232.V | 112439/2.V | 12450 | 1 | 5021701 | 26.4.002138 | 800232.V | 112440/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
56 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002141 | 800232.V | 112438/2.V | 12450 | 1 | 5021701 | 26.4.002139 | 800232.V | 112435/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
57 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002142 | 800232.V | 112443/1.V | 12450 | 1 | 5021701 | 26.4.002140 | 800232.V | 112439/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
58 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002143 | 800232.V | 112442/2.V | 12450 | 1 | 5021701 | 26.4.002141 | 800232.V | 112438/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
59 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002144 | 800233.V | 112484/2.V | 12470 | 1 | 5021701 | 26.4.002142 | 800232.V | 112443/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
60 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002145 | 800233.V | 112486/1.V | 12470 | 1 | 5021701 | 26.4.002147 | 800233.V | 112487/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
61 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002146 | 800233.V | 112484/1.V | 12450 | 1 | 5021701 | 26.4.002111 | 800229.V | 112431/1.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
62 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002091 | 800229.V | 112431/2.V | 12360 | 1 | 5021701 | 26.4.002094 | 800229.V | 112430/1.V | 11360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
63 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002148 | 800233.V | 112490/2.V | 12450 | 1 | 5021701 | 26.4.002146 | 800233.V | 112484/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
64 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002149 | 800233.V | 112483/2.V | 12450 | 1 | 5021701 | 26.4.002214 | 974062.V | 112473/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
65 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002150 | 800233.V | 112489/1.V | 12450 | 1 | 5021701 | 26.4.002148 | 800233.V | 112490/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
66 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002151 | 800233.V | 112485/1.V | 12450 | 1 | 5021701 | 26.4.002149 | 800233.V | 112483/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
67 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002152 | 800233.V | 112489/2.V | 12450 | 1 | 5021701 | 26.4.002150 | 800233.V | 112489/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
68 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002153 | 800233.V | 112486/2.V | 12450 | 1 | 5021701 | 26.4.002151 | 800233.V | 112485/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
69 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002154 | 780325.V | 112403/1.V | 12470 | 1 | 5021701 | 26.4.002152 | 800233.V | 112489/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN
70 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002155 | 780325.V | 112405/2.V | 12450 | 1 | 5021701 | 26.4.002153 | 800233.V | 112486/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
71 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002156 | 780325.V | 112409/2.V | 12040 | 1 | 5021701 | 26.4.002154 | 780325.V | 112403/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
72 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002157 | 780325.V | 112406/2.V | 12480 | 1 | 5021701 | 26.4.002155 | 780325.V | 112405/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
73 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002158 | 780325.V | 112407/2.V | 12450 | 1 | 5021701 | 26.4.002157 | 780325.V | 112406/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
74 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002159 | 780325.V | 112405/1.V | 12450 | 1 | 5021701 | 26.4.002158 | 780325.V | 112407/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
75 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002160 | 780325.V | 112397/2.V | 12450 | 1 | 5021701 | 26.4.002159 | 780325.V | 112405/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
76 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002161 | 780325.V | 112404/2.V | 12450 | 1 | 5021701 | 26.4.002243 | 974058.V | 113145/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
77 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002162 | 800233.V | 112488/1.V | 12450 | 1 | 5021701 | 26.4.002161 | 780325.V | 112404/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
78 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002163 | 780325.V | 112404/1.V | 12450 | 1 | 5021701 | 26.4.002162 | 800233.V | 112488/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
79 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002164 | 780325.V | 112408/1.V | 12450 | 1 | 5021701 | 26.4.002163 | 780325.V | 112404/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
80 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002165 | 780325.V | 112408/2.V | 12450 | 1 | 5021701 | 26.4.002164 | 780325.V | 112408/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
81 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002166 | 780325.V | 112400/2.V | 12450 | 1 | 5021701 | 26.4.002165 | 780325.V | 112408/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
82 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002167 | 780325.V | 112399/2.V | 12450 | 1 | 5021701 | 26.4.002166 | 780325.V | 112400/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
83 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002168 | 780325.V | 112401/2.V | 12450 | 1 | 5021701 | 26.4.002167 | 780325.V | 112399/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
84 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002126 | 800232.V | 112439/1.V | 12450 | 1 | 5021701 | 26.4.002168 | 780325.V | 112401/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
85 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002170 | 780325.V | 112403/2.V | 12450 | 1 | 5021701 | 26.4.002169 | 780325.V | 112406/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
86 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002171 | 780325.V | 112401/1.V | 12070 | 1 | 5021701 | 26.4.002171 | 780325.V | 112401/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
87 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002172 | 780325.V | 112402/2.V | 12450 | 1 | 5021701 | 26.4.002172 | 780325.V | 112402/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
88 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002173 | 780325.V | 112399/1.V | 12450 | 1 | 5021701 | 26.4.002173 | 780325.V | 112399/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
89 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002174 | 974062.V | 112482/1.V | 12450 | 1 | 5021701 | 26.4.002174 | 974062.V | 112482/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
90 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002175 | 974062.V | 112470/2.V | 12450 | 1 | 5021701 | 26.4.002175 | 974062.V | 112470/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
91 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002176 | 974062.V | 112478/1.V | 12460 | 1 | 5021701 | 26.4.002176 | 974062.V | 112478/1.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
92 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002177 | 974062.V | 112481/2.V | 12460 | 1 | 5021701 | 26.4.007750 | 801208.V | 122030/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
93 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002178 | 800223.V | 112461/2.V | 12450 | 1 | 5021701 | 26.4.002178 | 800223.V | 112461/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
94 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002179 | 800223.V | 112461/1.V | 12460 | 1 | 5021701 | 26.4.002180 | 800223.V | 112463/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
95 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002180 | 800223.V | 112463/2.V | 12450 | 1 | 5021701 | 26.4.002181 | 800223.V | 112464/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
96 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002181 | 800223.V | 112464/2.V | 12460 | 1 | 5021701 | 26.4.002182 | 800223.V | 112462/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
97 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002182 | 800223.V | 112462/2.V | 12450 | 1 | 5021701 | 26.4.002183 | 800223.V | 112458/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
98 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002183 | 800223.V | 112458/2.V | 12450 | 1 | 5021701 | 26.4.002184 | 800223.V | 112464/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
99 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002184 | 800223.V | 112464/1.V | 12450 | 1 | 5021701 | 26.4.002185 | 800223.V | 112463/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
100 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002185 | 800223.V | 112463/1.V | 12450 | 1 | 5021701 | 26.4.007976 | 780993.V | 118565/2.V | 12450 | EC
101 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002186 | 800223.V | 112454/2.V | 12450 | 1 | 5021701 | 26.4.002187 | 800223.V | 112458/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
102 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002187 | 800223.V | 112458/1.V | 12470 | 1 | 5021701 | 26.4.002188 | 800223.V | 112455/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
103 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002188 | 800223.V | 112455/2.V | 12450 | 1 | 5021701 | 26.4.002103 | 800229.V | 112427/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
104 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002189 | 800223.V | 112456/1.V | 12460 | 1 | 5021701 | 26.4.002190 | 800223.V | 112454/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
105 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002190 | 800223.V | 112454/1.V | 12470 | 1 | 5021701 | 26.4.002191 | 800223.V | 112462/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
106 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002191 | 800223.V | 112462/1.V | 12460 | 1 | 5021701 | 26.4.002192 | 800223.V | 112455/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
107 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002192 | 800223.V | 112455/1.V | 12470 | 1 | 5021701 | 26.4.002193 | 800223.V | 112457/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
108 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002193 | 800223.V | 112457/2.V | 12450 | 1 | 5021701 | 26.4.007784 | 781297.V | 121345/1A.V | 12460 | EC | PU | SEL | SI
109 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002194 | 780325.V | 112397/1.V | 12460 | 1 | 5021701 | 26.4.002195 | 800223.V | 112457/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
110 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002195 | 800223.V | 112457/1.V | 12460 | 1 | 5021701 | 26.4.002196 | 780325.V | 112402/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
111 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002196 | 780325.V | 112402/1.V | 12450 | 1 | 5021701 | 26.4.002197 | 780325.V | 112400/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
112 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002197 | 780325.V | 112400/1.V | 12460 | 1 | 5021701 | 26.4.002198 | 780325.V | 112398/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
113 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002198 | 780325.V | 112398/1.V | 12450 | 1 | 5021701 | 26.4.002199 | 780325.V | 112398/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
114 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002199 | 780325.V | 112398/2.V | 12450 | 1 | 5021701 | 26.4.002200 | 780325.V | 112410/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
115 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002200 | 780325.V | 112410/2.V | 12470 | 1 | 5021701 | 26.4.002201 | 780325.V | 112409/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
116 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002201 | 780325.V | 112409/1.V | 12450 | 1 | 5021701 | 26.4.002202 | 780325.V | 112407/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
117 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002202 | 780325.V | 112407/1.V | 12450 | 1 | 5021701 | 26.4.002203 | 780325.V | 112410/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
118 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002203 | 780325.V | 112410/1.V | 12450 | 1 | 5021701 | 26.4.002204 | 800222.V | 112448/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
119 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002204 | 800222.V | 112448/1.V | 12460 | 1 | 5021701 | 26.4.002205 | 800222.V | 112449/1.V | 12460 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA
120 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002205 | 800222.V | 112449/1.V | 12460 | 1 | 5021701 | 26.4.002206 | 800222.V | 112448/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
121 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002206 | 800222.V | 112448/2.V | 12480 | 1 | 5021701 | 26.4.002207 | 800222.V | 112452/1.V | 12460 | EC | PU | SEL | SI | SE | U1
122 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002207 | 800222.V | 112452/1.V | 12450 | 1 | 5021701 | 26.4.002208 | 800222.V | 112447/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
123 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002208 | 800222.V | 112447/2.V | 12470 | 1 | 5021701 | 26.4.002209 | 800222.V | 112446/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
124 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002209 | 800222.V | 112446/1.V | 12460 | 1 | 5021701 | 26.4.002145 | 800233.V | 112486/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
125 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002210 | 800222.V | 112446/2.V | 12450 | 1 | 5021701 | 26.4.002110 | 800229.V | 112423/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
126 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002087 | 800229.V | 112432/2.V | 12470 | 1 | 5021701 | 26.4.002213 | 974062.V | 112475/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
127 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002212 | 974062.V | 112471/2.V | 12470 | 1 | 5021701 | 26.4.002212 | 974062.V | 112471/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
128 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002213 | 974062.V | 112475/2.V | 12460 | 1 | 5021701 | 26.4.002144 | 800233.V | 112484/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
129 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002214 | 974062.V | 112473/1.V | 12460 | 1 | 5021701 | 26.4.002215 | 974062.V | 112477/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
130 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002215 | 974062.V | 112477/1.V | 12460 | 1 | 5021701 | 26.4.002216 | 974062.V | 112476/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
131 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002216 | 974062.V | 112476/1.V | 12460 | 1 | 5021701 | 26.4.002217 | 974062.V | 112476/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
132 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002217 | 974062.V | 112476/2.V | 12460 | 1 | 5021701 | 26.4.002218 | 974062.V | 112474/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
133 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002218 | 974062.V | 112474/2.V | 12370 | 1 | 5021701 | 26.4.002219 | 974062.V | 112474/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
134 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002219 | 974062.V | 112474/1.V | 12460 | 1 | 5021701 | 26.4.002220 | 974062.V | 112470/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
135 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002220 | 974062.V | 112470/1.V | 12470 | 1 | 5021701 | 26.4.002221 | 974062.V | 112471/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
136 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002221 | 974062.V | 112471/1.V | 12450 | 1 | 5021701 | 26.4.002222 | 974062.V | 112480/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
137 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002222 | 974062.V | 112480/2.V | 12450 | 1 | 5021701 | 26.4.002223 | 974062.V | 112472/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
138 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002223 | 974062.V | 112472/2.V | 12380 | 1 | 5021701 | 26.4.002224 | 974062.V | 112473/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
139 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002224 | 974062.V | 112473/2.V | 12450 | 1 | 5021701 | 26.4.002225 | 974062.V | 112478/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
140 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002225 | 974062.V | 112478/2.V | 12450 | 1 | 5021701 | 26.4.002226 | 974062.V | 112469/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
141 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002226 | 974062.V | 112469/2.V | 12450 | 1 | 5021701 | 26.4.002227 | 974062.V | 112482/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
142 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002227 | 974062.V | 112482/2.V | 12450 | 1 | 5021701 | 26.4.002228 | 974062.V | 112479/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
143 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002228 | 974062.V | 112479/1.V | 12460 | 1 | 5021701 | 26.4.002229 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
144 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002229 | 974062.V | 112469/1.V | 12450 | 1 | 5021701 | 26.4.002230 | 974062.V | 112475/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
145 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002230 | 974062.V | 112475/1.V | 12450 | 1 | 5021701 | 26.4.002231 | 974062.V | 112479/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
146 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002231 | 974062.V | 112479/2.V | 12450 | 1 | 5021701 | 26.4.002232 | 974062.V | 112477/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
147 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002232 | 974062.V | 112477/2.V | 12470 | 1 | 5021701 | 26.4.002233 | 974062.V | 112472/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
148 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002233 | 974062.V | 112472/1.V | 12470 | 1 | 5021701 | 26.4.002234 | 800222.V | 112450/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
149 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002234 | 800222.V | 112450/1.V | 12450 | 1 | 5021701 | 26.4.002235 | 800222.V | 112451/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
150 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002235 | 800222.V | 112451/1.V | 12450 | 1 | 5021701 | 26.4.002236 | 974058.V | 112417/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
151 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002236 | 974058.V | 112417/1.V | 12470 | 1 | 5021701 | 26.4.002237 | 974058.V | 112413/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
152 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002237 | 974058.V | 112413/2.V | 12480 | 1 | 5021701 | 26.4.002239 | 974058.V | 112416/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
153 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002238 | 974058.V | 112416/1.V | 12460 | 1 | 5021701 | 26.4.002240 | 974058.V | 113145/2.V | 12210 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  |  | TH | UTPA | UTMAN
154 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002239 | 974058.V | 112416/2.V | 12470 | 1 | 5021701 | 26.4.002241 | 974058.V | 112415/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
155 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002240 | 974058.V | 113145/2.V | 12450 | 1 | 5021701 | 26.4.002242 | 974058.V | 112418/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
156 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002241 | 974058.V | 112415/2.V | 12450 | 1 | 5021701 | 26.4.007880 | 800957.V | 119869/1A.V | 12450 | EC
157 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002242 | 974058.V | 112418/1.V | 12450 | 1 | 5021701 | 26.4.002244 | 800222.V | 112450/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
158 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002243 | 974058.V | 113145/1.V | 12450 | 1 | 5021701 | 26.4.002245 | 800222.V | 112452/2.V | 11810 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
159 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002244 | 800222.V | 112450/2.V | 12450 | 1 | 5021701 | 26.4.002246 | 800222.V | 112453/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
160 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002245 | 800222.V | 112452/2.V | 12470 | 1 | 5021701 | 26.4.002247 | 800222.V | 112451/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
161 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002246 | 800222.V | 112453/2.V | 12480 | 1 | 5021701 | 26.4.002248 | 974058.V | 112415/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
162 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002247 | 800222.V | 112451/2.V | 12470 | 1 | 5021701 | 26.4.002249 | 800222.V | 112449/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
163 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002248 | 974058.V | 112415/1.V | 12450 | 1 | 5021701 | 26.4.002251 | 974058.V | 112417/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
164 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002249 | 800222.V | 112449/2.V | 12450 | 1 | 5021701 | 26.4.002252 | 974058.V | 112418/2.V | 12470 | EC | PU | SEL | SI | SE | U1
165 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002250 | 974058.V | 112414/1.V | 12460 | 1 | 5021701 | 26.4.002253 | 974058.V | 112414/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
166 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002251 | 974058.V | 112417/2.V | 12460 | 1 | 5021701 | 26.4.002254 | 974058.V | 112413/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
167 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002252 | 974058.V | 112418/2.V | 12450 | 1 | 5021701 | 26.4.007729 | 781283.V | 121411/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
168 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002253 | 974058.V | 112414/2.V | 12450 | 1 | 5021701 | 26.4.007730 | 781283.V | 121418/1.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
169 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002254 | 974058.V | 112413/1.V | 12450 | 1 | 5021701 | 26.4.007731 | 781283.V | 121419/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
170 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002169 | 780325.V | 112406/1.V | 12470 | 1 | 5021701 | 26.4.007732 | 781283.V | 121409/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007733 | 781283.V | 121420/1.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.007734 | 781283.V | 121420/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007735 | 781283.V | 121415/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.007736 | 781283.V | 121416/2.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007737 | 781283.V | 121416/1.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.007738 | 781283.V | 121415/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007739 | 801208.V | 122028/2.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007740 | 801208.V | 122028/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007741 | 801208.V | 122018/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007742 | 801208.V | 122025/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007743 | 801208.V | 122021/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007744 | 801208.V | 122025/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007745 | 801208.V | 122022/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007746 | 781283.V | 121407/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007747 | 781283.V | 121407/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.007748 | 781283.V | 121418/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007749 | 801208.V | 122027/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007944 | 801198.V | 121320/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007751 | 801208.V | 122031/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007752 | 801208.V | 122023/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007753 | 801208.V | 122023/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007754 | 801208.V | 122022/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007755 | 801208.V | 122019/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007756 | 781283.V | 121412/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007757 | 801208.V | 122018/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007758 | 801208.V | 122021/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007759 | 781283.V | 121408/2.V | 12370 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007760 | 781283.V | 121419/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007761 | 781283.V | 121414/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX
[9 empty] | 5021701 | 26.4.007762 | 781283.V | 121410/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007763 | 781283.V | 121411/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007765 | 781283.V | 121413/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007767 | 781283.V | 121409/1.V | 12370 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007977 | 780993.V | 118565/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007769 | 781283.V | 121414/1.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007770 | 781283.V | 121408/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007771 | 801208.V | 122029/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007772 | 801208.V | 122029/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007773 | 801208.V | 122027/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.002132 | 800232.V | 112440/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.002189 | 800223.V | 112456/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007776 | 801208.V | 122020/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007777 | 801208.V | 122031/2.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007778 | 801208.V | 122019/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007779 | 801208.V | 122024/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007780 | 801208.V | 122024/1A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007781 | 781297.V | 121333/2.V | 12470 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.007782 | 781297.V | 121339/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007783 | 781297.V | 121334/2.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.007819 | 781297.V | 121342/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007785 | 781297.V | 121337/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007786 | 781297.V | 121333/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007787 | 781297.V | 121338/1A.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007788 | 781297.V | 121344/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007789 | 781297.V | 121336/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007790 | 781297.V | 121344/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007791 | 974992.V | 122002/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007792 | 974992.V | 122006/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007793 | 974992.V | 122004/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007794 | 974992.V | 122003/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007795 | 781297.V | 121342/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007796 | 974992.V | 122003/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007797 | 781297.V | 121345/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007798 | 781297.V | 121341/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007799 | 781297.V | 121338/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007800 | 781297.V | 121340/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007801 | 781297.V | 121339/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007802 | 781297.V | 121346/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007803 | 781297.V | 121340/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007804 | 974992.V | 122005/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007805 | 974992.V | 122005/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007806 | 974992.V | 121999/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007807 | 974992.V | 122000/2.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007808 | 974992.V | 122001/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007809 | 974992.V | 122004/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007810 | 974992.V | 122006/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007811 | 974992.V | 122002/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007812 | 974992.V | 122000/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.007813 | 974992.V | 121999/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007814 | 974992.V | 122001/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007815 | 781297.V | 121335/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007818 | 781297.V | 121337/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.002211 | 800222.V | 112447/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007817 | 781297.V | 121334/1A.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007816 | 781297.V | 121335/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007820 | 781297.V | 121336/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007821 | 781297.V | 121346/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH
[9 empty] | 5021701 | 26.4.007822 | 975002.V | 121360/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007823 | 801219.V | 122060/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007824 | 801219.V | 122063/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007825 | 801219.V | 122066/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007826 | 801219.V | 122066/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007827 | 975002.V | 121354/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007828 | 975002.V | 121350/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007829 | 975002.V | 121350/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007830 | 975002.V | 121358/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007831 | 975002.V | 121358/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007832 | 801219.V | 122071/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007833 | 801219.V | 122069/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007834 | 801219.V | 122073/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007835 | 975002.V | 121347/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007836 | 975002.V | 121356/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007837 | 975002.V | 121356/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007838 | 975002.V | 121360/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007839 | 975002.V | 121352/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007840 | 975002.V | 121355/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007841 | 975002.V | 121357/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007842 | 975002.V | 121353/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007843 | 975002.V | 121351/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007844 | 975002.V | 121351/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007845 | 801219.V | 122072/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007846 | 801219.V | 122072/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007847 | 801219.V | 122067/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007848 | 801219.V | 122071/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007849 | 801219.V | 122070/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007850 | 801219.V | 122073/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007851 | 801219.V | 122065/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007852 | 801219.V | 122061/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.007853 | 801219.V | 122062/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.007854 | 801219.V | 122062/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007855 | 801219.V | 122064/2.V | 12470 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.007856 | 801219.V | 122068/2.V | 12450 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.007857 | 801219.V | 122068/1.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.007858 | 801219.V | 122069/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.007859 | 975002.V | 121347/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.007860 | 975002.V | 121353/1A.V | 12470 | EC | PU
[9 empty] | 5021701 | 26.4.007861 | 975002.V | 121348/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.007862 | 975002.V | 121355/1A.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.007863 | 975002.V | 121352/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.007864 | 975002.V | 121359/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007865 | 975002.V | 121354/1A.V | 12470 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.007866 | 801219.V | 122065/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.007867 | 801219.V | 122064/1A.V | 12470 | EC | PU
[9 empty] | 5021701 | 26.4.007868 | 801219.V | 122067/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007869 | 801219.V | 122061/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007870 | 801219.V | 122060/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.007871 | 801219.V | 122070/1.V | 12470 | EC | PU
[9 empty] | 5021701 | 26.4.007872 | 801219.V | 122063/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007873 | 975002.V | 121359/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007874 | 975002.V | 121349/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007875 | 975002.V | 121349/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007876 | 800957.V | 119868/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007877 | 800957.V | 119873/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007878 | 800943.V | 119469/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007879 | 800943.V | 119476/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.002210 | 800222.V | 112446/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007881 | 800943.V | 119477/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007882 | 800943.V | 119471/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007883 | 800957.V | 119862/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007884 | 800943.V | 119475/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007885 | 800943.V | 119474/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007886 | 800957.V | 119867/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007887 | 800957.V | 119862/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007888 | 800957.V | 119866/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007889 | 800957.V | 119871/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007890 | 800943.V | 119464/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007891 | 800957.V | 119867/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007892 | 800957.V | 119870/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007893 | 800957.V | 119869/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007894 | 800957.V | 119872/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007895 | 800943.V | 119471/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007896 | 800943.V | 119466/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007897 | 800943.V | 119470/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007898 | 800943.V | 119470/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007899 | 800957.V | 119866/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007900 | 800943.V | 119465/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007901 | 800943.V | 119465/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007902 | 800957.V | 119871/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007903 | 800957.V | 119870/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007904 | 800943.V | 119464/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007905 | 800957.V | 119873/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007906 | 800943.V | 119473/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007907 | 800957.V | 119863/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007908 | 800943.V | 119468/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007909 | 800943.V | 119474/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007910 | 800943.V | 119467/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007911 | 800957.V | 119875/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007912 | 800957.V | 119865/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007913 | 800957.V | 119874/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007914 | 800957.V | 119875/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007915 | 800957.V | 119865/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007916 | 800957.V | 119868/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007917 | 800943.V | 119476/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007918 | 800943.V | 119477/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007919 | 800957.V | 119864/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007920 | 800943.V | 119468/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007921 | 800943.V | 119466/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007922 | 800957.V | 119874/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007923 | 800943.V | 119469/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007924 | 800957.V | 119863/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007925 | 800957.V | 119872/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007926 | 800943.V | 119467/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007927 | 800943.V | 119472/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007928 | 800957.V | 119864/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007929 | 800943.V | 119475/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007930 | 800943.V | 119472/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007931 | 801198.V | 121322/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007932 | 801198.V | 121324/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007933 | 801198.V | 121319/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007934 | 801198.V | 121319/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007935 | 801198.V | 121332/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007936 | 801198.V | 121327/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007937 | 801198.V | 121322/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007938 | 801198.V | 121328/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007939 | 801198.V | 121328/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007940 | 801198.V | 121329/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007941 | 801198.V | 121323/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007942 | 801198.V | 121320/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007943 | 801198.V | 121331/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.002143 | 800232.V | 112442/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007945 | 801198.V | 121323/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007946 | 801198.V | 121329/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007947 | 801198.V | 121332/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007948 | 801198.V | 121327/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007949 | 801198.V | 121326/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007950 | 801198.V | 121331/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007951 | 801198.V | 121330/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007952 | 801198.V | 121330/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007953 | 780993.V | 118572/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007954 | 780993.V | 118569/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007955 | 780993.V | 118570/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007956 | 780993.V | 118562/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007957 | 801198.V | 121321/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007958 | 801198.V | 121321/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007959 | 801198.V | 121325/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007960 | 801198.V | 121325/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007961 | 780993.V | 118572/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007962 | 780993.V | 118564/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007963 | 780993.V | 118568/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007964 | 780993.V | 118574/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007965 | 780993.V | 118573/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007966 | 780993.V | 118570/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007967 | 780993.V | 118562/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007968 | 780993.V | 118569/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007969 | 780993.V | 118564/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007970 | 801198.V | 121324/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007971 | 801198.V | 121326/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007972 | 780993.V | 118563/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007973 | 780993.V | 118563/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007974 | 780993.V | 118566/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007975 | 780993.V | 118567/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.002109 | 800229.V | 112428/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.002093 | 800229.V | 112425/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007978 | 780993.V | 118566/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007979 | 780993.V | 118567/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007980 | 780993.V | 118571/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007981 | 780993.V | 118573/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007982 | 780993.V | 118568/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007983 | 780993.V | 118571/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007984 | 780993.V | 118561/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007985 | 780993.V | 118561/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007986 | 780993.V | 118574/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.900028 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.900029 | 974062.V | 112469/1.V | 3540 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA
[9 empty] | 5021701 | 26.4.007774 | 781283.V | 121410/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX
[9 empty] | DT03610322 | 26.4.002117 | 800233.V | 112490/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | BA

## Pivot
| PO 5021701 | [7 empty] | PO 5021701 Totale | Totale complessivo
| 780325.V | 800222.V | 800223.V | 800229.V | 800232.V | 800233.V | 974058.V | 974062.V
ITP Steps.
Incoming Plate | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Pipe Forming | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Tack Welding | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
ID SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
OD SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
AUT1 | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Fluoroscopic |  |  | 3 | 1 | 1 | 1 | 4 | 2 | 12 | 12
Welding Repair |  | 2 |  | 1 |  |  | 1 |  | 4 | 4
MCE1 | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
MCE2
MCE Inspection | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
Straighness Re-work | 1 |  | 2 | 2 |  |  | 1 |  | 6 | 6
Hydro Test | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
AUT2
Phase Arr. | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
MUT_ | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
End UT | 27 | 13 | 19 | 17 | 24 | 16 | 15 | 26 | 157 | 157
X-Ray | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
OoR Pipe Body | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
Dimensional 1 | 25 | 12 | 18 | 15 | 24 | 16 | 15 | 25 | 150 | 150
Dimensional 2 | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
MPI | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
UT DHC | 25 | 12 | 17 | 15 | 24 | 16 | 14 | 24 | 147 | 147
Final Marking and Weighing | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149

## Chart
Este gráfico não está disponível na sua versão de Excel. Editar esta forma ou salvar esta pasta de trabalho em um formato de arquivo diferente quebrará o gráfico permanentemente.

## Repair
24OD x 1.268WT
REPAIR TABLE
DATE | Shift | Pipe Nº | Defect | Pipe Position (mm) | Extension (mm) | Remarks
2026-02-11 | 1 | 26.4.2089 | Weld heigh bead below the specified | 1200 | 300
2026-02-19 | 1 | 26.4.2205 | OD Slag Inclusion | 1450 | 100
2026-02-20 | 1 | 26.4.2207 | OD Underfill | 5510 | 130
2026-02-21 | 1 | 26.4.2252 | ID Stop/Start | 2320 | 200

## Rejection
24OD x 1.268WT
REJECTION TABLE
DATE | Shift | Pipe Nº | Defect | Remarks
2026-02-11 | 1 | 26.4.2095 | Burn Through | MPQT Pipe (NCR-001)
2026-02-23 | 1 | 26.4.2094 | Pore | 2350x50mm
2026-02-23 | 1 | 26.4.2250 | WT Below Spec | 8100x640mm
2026-03-10 | 1 | 26.4.2114 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2185 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2107 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2145 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2148 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2144 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2149 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2180 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2115 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2086 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-04-22 | 1 | 26.4.2156 | Sample Removal | NA
2026-05-19 | 1 | 26.4.2117 | CVN Rejection | (NCR-004)
2026-06-02 | 2 | 26.4.7733 | Tack Weld Parametert | NA