## Dashboard
SAKARYA PROJECT - INSPECTION & TEST PLAN — PIPE PRODUCTION TRACKING
Input | 170
Seq. n° | ITP Step | Section | Count | Yield vs Input | Loss vs Input | Cumul. Loss | Remarks
1 | Incoming Plate | Forming | 170 | 100% | 0 | 0
2 | Pipe Forming | Forming | 170 | 100% | 0 | 0
3 | Tack Welding | Forming | 170 | 100% | 0 | 0
4 | ID SAWL | Forming | 170 | 100% | 0 | 0
5 | OD SAWL | Forming | 170 | 100% | 0 | 0
6 | AUT1 | Welding & NDT | 170 | 100% | 0 | 0
7 | Fluoroscopic | Welding & NDT | 12 | 7.059% | 158 | 158
8 | Welding Repair | Welding & NDT | 4 | 2.353% | 4 | 4
9 | MCE1 | Mechanical | 164 | 96.47% | 6 | 6
10 | MCE2 | Mechanical | 0 | — | — | —
11 | MCE Inspection | Mechanical | 164 | 96.47% | 6 | 6
12 | Straightness Re-work | Mechanical | 6 | — | — | —
13 | Hydro Test | Testing | 158 | 92.94% | 12 | 12
14 | AUT2 | Testing | 0 | — | — | —
15 | Phase Arr. | Testing | 158 | 92.94% | 12 | 12
16 | MUT | Testing | 158 | 92.94% | 12 | 12
17 | End UT | Testing | 157 | 92.35% | 13 | 13
18 | X-Ray | Testing | 156 | 91.76% | 14 | 14
19 | OoR Pipe Body | Dimensional & Final | 156 | 91.76% | 14 | 14
20 | Dimensional 1 | Dimensional & Final | 150 | 88.24% | 20 | 20
21 | Dimensional 2 | Dimensional & Final | 149 | 87.65% | 21 | 21
22 | MPI | Dimensional & Final | 149 | 87.65% | 21 | 21
23 | UT DHC | Dimensional & Final | 147 | 86.47% | 23 | 23
24 | Final Mark & Weigh | Dimensional & Final | 149 | 87.65% | 21 | 21
SUMMARY
Total Pipes |  |  |  | 170
Total pipes Accepted |  |  |  | 149
Overall Status % |  |  |  | 87.65%
Welding Repair |  |  |  | 47

## MPQT - WPQT
Overview MPQT / WPQT SAWL Line Pipe - Lab Tests Control Table SAKARYA PROJECT
OD X WT (in X in) | WPS Nº | Pipe Nº | Heat N° | Tenaris Labs Report | Chemical Compos. Analysis |  | Tensile Tests | [8 empty] | Transversal Compression Test |  | BM CVN Impact Testing -30°C |  | CVN Impact Testing of the Weld Seam @ -30°C | [12 empty] | CVN Impact Testing Transition Curve Base Metal @ +20°C to -120°C |  | Drop Weight Tear Testing (DWTT) |  | CTOD (AF) |  |  | CTOD (AC) |  |  | Grain Size BM | Guided Bend Tests |  |  | VicKers Hardness Tests |  |  | Macrographic Test | Flux Humidity (Karl Fischer) | Ring Splitting Test |  | HIC |  | SSC |  | Remarks
[5 empty] | BM | WM | Longitudinal BM | Longitudinal BM (Coated) | Transversal BM | Transversal BM (Coated) | Transversal WM | Transversal WM (DNV) | Transversal WM (Coated) | ID and OD All Weld | All Weld (Coated) | Without Inline Heat Treatment | Inline Heat Treatment (Coated) | AF | Coated | OD Weld Metal | OD Weld FL | OD Weld FL +2mm | OD Weld FL +5mm | Root Weld Metal | Root Weld FL | Root Weld FL +2mm | Root Weld FL +5mm | ID Weld Metal | ID Weld FL | ID Weld FL +2mm | ID Weld FL +5mm | WM (Coated) | AF | AF (Aged) | AF | Transition Curve | BM | WM | HAZ | BM | WM | HAZ |  | OD | ID | Side | BM | HAZ | WM | Interpenetration | WPQT | AF | AC | BM | WM | BM | WM
[5 empty] | 1/Pipe |  | All | All | All | All | All | WPQT Pipes | All | All | All | All |  | All |  | All | [12 empty] | All |  | All |  | All |  |  | All |  |  | All | All |  |  | All |  |  | All |  | All | All | All
24 x 1.268 | 3973 | 26.4.002096 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Border Line *CVN ID Fusino Line Rejected with single results 26J. *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002097 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *CVN ID Fusino Line Rejected with single results 29J *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002098 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10
| 3974 | 26.4.002240 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *ReTest performed as per NCR-003 and approved
| 3973 | 26.4.002099 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002100 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A
| 3973 | 26.4.002101 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002243 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
Repair Qualification
24 x 1.268 (STOP/START) | WPS-3973 | 26.4. 2128 (INT) | 800232.V |  |  |  | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-19 |  |  | N/A | IR-19 |  |  | N/A | IR-19 | IR-19 | IR-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | IR-18 | IR-18 | IR-18 | IR-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 26.4.2128 (EXT) |  |  |  |  | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-19 | IR-19 | IR-19 | N/A | IR-19 |  |  | N/A | IR-19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | IR-18 | IR-18 | IR-18 | IR-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OD 24 x 1.268 (rWPS) | WPS-265 (SHALLOW) | 26.4. 2128 |  |  |  |  | N/A | N/A | N/A | N/A | IR-20 |  | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-20 | IR-20 | IR-20 | IR-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-20 | [6 empty] | N/A |  | N/A | N/A | N/A | N/A | Started on Jun. 18th 2026
| WPS-266 (DEEP) | [5 empty] | N/A | N/A | N/A | N/A | IR-20 |  | N/A | IR-20 | N/A | N/A | N/A | N/A | N/A | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | IR-20 |  |  |  |  | N/A |  | N/A | N/A | N/A | N/A | Started on Jun. 18th 2026
ID 24 x 1.268 (rWPS) | WPS-265 (SHALLOW) | 26.4. 2205 | 800222.V |  |  |  | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
| WPS-266 (DEEP) | [5 empty] | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A

## 24 X 1.268 OFF
SAKARYA PROJECT - Overview Mass Production for SAWL Line Pipe - Lab Tests Control Table
OD24in X WT1.268in
OD X WT | Pipe Nº | Heat Plate N° | Chemical Compos. Analysis |  | Tensile Tests |  |  |  | Transversal Compression Test | BM CVN Impact Testing -30°C | CVN Impact Testing of the Weld Seam @ -30°C | [8 empty] | Drop Weight Tear Testing (DWTT) | Grain Size BM | Guided Bend Tests |  | VicKers Hardness Tests |  |  | Macrographic Test | HIC |  | Remarks
|  |  | BM | BM | Longitudinal BM | Transversal BM | Transversal WM | Transversal WM (Coated) | Inline Heat Treatment | AF | WM OD | WD ID | WM Root | FL OD | FL ID | FL Root | FL + 2 OD | FL + 2 ID | FL + 2 Root | BM |  | OD | ID | BM | HAZ | WM | Interpenetration | BM | WM
|  |  | 1/Pipe |  | 1/Heat | 1/Heat | 1/Heat | All | 4/Heat 20 1/Heat | 1/Heat | 1/Heat | [8 empty] | 1/Heat | 1 / 5 Heats | 1/Heat |  | 1/Heat |  |  | 1/Shift | 1 /Heat (first five Heat, than 1 / 10)
36 x 0.406 | 11646 | 780325 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at OD FL+2mm (NCR-004) - Re-test performed and approved
|  | 800222 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio FL (NCR-004) - Re-test performed and approved
|  | 800229 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersection, on the NCR-004 Tenaris have informed that the CVN specimen of Intersevtion WM, was with the notch on the wrong sectiom and it is a FL Re-test performed and approved
|  | 800232 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08
|  | 800233 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 IR-15 IR-17 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio ID and OD FL (NCR-004) - Re-test performed Rejected on the same pipe (26.4.2117). Retest Performed and approved in two addtional Pipes from the same Test unit and approved (26.4.2147 and 2152)
|  | 974062 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08
|  | 780991 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 780992 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20
|  | 780993 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 780995 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20
|  | 781083 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 781283 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-20 | IR-19 | IR-20 | IR-19 | IR-19 | IR-19 |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 781297 | IR-19 | IR-19 |  | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 |  |  | IR-20 | IR-20 |  |  |  | IR-20
800223
|  | 800943 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  | IR-20 |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 800957 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 800958 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 800959 | IR-20 | IR-20 |  | IR-20 | IR-20 | [6 empty] | IR-20 |  | IR-20 | [5 empty] | IR-20 | IR-20
|  | 800965 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20
|  | 800970 | IR-20 | IR-20 |  | IR-20 | IR-20 |  |  |  |  | IR-20 |  | IR-20 | IR-20 | IR-20 |  | IR-20 |  |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 801169 | IR-20 | IR-20 |  | IR-20 | IR-20 | [14 empty] | IR-20 | IR-20 |  |  |  | IR-20
|  | 801174 | IR-20 | IR-20 |  | IR-20 | IR-20 | [6 empty] | IR-20 | IR-20 | [6 empty] | IR-20 | IR-20
|  | 801198 | IR-20 |  | IR-20 |  |  |  |  | IR-20 | IR-20 | IR-20 | IR-20 |  | IR-20 | IR-19 | IR-20 | IR-20 | IR-20 | [7 empty] | IR-20
|  | 801208 | IR-19 | IR-19 |  | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 801219 | IR-19 | IR-19 | IR-20 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
974058
|  | 974992 | IR-19 | IR-20 |  | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-20 | IR-19 | IR-20 | IR-20 | IR-20 | IR-19 | IR-20 | IR-19 |  |  | IR-20 | IR-20
|  | 975002 | IR-19 | IR-20 |  | IR-20 | IR-20 |  |  |  |  | IR-19 |  | IR-19 | IR-19 | IR-19 |  | IR-19 |  |  |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 781062 | IR-20 | IR-20 |  | IR-20 | IR-20 | [14 empty] | IR-20 | IR-20 |  |  |  | IR-20
|  | 975015 | IR-20 | IR-20 |  | IR-20 | IR-20 | [14 empty] | IR-20 | IR-20
|  | 975011 | [24 empty] | IR-20
|  | 800848 |  |  | IR-20
|  | 800964 |  |  | IR-20

## PO5021701
Totale | [7 empty] | 170 |  |  |  |  | 0 | 1428 | 1298 | 1291 | 1265 | 1251 | 1244 | 14 | 34 | 898 | 1215 | 19 | 1208 | 1182 | 1168 | 1147 | 1145 | 1144 | 1122 | 1012 | 1004 | 1005 | 286
Seq. N° | Tenaris Batch | Pipe Dimensional | Pipe Std | Pipe Number | Heat Number | Plate Number | Pipe length | Total Pipes | Tenaris Lote | Pipe N° | Heat N° | Plate N° | Pipe length2 | Plate Entrance | Pipe Forming | Tack Welding | ID SAWL | OD SAWL | AUT1 in House | Fluoroscopic/TOFD In House | Repair | MCE 1 | MCE 2 | Straighness Re-work | Hydrostatic Test | Phase Array | MUT | Pipe End UT | X-Ray | OoR Pipe Body | Dimensional 1 | Dimensional 2 | MPI | Final Marking and Weighing | UT DHC
1 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002086 | 800229.V | 112430/2.V | 12350 | 1 | 4RF0150217 | 26.4.008260 | 781062.V | 119452/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
2 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002211 | 800222.V | 112447/1.V | 12450 | 1 | 4RF0150217 | 26.4.007733 | 781283.V | 121420/1.V | 12460 | EC | PU | SEL
3 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002085 | 800229.V | 112426/2.V | 12380 | 1 | 4RF0150217 | 26.4.008270 | 781062.V | 119463/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
4 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002089 | 800229.V | 112427/1.V | 12470 | 1 | 4RF0150217 | 26.4.008264 | 781062.V | 119459/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
5 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002090 | 800229.V | 112432/1.V | 12360 | 1 | 4RF0150217 | 26.4.008200 | 801174.V | 120820/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
6 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002147 | 800233.V | 112487/2.V | 12460 | 1 | 4RF0150217 | 26.4.002250 | 974058.V | 112414/1.V | 12460 | EC | PU | SEL | SI | SE | U1
7 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002092 | 800229.V | 112424/1.V | 12360 | 1 | 4RF0150217 | 26.4.008576 | 800977.V | 119578/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
8 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002088 | 800229.V | 112426/1.V | 12430 | 1 | 4RF0150217 | 26.4.002156 | 780325.V | 112409/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
9 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002094 | 800229.V | 112430/1.V | 12470 | 1 | 4RF0150217 | 26.4.008265 | 781062.V | 119453/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
10 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002095 | 974058.V | 112411/1.V | 12460 | 1 | 4RF0150217 | 26.4.008267 | 781062.V | 119453/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
11 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002096 | 974058.V | 112412/2.V | 12470 | 1 | 4RF0150217 | 26.4.008247 | 975015.V | 121405/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
12 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002097 | 800223.V | 112460/1.V | 12370 | 1 | 4RF0150217 | 26.4.008275 | 781062.V | 119457/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
13 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002098 | 800223.V | 112459/2.V | 12370 | 1 | 4RF0150217 | 26.4.008206 | 801169.V | 120797/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX
14 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002115 | 800233.V | 112488/2.V | 12450 | 1 | 4RF0150217 | 26.4.008244 | 975015.V | 121399/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
15 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002100 | 800223.V | 112460/2.V | 12470 | 1 | 4RF0150217 | 26.4.008205 | 801169.V | 120797/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
16 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002101 | 974058.V | 112412/1.V | 12460 | 1 | 4RF0150217 | 26.4.008269 | 781062.V | 119455/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
17 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002102 | 974058.V | 112411/2.V | 12460 | 1 | 4RF0150217 | 26.4.008251 | 781062.V | 119452/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
18 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002103 | 800229.V | 112427/2.V | 12440 | 1 | 4RF0150217 | 26.4.008276 | 975015.V | 121396/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
19 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002093 | 800229.V | 112425/2.V | 12440 | 1 | 4RF0150217 | 26.4.008043 | 800965.V | 119508/1.V | 12470 | EC | PU | SEL | SI | SE | U1
20 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002105 | 800229.V | 112425/1.V | 12340 | 1 | 4RF0150217 | 26.4.008688 | 780939.V | 118434/1.V | 12460 | EC | PU | SEL | SI | SE
21 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002106 | 800229.V | 112422/2.V | 12320 | 1 | 4RF0150217 | 26.4.008190 | 801169.V | 120794/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
22 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002107 | 800229.V | 112423/2.V | 12370 | 1 | 4RF0150217 | 26.4.008250 | 781062.V | 119450/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
23 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002108 | 800229.V | 112424/2.V | 12330 | 1 | 4RF0150217 | 26.4.008273 | 781062.V | 119460/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
24 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002109 | 800229.V | 112428/2.V | 12470 | 1 | 4RF0150217 | 26.4.008185 | 801174.V | 120824/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
25 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002110 | 800229.V | 112423/1.V | 12300 | 1 | 4RF0150217 | 26.4.008181 | 801169.V | 120794/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
26 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002111 | 800229.V | 112431/1.V | 12440 | 1 | 4RF0150217 | 26.4.007859 | 975002.V | 121347/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
27 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002112 | 800229.V | 112428/1.V | 12440 | 1 | 4RF0150217 | 26.4.008208 | 801169.V | 120796/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
28 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002113 | 800229.V | 112429/2.V | 12470 | 1 | 4RF0150217 | 26.4.008201 | 801174.V | 120814/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
29 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002114 | 800233.V | 112487/1.V | 12450 | 1 | 4RF0150217 | 26.4.008266 | 781062.V | 119459/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
30 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002099 | 800223.V | 112459/1.V | 12460 | 1 | 4RF0150217 | 26.4.008194 | 801174.V | 120813/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
31 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002116 | 800233.V | 112485/2.V | 12020 | 1 | 5021601 | 26.4.002238 | 974058.V | 112416/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
32 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002117 | 800233.V | 112490/1.V | 12020 | 1 | 5021601 | 26.4.002170 | 780325.V | 112403/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
33 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002118 | 800232.V | 112444/2.V | 12470 | 1 | 5021601 | 26.4.002113 | 800229.V | 112429/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
34 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002119 | 800233.V | 112483/1.V | 12450 | 1 | 5021601 | 26.4.002179 | 800223.V | 112461/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
35 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002120 | 800232.V | 112437/2.V | 12450 | 1 | 5021601 | 26.4.002090 | 800229.V | 112432/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
36 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002121 | 800232.V | 112441/2.V | 12450 | 1 | 5021701 | 26.4.002111 | 800229.V | 112431/1.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
37 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002122 | 800232.V | 112434/2.V | 12450 | 1 | 5021701 | 26.4.002173 | 780325.V | 112399/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
38 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002123 | 800232.V | 112437/1.V | 12450 | 1 | 5021701 | 26.4.002109 | 800229.V | 112428/2.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
39 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002124 | 800232.V | 112436/2.V | 12450 | 1 | 5021701 | 26.4.002107 | 800229.V | 112423/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
40 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002125 | 800232.V | 112442/1.V | 12450 | 1 | 5021701 | 26.4.007756 | 781283.V | 121412/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
41 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002104 | 800229.V | 112429/1.V | 12430 | 1 | 5021701 | 26.4.002164 | 780325.V | 112408/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
42 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002127 | 800232.V | 112436/1.V | 12450 | 1 | 5021701 | 26.4.002105 | 800229.V | 112425/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
43 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002128 | 800232.V | 112434/1.V | 12450 | 1 | 5021701 | 26.4.002103 | 800229.V | 112427/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
44 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002129 | 800232.V | 112433/2.V | 12450 | 1 | 5021701 | 26.4.002155 | 780325.V | 112405/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
45 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002130 | 800232.V | 112444/1.V | 12450 | 1 | 5021701 | 26.4.002101 | 974058.V | 112412/1.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
46 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002131 | 800232.V | 112438/1.V | 12450 | 1 | 5021701 | 26.4.002100 | 800223.V | 112460/2.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
47 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002132 | 800232.V | 112440/2.V | 12450 | 1 | 5021701 | 26.4.002151 | 800233.V | 112485/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
48 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002133 | 800232.V | 112441/1.V | 12450 | 1 | 5021701 | 26.4.002099 | 800223.V | 112459/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
49 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002134 | 800232.V | 112443/2.V | 12450 | 1 | 5021701 | 26.4.002098 | 800223.V | 112459/2.V | 12340 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN
50 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002135 | 800232.V | 112445/2.V | 12450 | 1 | 5021701 | 26.4.007740 | 801208.V | 122028/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
51 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002136 | 800232.V | 112435/1.V | 12450 | 1 | 5021701 | 26.4.002102 | 974058.V | 112411/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
52 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002137 | 800232.V | 112445/1.V | 12450 | 1 | 5021701 | 26.4.002160 | 780325.V | 112397/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
53 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002138 | 800232.V | 112440/1.V | 12450 | 1 | 5021701 | 26.4.002104 | 800229.V | 112429/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
54 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002139 | 800232.V | 112435/2.V | 12450 | 1 | 5021701 | 26.4.007986 | 780993.V | 118574/2.V | 12460 | EC | PU | SEL |  |  |  |  | REP
55 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002140 | 800232.V | 112439/2.V | 12450 | 1 | 5021701 | 26.4.002106 | 800229.V | 112422/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
56 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002141 | 800232.V | 112438/2.V | 12450 | 1 | 5021701 | 26.4.002168 | 780325.V | 112401/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
57 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002142 | 800232.V | 112443/1.V | 12450 | 1 | 5021701 | 26.4.002108 | 800229.V | 112424/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
58 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002143 | 800232.V | 112442/2.V | 12450 | 1 | 5021701 | 26.4.007775 | 801208.V | 122020/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
59 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002144 | 800233.V | 112484/2.V | 12470 | 1 | 5021701 | 26.4.002110 | 800229.V | 112423/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
60 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002145 | 800233.V | 112486/1.V | 12470 | 1 | 5021701 | 26.4.002177 | 974062.V | 112481/2.V | 12440 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
61 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002146 | 800233.V | 112484/1.V | 12450 | 1 | 5021701 | 26.4.002112 | 800229.V | 112428/1.V | 12040 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
62 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002091 | 800229.V | 112431/2.V | 12360 | 1 | 5021701 | 26.4.008336 | 781068.V | 119539/1.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
63 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002148 | 800233.V | 112490/2.V | 12450 | 1 | 5021701 | 26.4.007921 | 800943.V | 119466/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
64 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002149 | 800233.V | 112483/2.V | 12450 | 1 | 5021701 | 26.4.002247 | 800222.V | 112451/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
65 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002150 | 800233.V | 112489/1.V | 12450 | 1 | 5021701 | 26.4.002147 | 800233.V | 112487/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
66 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002151 | 800233.V | 112485/1.V | 12450 | 1 | 5021701 | 26.4.002097 | 800223.V | 112460/1.V | 12300 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN
67 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002152 | 800233.V | 112489/2.V | 12450 | 1 | 5021701 | 26.4.002096 | 974058.V | 112412/2.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN
68 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002153 | 800233.V | 112486/2.V | 12450 | 1 | 5021701 | 26.4.002143 | 800232.V | 112442/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
69 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002154 | 780325.V | 112403/1.V | 12470 | 1 | 5021701 | 26.4.002095 | 974058.V | 112411/1.V | 12460 | EC | PU | SEL | SI | SE | U1
70 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002155 | 780325.V | 112405/2.V | 12450 | 1 | 5021701 | 26.4.002094 | 800229.V | 112430/1.V | 11360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE
71 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002156 | 780325.V | 112409/2.V | 12040 | 1 | 5021701 | 26.4.007889 | 800957.V | 119871/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
72 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002157 | 780325.V | 112406/2.V | 12480 | 1 | 5021701 | 26.4.002230 | 974062.V | 112475/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
73 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002158 | 780325.V | 112407/2.V | 12450 | 1 | 5021701 | 26.4.008278 | 781052.V | 119842/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
74 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002159 | 780325.V | 112405/1.V | 12450 | 1 | 5021701 | 26.4.002092 | 800229.V | 112424/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
75 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002160 | 780325.V | 112397/2.V | 12450 | 1 | 5021701 | 26.4.002135 | 800232.V | 112445/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
76 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002161 | 780325.V | 112404/2.V | 12450 | 1 | 5021701 | 26.4.002091 | 800229.V | 112431/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
77 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002162 | 800233.V | 112488/1.V | 12450 | 1 | 5021701 | 26.4.002134 | 800232.V | 112443/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
78 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002163 | 780325.V | 112404/1.V | 12450 | 1 | 5021701 | 26.4.002133 | 800232.V | 112441/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
79 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002164 | 780325.V | 112408/1.V | 12450 | 1 | 5021701 | 26.4.002089 | 800229.V | 112427/1.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
80 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002165 | 780325.V | 112408/2.V | 12450 | 1 | 5021701 | 26.4.002132 | 800232.V | 112440/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
81 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002166 | 780325.V | 112400/2.V | 12450 | 1 | 5021701 | 26.4.007856 | 801219.V | 122068/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
82 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002167 | 780325.V | 112399/2.V | 12450 | 1 | 5021701 | 26.4.002222 | 974062.V | 112480/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
83 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002168 | 780325.V | 112401/2.V | 12450 | 1 | 5021701 | 26.4.002136 | 800232.V | 112435/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
84 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002126 | 800232.V | 112439/1.V | 12450 | 1 | 5021701 | 26.4.002137 | 800232.V | 112445/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
85 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002170 | 780325.V | 112403/2.V | 12450 | 1 | 5021701 | 26.4.002138 | 800232.V | 112440/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
86 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002171 | 780325.V | 112401/1.V | 12070 | 1 | 5021701 | 26.4.008259 | 975015.V | 121395/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
87 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002172 | 780325.V | 112402/2.V | 12450 | 1 | 5021701 | 26.4.007893 | 800957.V | 119869/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
88 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002173 | 780325.V | 112399/1.V | 12450 | 1 | 5021701 | 26.4.002141 | 800232.V | 112438/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
89 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002174 | 974062.V | 112482/1.V | 12450 | 1 | 5021701 | 26.4.002142 | 800232.V | 112443/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
90 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002175 | 974062.V | 112470/2.V | 12450 | 1 | 5021701 | 26.4.002239 | 974058.V | 112416/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
91 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002176 | 974062.V | 112478/1.V | 12460 | 1 | 5021701 | 26.4.002144 | 800233.V | 112484/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
92 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002177 | 974062.V | 112481/2.V | 12460 | 1 | 5021701 | 26.4.002145 | 800233.V | 112486/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
93 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002178 | 800223.V | 112461/2.V | 12450 | 1 | 5021701 | 26.4.002146 | 800233.V | 112484/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
94 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002179 | 800223.V | 112461/1.V | 12460 | 1 | 5021701 | 26.4.008337 | 781085.V | 120895/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
95 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002180 | 800223.V | 112463/2.V | 12450 | 1 | 5021701 | 26.4.002148 | 800233.V | 112490/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
96 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002181 | 800223.V | 112464/2.V | 12460 | 1 | 5021701 | 26.4.002149 | 800233.V | 112483/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
97 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002182 | 800223.V | 112462/2.V | 12450 | 1 | 5021701 | 26.4.002150 | 800233.V | 112489/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
98 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002183 | 800223.V | 112458/2.V | 12450 | 1 | 5021701 | 26.4.007730 | 781283.V | 121418/1.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
99 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002184 | 800223.V | 112464/1.V | 12450 | 1 | 5021701 | 26.4.002152 | 800233.V | 112489/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
100 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002185 | 800223.V | 112463/1.V | 12450 | 1 | 5021701 | 26.4.002153 | 800233.V | 112486/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
101 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002186 | 800223.V | 112454/2.V | 12450 | 1 | 5021701 | 26.4.002154 | 780325.V | 112403/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
102 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002187 | 800223.V | 112458/1.V | 12470 | 1 | 5021701 | 26.4.007954 | 780993.V | 118569/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
103 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002188 | 800223.V | 112455/2.V | 12450 | 1 | 5021701 | 26.4.002157 | 780325.V | 112406/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
104 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002189 | 800223.V | 112456/1.V | 12460 | 1 | 5021701 | 26.4.002158 | 780325.V | 112407/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
105 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002190 | 800223.V | 112454/1.V | 12470 | 1 | 5021701 | 26.4.002159 | 780325.V | 112405/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
106 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002191 | 800223.V | 112462/1.V | 12460 | 1 | 5021701 | 26.4.007748 | 781283.V | 121418/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
107 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002192 | 800223.V | 112455/1.V | 12470 | 1 | 5021701 | 26.4.002161 | 780325.V | 112404/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
108 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002193 | 800223.V | 112457/2.V | 12450 | 1 | 5021701 | 26.4.002162 | 800233.V | 112488/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
109 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002194 | 780325.V | 112397/1.V | 12460 | 1 | 5021701 | 26.4.002163 | 780325.V | 112404/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
110 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002195 | 800223.V | 112457/1.V | 12460 | 1 | 5021701 | 26.4.008464 | 800848.V | 118432/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
111 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002196 | 780325.V | 112402/1.V | 12450 | 1 | 5021701 | 26.4.002165 | 780325.V | 112408/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
112 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002197 | 780325.V | 112400/1.V | 12460 | 1 | 5021701 | 26.4.002166 | 780325.V | 112400/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
113 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002198 | 780325.V | 112398/1.V | 12450 | 1 | 5021701 | 26.4.002167 | 780325.V | 112399/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
114 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002199 | 780325.V | 112398/2.V | 12450 | 1 | 5021701 | 26.4.007765 | 781283.V | 121413/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
115 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002200 | 780325.V | 112410/2.V | 12470 | 1 | 5021701 | 26.4.002169 | 780325.V | 112406/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
116 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002201 | 780325.V | 112409/1.V | 12450 | 1 | 5021701 | 26.4.002171 | 780325.V | 112401/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
117 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002202 | 780325.V | 112407/1.V | 12450 | 1 | 5021701 | 26.4.002172 | 780325.V | 112402/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
118 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002203 | 780325.V | 112410/1.V | 12450 | 1 | 5021701 | 26.4.008018 | 780992.V | 118293/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
119 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002204 | 800222.V | 112448/1.V | 12460 | 1 | 5021701 | 26.4.002174 | 974062.V | 112482/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
120 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002205 | 800222.V | 112449/1.V | 12460 | 1 | 5021701 | 26.4.002175 | 974062.V | 112470/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
121 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002206 | 800222.V | 112448/2.V | 12480 | 1 | 5021701 | 26.4.002176 | 974062.V | 112478/1.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
122 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002207 | 800222.V | 112452/1.V | 12450 | 1 | 5021701 | 26.4.007783 | 781297.V | 121334/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
123 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002208 | 800222.V | 112447/2.V | 12470 | 1 | 5021701 | 26.4.002178 | 800223.V | 112461/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
124 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002209 | 800222.V | 112446/1.V | 12460 | 1 | 5021701 | 26.4.002180 | 800223.V | 112463/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
125 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002210 | 800222.V | 112446/2.V | 12450 | 1 | 5021701 | 26.4.002181 | 800223.V | 112464/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
126 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002087 | 800229.V | 112432/2.V | 12470 | 1 | 5021701 | 26.4.002214 | 974062.V | 112473/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
127 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002212 | 974062.V | 112471/2.V | 12470 | 1 | 5021701 | 26.4.002131 | 800232.V | 112438/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
128 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002213 | 974062.V | 112475/2.V | 12460 | 1 | 5021701 | 26.4.002088 | 800229.V | 112426/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
129 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002214 | 974062.V | 112473/1.V | 12460 | 1 | 5021701 | 26.4.002231 | 974062.V | 112479/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
130 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002215 | 974062.V | 112477/1.V | 12460 | 1 | 5021701 | 26.4.002130 | 800232.V | 112444/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
131 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002216 | 974062.V | 112476/1.V | 12460 | 1 | 5021701 | 26.4.002129 | 800232.V | 112433/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
132 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002217 | 974062.V | 112476/2.V | 12460 | 1 | 5021701 | 26.4.002087 | 800229.V | 112432/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
133 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002218 | 974062.V | 112474/2.V | 12370 | 1 | 5021701 | 26.4.002128 | 800232.V | 112434/1.V | 12470 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA
134 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002219 | 974062.V | 112474/1.V | 12460 | 1 | 5021701 | 26.4.002206 | 800222.V | 112448/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
135 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002220 | 974062.V | 112470/1.V | 12470 | 1 | 5021701 | 26.4.002127 | 800232.V | 112436/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
136 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002221 | 974062.V | 112471/1.V | 12450 | 1 | 5021701 | 26.4.002086 | 800229.V | 112430/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
137 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002222 | 974062.V | 112480/2.V | 12450 | 1 | 5021701 | 26.4.002126 | 800232.V | 112439/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
138 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002223 | 974062.V | 112472/2.V | 12380 | 1 | 5021701 | 26.4.002125 | 800232.V | 112442/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
139 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002224 | 974062.V | 112473/2.V | 12450 | 1 | 5021701 | 26.4.002085 | 800229.V | 112426/2.V | 12130 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
140 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002225 | 974062.V | 112478/2.V | 12450 | 1 | 5021701 | 26.4.002201 | 780325.V | 112409/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
141 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002226 | 974062.V | 112469/2.V | 12450 | 1 | 5021701 | 26.4.002200 | 780325.V | 112410/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
142 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002227 | 974062.V | 112482/2.V | 12450 | 1 | 5021701 | 26.4.002124 | 800232.V | 112436/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
143 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002228 | 974062.V | 112479/1.V | 12460 | 1 | 5021701 | 26.4.002199 | 780325.V | 112398/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
144 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002229 | 974062.V | 112469/1.V | 12450 | 1 | 5021701 | 26.4.008723 | 800840.V | 118419/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
145 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002230 | 974062.V | 112475/1.V | 12450 | 1 | 5021701 | 26.4.008116 | 781083.V | 120864/1A.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
146 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002231 | 974062.V | 112479/2.V | 12450 | 1 | 5021701 | 26.4.002202 | 780325.V | 112407/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
147 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002232 | 974062.V | 112477/2.V | 12470 | 1 | 5021701 | 26.4.002203 | 780325.V | 112410/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
148 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002233 | 974062.V | 112472/1.V | 12470 | 1 | 5021701 | 26.4.002204 | 800222.V | 112448/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
149 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002234 | 800222.V | 112450/1.V | 12450 | 1 | 5021701 | 26.4.002205 | 800222.V | 112449/1.V | 12460 | EC | PU | SEL | SI | SE | U1 | FL | REP | SMS | EX2 |  | TH | UTPA
150 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002235 | 800222.V | 112451/1.V | 12450 | 1 | 5021701 | 26.4.007839 | 975002.V | 121352/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
151 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002236 | 974058.V | 112417/1.V | 12470 | 1 | 5021701 | 26.4.002207 | 800222.V | 112452/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
152 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002237 | 974058.V | 112413/2.V | 12480 | 1 | 5021701 | 26.4.002208 | 800222.V | 112447/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
153 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002238 | 974058.V | 112416/1.V | 12460 | 1 | 5021701 | 26.4.002209 | 800222.V | 112446/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
154 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002239 | 974058.V | 112416/2.V | 12470 | 1 | 5021701 | 26.4.002210 | 800222.V | 112446/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
155 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002240 | 974058.V | 113145/2.V | 12450 | 1 | 5021701 | 26.4.002211 | 800222.V | 112447/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
156 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002241 | 974058.V | 112415/2.V | 12450 | 1 | 5021701 | 26.4.002212 | 974062.V | 112471/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
157 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002242 | 974058.V | 112418/1.V | 12450 | 1 | 5021701 | 26.4.002213 | 974062.V | 112475/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
158 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002243 | 974058.V | 113145/1.V | 12450 | 1 | 5021701 | 26.4.008180 | 800958.V | 119480/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
159 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002244 | 800222.V | 112450/2.V | 12450 | 1 | 5021701 | 26.4.002215 | 974062.V | 112477/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
160 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002245 | 800222.V | 112452/2.V | 12470 | 1 | 5021701 | 26.4.002216 | 974062.V | 112476/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
161 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002246 | 800222.V | 112453/2.V | 12480 | 1 | 5021701 | 26.4.002217 | 974062.V | 112476/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
162 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002247 | 800222.V | 112451/2.V | 12470 | 1 | 5021701 | 26.4.002218 | 974062.V | 112474/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
163 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002248 | 974058.V | 112415/1.V | 12450 | 1 | 5021701 | 26.4.002219 | 974062.V | 112474/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
164 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002249 | 800222.V | 112449/2.V | 12450 | 1 | 5021701 | 26.4.002220 | 974062.V | 112470/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
165 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002250 | 974058.V | 112414/1.V | 12460 | 1 | 5021701 | 26.4.002221 | 974062.V | 112471/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
166 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002251 | 974058.V | 112417/2.V | 12460 | 1 | 5021701 | 26.4.007873 | 975002.V | 121359/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
167 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002252 | 974058.V | 112418/2.V | 12450 | 1 | 5021701 | 26.4.002223 | 974062.V | 112472/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
168 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002253 | 974058.V | 112414/2.V | 12450 | 1 | 5021701 | 26.4.002224 | 974062.V | 112473/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
169 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002254 | 974058.V | 112413/1.V | 12450 | 1 | 5021701 | 26.4.002225 | 974062.V | 112478/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
170 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002169 | 780325.V | 112406/1.V | 12470 | 1 | 5021701 | 26.4.002226 | 974062.V | 112469/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002227 | 974062.V | 112482/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002228 | 974062.V | 112479/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002229 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008989 | 780977.V | 118252/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008280 | 781052.V | 119842/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008277 | 781052.V | 119846/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002233 | 974062.V | 112472/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002234 | 800222.V | 112450/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002235 | 800222.V | 112451/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002236 | 974058.V | 112417/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002237 | 974058.V | 112413/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007905 | 800957.V | 119873/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002240 | 974058.V | 113145/2.V | 12210 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.002241 | 974058.V | 112415/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002242 | 974058.V | 112418/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002243 | 974058.V | 113145/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002244 | 800222.V | 112450/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002245 | 800222.V | 112452/2.V | 11810 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002246 | 800222.V | 112453/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007922 | 800957.V | 119874/1A.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002248 | 974058.V | 112415/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002249 | 800222.V | 112449/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002251 | 974058.V | 112417/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002252 | 974058.V | 112418/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.002253 | 974058.V | 112414/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002254 | 974058.V | 112413/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007729 | 781283.V | 121411/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007937 | 801198.V | 121322/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007731 | 781283.V | 121419/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.007732 | 781283.V | 121409/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007734 | 781283.V | 121420/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007735 | 781283.V | 121415/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | [9 empty] | DHC
[9 empty] | 5021701 | 26.4.007737 | 781283.V | 121416/1.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.007738 | 781283.V | 121415/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.007739 | 801208.V | 122028/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008400 | 781086.V | 120903/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007741 | 801208.V | 122018/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007742 | 801208.V | 122025/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007743 | 801208.V | 122021/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007744 | 801208.V | 122025/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.007745 | 801208.V | 122022/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007746 | 781283.V | 121407/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007747 | 781283.V | 121407/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.007970 | 801198.V | 121324/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007749 | 801208.V | 122027/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007750 | 801208.V | 122030/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007751 | 801208.V | 122031/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.007752 | 801208.V | 122023/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.007753 | 801208.V | 122023/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007754 | 801208.V | 122022/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007755 | 801208.V | 122019/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008465 | 800848.V | 118421/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007757 | 801208.V | 122018/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007758 | 801208.V | 122021/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007759 | 781283.V | 121408/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007760 | 781283.V | 121419/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007761 | 781283.V | 121414/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007762 | 781283.V | 121410/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007763 | 781283.V | 121411/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008002 | 780995.V | 118311/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007767 | 781283.V | 121409/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007768 | 801208.V | 122030/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007769 | 781283.V | 121414/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007770 | 781283.V | 121408/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007771 | 801208.V | 122029/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.007772 | 801208.V | 122029/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007774 | 781283.V | 121410/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008529 | 800995.V | 120692/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.007776 | 801208.V | 122020/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007777 | 801208.V | 122031/2.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007778 | 801208.V | 122019/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007779 | 801208.V | 122024/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007780 | 801208.V | 122024/1A.V | 12050 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007781 | 781297.V | 121333/2.V | 11870 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007782 | 781297.V | 121339/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008034 | 780995.V | 118312/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007784 | 781297.V | 121345/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007785 | 781297.V | 121337/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007786 | 781297.V | 121333/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007787 | 781297.V | 121338/1A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007788 | 781297.V | 121344/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007789 | 781297.V | 121336/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007790 | 781297.V | 121344/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007823 | 801219.V | 122060/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.002198 | 780325.V | 112398/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002123 | 800232.V | 112437/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002197 | 780325.V | 112400/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002196 | 780325.V | 112402/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002122 | 800232.V | 112434/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002195 | 800223.V | 112457/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007815 | 781297.V | 121335/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002194 | 780325.V | 112397/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002121 | 800232.V | 112441/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002193 | 800223.V | 112457/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002192 | 800223.V | 112455/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002120 | 800232.V | 112437/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007810 | 974992.V | 122006/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007809 | 974992.V | 122004/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.002191 | 800223.V | 112462/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007808 | 974992.V | 122001/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008658 | 781241.V | 120929/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008083 | 800965.V | 119515/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007807 | 974992.V | 122000/2.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007811 | 974992.V | 122002/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007812 | 974992.V | 122000/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007813 | 974992.V | 121999/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007814 | 974992.V | 122001/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008099 | 800970.V | 119905/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007816 | 781297.V | 121335/1A.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007817 | 781297.V | 121334/1A.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007818 | 781297.V | 121337/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007819 | 781297.V | 121342/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007820 | 781297.V | 121336/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007821 | 781297.V | 121346/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007822 | 975002.V | 121360/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008724 | 800840.V | 118412/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007824 | 801219.V | 122063/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007825 | 801219.V | 122066/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007826 | 801219.V | 122066/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007827 | 975002.V | 121354/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007828 | 975002.V | 121350/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007829 | 975002.V | 121350/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007830 | 975002.V | 121358/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007831 | 975002.V | 121358/2.V | 11860 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007832 | 801219.V | 122071/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007833 | 801219.V | 122069/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007834 | 801219.V | 122073/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007835 | 975002.V | 121347/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007836 | 975002.V | 121356/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007837 | 975002.V | 121356/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007838 | 975002.V | 121360/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008148 | 800959.V | 119888/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007840 | 975002.V | 121355/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP | [13 empty] | DHC
[9 empty] | 5021701 | 26.4.007841 | 975002.V | 121357/1A.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.007842 | 975002.V | 121353/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007843 | 975002.V | 121351/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007844 | 975002.V | 121351/1A.V | 12150 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007845 | 801219.V | 122072/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007846 | 801219.V | 122072/1.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007847 | 801219.V | 122067/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007848 | 801219.V | 122071/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007849 | 801219.V | 122070/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007850 | 801219.V | 122073/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007851 | 801219.V | 122065/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007852 | 801219.V | 122061/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007853 | 801219.V | 122062/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007855 | 801219.V | 122064/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008851 | 780977.V | 118253/2A.V | 12450 | EC | PU
[9 empty] | 5021701 | 26.4.007857 | 801219.V | 122068/1.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007858 | 801219.V | 122069/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007860 | 975002.V | 121353/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007861 | 975002.V | 121348/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007862 | 975002.V | 121355/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007863 | 975002.V | 121352/2.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007864 | 975002.V | 121359/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007865 | 975002.V | 121354/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007866 | 801219.V | 122065/2.V | 12470 | EC | PU | SEL | SI | SE |  |  | REP
[9 empty] | 5021701 | 26.4.007867 | 801219.V | 122064/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007868 | 801219.V | 122067/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.007869 | 801219.V | 122061/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007870 | 801219.V | 122060/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007871 | 801219.V | 122070/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007872 | 801219.V | 122063/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008221 | 781062.V | 119462/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007874 | 975002.V | 121349/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007875 | 975002.V | 121349/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007876 | 800957.V | 119868/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007877 | 800957.V | 119873/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007878 | 800943.V | 119469/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007879 | 800943.V | 119476/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007880 | 800957.V | 119869/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007881 | 800943.V | 119477/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007882 | 800943.V | 119471/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007883 | 800957.V | 119862/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007884 | 800943.V | 119475/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007885 | 800943.V | 119474/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007886 | 800957.V | 119867/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007887 | 800957.V | 119862/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007888 | 800957.V | 119866/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008990 | 974777.V | 119937/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007890 | 800943.V | 119464/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007891 | 800957.V | 119867/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007892 | 800957.V | 119870/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002093 | 800229.V | 112425/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008279 | 781052.V | 119836/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007895 | 800943.V | 119471/1.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007896 | 800943.V | 119466/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007897 | 800943.V | 119470/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007898 | 800943.V | 119470/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007899 | 800957.V | 119866/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007900 | 800943.V | 119465/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007901 | 800943.V | 119465/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007902 | 800957.V | 119871/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007903 | 800957.V | 119870/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.007904 | 800943.V | 119464/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008303 | 975011.V | 122053/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007906 | 800943.V | 119473/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007907 | 800957.V | 119863/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007908 | 800943.V | 119468/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007909 | 800943.V | 119474/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007910 | 800943.V | 119467/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.007911 | 800957.V | 119875/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007912 | 800957.V | 119865/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007913 | 800957.V | 119874/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007914 | 800957.V | 119875/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007915 | 800957.V | 119865/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007916 | 800957.V | 119868/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007917 | 800943.V | 119476/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007918 | 800943.V | 119477/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007919 | 800957.V | 119864/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007920 | 800943.V | 119468/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002190 | 800223.V | 112454/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008338 | 781068.V | 119544/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007923 | 800943.V | 119469/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007924 | 800957.V | 119863/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007925 | 800957.V | 119872/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007926 | 800943.V | 119467/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007927 | 800943.V | 119472/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.007928 | 800957.V | 119864/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007929 | 800943.V | 119475/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.007930 | 800943.V | 119472/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007931 | 801198.V | 121322/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007932 | 801198.V | 121324/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007933 | 801198.V | 121319/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007934 | 801198.V | 121319/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007935 | 801198.V | 121332/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007936 | 801198.V | 121327/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008368 | 781068.V | 119548/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007938 | 801198.V | 121328/1A.V | 12120 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007939 | 801198.V | 121328/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007940 | 801198.V | 121329/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007941 | 801198.V | 121323/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007942 | 801198.V | 121320/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007943 | 801198.V | 121331/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007944 | 801198.V | 121320/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007945 | 801198.V | 121323/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007946 | 801198.V | 121329/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007947 | 801198.V | 121332/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007948 | 801198.V | 121327/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007949 | 801198.V | 121326/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007950 | 801198.V | 121331/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007951 | 801198.V | 121330/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.007953 | 780993.V | 118572/1.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008401 | 781086.V | 120902/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.007955 | 780993.V | 118570/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.007956 | 780993.V | 118562/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007957 | 801198.V | 121321/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007958 | 801198.V | 121321/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007959 | 801198.V | 121325/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007960 | 801198.V | 121325/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007961 | 780993.V | 118572/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007962 | 780993.V | 118564/2.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007963 | 780993.V | 118568/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007964 | 780993.V | 118574/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007965 | 780993.V | 118573/1.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007966 | 780993.V | 118570/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007967 | 780993.V | 118562/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007968 | 780993.V | 118569/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007969 | 780993.V | 118564/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008432 | 800841.V | 118140/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.007971 | 801198.V | 121326/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007972 | 780993.V | 118563/2.V | 12470 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.007973 | 780993.V | 118563/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007974 | 780993.V | 118566/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007975 | 780993.V | 118567/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007976 | 780993.V | 118565/2.V | 11800 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007977 | 780993.V | 118565/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007978 | 780993.V | 118566/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007979 | 780993.V | 118567/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007980 | 780993.V | 118571/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007981 | 780993.V | 118573/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007982 | 780993.V | 118568/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007983 | 780993.V | 118571/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007984 | 780993.V | 118561/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007985 | 780993.V | 118561/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002119 | 800233.V | 112483/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007987 | 780995.V | 118301/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007988 | 780995.V | 118309/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007989 | 780995.V | 118309/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007990 | 780992.V | 118290/2.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007991 | 780995.V | 118307/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007992 | 780992.V | 118295/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007993 | 780992.V | 118292/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007994 | 780992.V | 118291/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007995 | 780992.V | 118294/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007996 | 780992.V | 118294/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007997 | 780992.V | 118298/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007998 | 780992.V | 118288/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007999 | 780995.V | 118308/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008000 | 780992.V | 118288/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008001 | 780995.V | 118313/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.008496 | 800963.V | 119502/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008003 | 780995.V | 118304/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008004 | 780995.V | 118308/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008005 | 780995.V | 118302/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.008006 | 780995.V | 118313/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008007 | 780992.V | 118287/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008008 | 780995.V | 118301/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.008009 | 780992.V | 118297/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008010 | 780992.V | 118290/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008011 | 780992.V | 118287/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008012 | 780992.V | 118291/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008013 | 780992.V | 118289/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008014 | 780992.V | 118292/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008015 | 780992.V | 118293/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008016 | 780992.V | 118295/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008017 | 780992.V | 118299/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008530 | 800995.V | 120693/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008019 | 780995.V | 118310/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008020 | 780992.V | 118297/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008021 | 780995.V | 118305/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008022 | 780995.V | 118312/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008023 | 780992.V | 118298/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008024 | 780995.V | 118306/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008025 | 780992.V | 118296/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008026 | 780992.V | 118296/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008027 | 780995.V | 118303/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008028 | 780992.V | 118300/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008029 | 780995.V | 118307/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008030 | 780995.V | 118303/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008031 | 780995.V | 118310/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008032 | 780995.V | 118314/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008033 | 780995.V | 118304/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008561 | 800983.V | 119967/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008035 | 780995.V | 118314/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008036 | 780995.V | 118311/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008037 | 780995.V | 118305/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008038 | 780995.V | 118302/1.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008039 | 780992.V | 118299/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008040 | 780992.V | 118300/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008041 | 780992.V | 118289/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008042 | 800965.V | 119506/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008044 | 800965.V | 119503/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008045 | 800965.V | 119512/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008046 | 780991.V | 118554/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008047 | 780991.V | 118550/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008048 | 780991.V | 118559/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008049 | 780991.V | 118560/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008050 | 800965.V | 119504/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007806 | 974992.V | 121999/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007805 | 974992.V | 122005/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002189 | 800223.V | 112456/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007804 | 974992.V | 122005/1A.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007803 | 781297.V | 121340/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.002188 | 800223.V | 112455/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002118 | 800232.V | 112444/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007802 | 781297.V | 121346/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007801 | 781297.V | 121339/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002187 | 800223.V | 112458/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007800 | 781297.V | 121340/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008068 | 780991.V | 118553/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008626 | 781241.V | 120938/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008067 | 780991.V | 118553/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007799 | 781297.V | 121338/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.002186 | 800223.V | 112454/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002116 | 800233.V | 112485/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008066 | 780991.V | 118555/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008069 | 800965.V | 119505/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008070 | 800965.V | 119516/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008071 | 800965.V | 119513/2.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008072 | 800965.V | 119513/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008073 | 800965.V | 119512/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008074 | 800965.V | 119511/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008075 | 800965.V | 119506/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008076 | 800965.V | 119511/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008077 | 800965.V | 119507/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008078 | 800965.V | 119515/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008079 | 780991.V | 118551/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008080 | 780991.V | 118557/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008081 | 975002.V | 121348/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008082 | 800965.V | 119503/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008659 | 781237.V | 120712/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008084 | 780991.V | 118551/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008085 | 780991.V | 118552/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008086 | 780991.V | 118558/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008087 | 780991.V | 118552/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008088 | 780991.V | 118560/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008089 | 780991.V | 118558/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008090 | 780991.V | 118557/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008091 | 780991.V | 118559/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008092 | 780991.V | 118550/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008093 | 781083.V | 120867/2.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008094 | 781083.V | 120865/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008095 | 781083.V | 120869/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008096 | 781083.V | 120869/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008097 | 781083.V | 120867/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008098 | 781083.V | 120868/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008691 | 780932.V | 118403/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008100 | 781083.V | 120868/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008101 | 800970.V | 119907/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008102 | 800970.V | 119907/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008103 | 781083.V | 120864/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008104 | 781083.V | 120870/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008105 | 800970.V | 119906/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008106 | 800970.V | 119910/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008107 | 800970.V | 119910/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008108 | 800970.V | 119911/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008109 | 800970.V | 119908/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008110 | 800970.V | 119905/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008111 | 800970.V | 119904/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008112 | 800970.V | 119909/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008114 | 800970.V | 119904/2.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008115 | 781083.V | 120870/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008065 | 800965.V | 119504/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008117 | 781083.V | 120865/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008118 | 781083.V | 120866/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008119 | 781083.V | 120866/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008120 | 781083.V | 120871/1A.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008121 | 800970.V | 119906/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008122 | 781083.V | 120871/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008123 | 800970.V | 119908/1A.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008124 | 800970.V | 119909/1A.V | 12200 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008125 | 800958.V | 119482/1.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008126 | 800958.V | 119485/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008127 | 800959.V | 119878/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008128 | 800958.V | 119481/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008129 | 800958.V | 119479/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008130 | 800958.V | 119479/1.V | 11770 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008131 | 800958.V | 119489/1.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008132 | 800958.V | 119488/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008133 | 800959.V | 119880/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008134 | 800958.V | 119491/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008135 | 800959.V | 119880/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008136 | 800959.V | 119884/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008137 | 800959.V | 119879/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008138 | 800959.V | 119881/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008139 | 800959.V | 119881/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008140 | 800958.V | 119486/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008141 | 800958.V | 119484/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008142 | 800958.V | 119484/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008143 | 800958.V | 119483/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008144 | 800958.V | 119486/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008145 | 800958.V | 119489/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008146 | 800958.V | 119482/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008147 | 800959.V | 119886/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008787 | 780973.V | 118229/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008149 | 800958.V | 119490/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008150 | 800958.V | 119491/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008151 | 800959.V | 119876/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008152 | 800959.V | 119876/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008153 | 800958.V | 119490/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008154 | 800959.V | 119885/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008155 | 800959.V | 119878/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008156 | 800959.V | 119886/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008157 | 800958.V | 119487/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008158 | 800959.V | 119888/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008159 | 800958.V | 119487/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008160 | 800959.V | 119879/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008161 | 800958.V | 119485/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008162 | 800958.V | 119478/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008163 | 800958.V | 119481/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008164 | 800958.V | 119483/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008165 | 800959.V | 119889/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008166 | 800959.V | 119889/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008167 | 800959.V | 119887/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008168 | 800959.V | 119887/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008169 | 800959.V | 119877/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008170 | 800959.V | 119877/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008171 | 800959.V | 119882/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008172 | 800959.V | 119883/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008173 | 800958.V | 119478/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008174 | 800959.V | 119885/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008175 | 800959.V | 119882/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008176 | 800959.V | 119884/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008177 | 800958.V | 119488/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008178 | 800958.V | 119480/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008179 | 800959.V | 119883/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008852 | 780977.V | 118257/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008182 | 801174.V | 120820/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008183 | 801174.V | 120816/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008184 | 801169.V | 120791/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008186 | 801174.V | 120818/1A.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008187 | 801169.V | 120795/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008188 | 801174.V | 120823/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008189 | 801174.V | 120818/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008191 | 801174.V | 120813/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008192 | 801169.V | 120792/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008193 | 801174.V | 120817/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008195 | 801174.V | 120819/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008196 | 801174.V | 120819/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008197 | 801174.V | 120825/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008198 | 801174.V | 120825/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008199 | 801174.V | 120821/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008202 | 801174.V | 120821/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008203 | 801169.V | 120795/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008204 | 801174.V | 120822/2.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008207 | 801169.V | 120793/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008209 | 801169.V | 120796/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008210 | 801169.V | 120793/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008211 | 801174.V | 120823/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008212 | 801169.V | 120791/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008213 | 801174.V | 120822/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008214 | 801174.V | 120812/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008215 | 801174.V | 120812/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008216 | 801174.V | 120817/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008217 | 801174.V | 120824/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008218 | 801174.V | 120814/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008219 | 801174.V | 120816/2.V | 11770 | EC | PU | SEL | SI | SE | U1 |  | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008220 | 801169.V | 120792/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008925 | 974777.V | 119929/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008222 | 781062.V | 119461/1.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008223 | 781062.V | 119458/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.008224 | 781062.V | 119462/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008225 | 781062.V | 119451/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008226 | 781062.V | 119451/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008227 | 975015.V | 121401/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008228 | 975015.V | 121406/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008229 | 975015.V | 121402/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008230 | 975015.V | 121402/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008231 | 975015.V | 121393/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008232 | 975015.V | 121406/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008233 | 975015.V | 121400/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008234 | 975015.V | 121400/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008235 | 975015.V | 121404/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008236 | 781062.V | 119458/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008237 | 781062.V | 119450/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008238 | 975015.V | 121401/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008239 | 975015.V | 121394/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008240 | 975015.V | 121404/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008241 | 975015.V | 121396/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008242 | 975015.V | 121403/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008243 | 975015.V | 121394/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008245 | 975015.V | 121403/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008246 | 975015.V | 121405/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008248 | 781062.V | 119454/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008249 | 781062.V | 119457/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008252 | 781062.V | 119456/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008253 | 781062.V | 119456/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008254 | 975015.V | 121393/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008257 | 975015.V | 121398/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008258 | 975015.V | 121399/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007798 | 781297.V | 121341/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008261 | 975015.V | 121397/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008262 | 975015.V | 121397/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008263 | 781062.V | 119463/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008268 | 781062.V | 119454/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008271 | 781062.V | 119461/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.900029 | 974062.V | 112469/1.V | 3540 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002139 | 800232.V | 112435/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008064 | 780991.V | 118556/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002140 | 800232.V | 112439/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002232 | 974062.V | 112477/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007894 | 800957.V | 119872/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH
[9 empty] | 5021701 | 26.4.008281 | 975011.V | 122052/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008282 | 975011.V | 122050/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008284 | 975011.V | 122054/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008286 | 975011.V | 122054/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008287 | 781052.V | 119843/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008288 | 781052.V | 119843/1A.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008289 | 781052.V | 119838/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008290 | 781052.V | 119839/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008291 | 781052.V | 119835/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008292 | 781052.V | 119840/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008293 | 781052.V | 119837/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008294 | 781052.V | 119836/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008295 | 781052.V | 119838/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008296 | 975011.V | 122057/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008297 | 975011.V | 122056/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008298 | 975011.V | 122046/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008299 | 975011.V | 122046/2.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008300 | 975011.V | 122055/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008301 | 975011.V | 122049/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008302 | 975011.V | 122058/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008063 | 800965.V | 119507/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.008304 | 975011.V | 122058/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008305 | 975011.V | 122059/1A.V | 11820 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008306 | 975011.V | 122051/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008307 | 975011.V | 122047/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008308 | 975011.V | 122051/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008309 | 975011.V | 122047/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008310 | 975011.V | 122052/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008311 | 975011.V | 122048/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008312 | 975011.V | 122048/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008313 | 975011.V | 122056/1A.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008314 | 975011.V | 122053/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008315 | 975011.V | 122059/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008316 | 781052.V | 119839/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008317 | 781052.V | 119846/1A.V | 11700 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008318 | 781052.V | 119841/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008319 | 781052.V | 119845/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008320 | 781052.V | 119837/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008321 | 781052.V | 119835/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008322 | 781052.V | 119834/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008323 | 781052.V | 119847/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008324 | 781052.V | 119834/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008325 | 781052.V | 119845/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008326 | 781052.V | 119847/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008328 | 975011.V | 122049/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008329 | 781052.V | 119841/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008330 | 781052.V | 119840/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008331 | 781052.V | 119844/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008332 | 781052.V | 119844/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008333 | 781068.V | 119540/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008334 | 781068.V | 119546/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008335 | 781068.V | 119539/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007797 | 781297.V | 121345/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.002185 | 800223.V | 112463/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008062 | 800965.V | 119510/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008339 | 781085.V | 120888/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008340 | 781085.V | 120895/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008341 | 781085.V | 120891/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008342 | 781085.V | 120894/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008343 | 781085.V | 120888/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008344 | 781085.V | 120891/1.V | 12450 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008345 | 781085.V | 120889/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008346 | 781085.V | 120887/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008347 | 781085.V | 120894/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008348 | 781085.V | 120890/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008349 | 781085.V | 120896/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008350 | 781085.V | 120896/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008351 | 781085.V | 120887/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008352 | 781085.V | 120892/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008353 | 781085.V | 120892/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008354 | 781085.V | 120893/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008355 | 781085.V | 120893/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008356 | 781068.V | 119547/1.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008357 | 781068.V | 119549/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008358 | 781085.V | 120886/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008359 | 781085.V | 120890/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008360 | 781068.V | 119545/1.V | 12200 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008361 | 781085.V | 120886/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008362 | 781068.V | 119546/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008363 | 781068.V | 119547/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008364 | 781068.V | 119545/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008365 | 781068.V | 119541/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008366 | 781068.V | 119548/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008367 | 781068.V | 119542/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008061 | 780991.V | 118555/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008369 | 781085.V | 120889/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008370 | 781068.V | 119541/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008371 | 781068.V | 119542/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008372 | 781068.V | 119543/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008373 | 781068.V | 119549/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008374 | 781068.V | 119543/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008375 | 781068.V | 119544/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008376 | 781086.V | 120904/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008377 | 781086.V | 120901/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008378 | 781086.V | 120908/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008379 | 781090.V | 120684/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008380 | 781090.V | 120689/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008381 | 781090.V | 120678/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008382 | 781086.V | 120910/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008383 | 781090.V | 120678/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008384 | 781086.V | 120902/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008385 | 781090.V | 120689/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008386 | 781086.V | 120897/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008387 | 781086.V | 120910/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008388 | 781090.V | 120685/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008389 | 781090.V | 120677/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008390 | 781090.V | 120681/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008391 | 781090.V | 120687/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008392 | 781090.V | 120676/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008393 | 781090.V | 120685/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008394 | 781086.V | 120904/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008395 | 781090.V | 120676/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008396 | 781090.V | 120683/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008397 | 781090.V | 120679/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008398 | 781086.V | 120909/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008399 | 781086.V | 120907/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007796 | 974992.V | 122003/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008060 | 800965.V | 119508/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008402 | 781086.V | 120900/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008403 | 781086.V | 120909/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008404 | 781086.V | 120900/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008405 | 781086.V | 120908/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008406 | 781086.V | 120905/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008407 | 781086.V | 120898/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008408 | 781090.V | 120681/2.V | 12110 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008409 | 781086.V | 120906/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008410 | 781090.V | 120680/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008411 | 781090.V | 120688/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008412 | 781090.V | 120687/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008413 | 781090.V | 120680/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008414 | 781090.V | 120679/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008415 | 781090.V | 120682/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008416 | 781090.V | 120677/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008417 | 781086.V | 120906/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008418 | 781090.V | 120683/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008419 | 781090.V | 120682/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008420 | 781090.V | 120686/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008421 | 781090.V | 120684/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008422 | 781090.V | 120688/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008423 | 781086.V | 120898/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008424 | 781086.V | 120897/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008425 | 781086.V | 120899/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008426 | 781086.V | 120905/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008427 | 781086.V | 120899/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008428 | 781090.V | 120686/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008429 | 781086.V | 120903/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008430 | 800841.V | 118134/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008431 | 800841.V | 118136/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008059 | 800965.V | 119514/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008433 | 800841.V | 118141/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008434 | 800841.V | 118139/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008435 | 800841.V | 118134/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008436 | 800841.V | 118145/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008437 | 800841.V | 118145/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008438 | 800848.V | 118430/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008439 | 800841.V | 118139/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008440 | 800848.V | 118429/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008441 | 800848.V | 118433/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008442 | 800848.V | 118423/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008443 | 800848.V | 118425/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008444 | 800848.V | 118426/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008445 | 800848.V | 118424/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008446 | 800841.V | 118147/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008447 | 800841.V | 118137/2A.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008448 | 800848.V | 118425/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008449 | 800848.V | 118431/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008450 | 800848.V | 118422/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008451 | 800848.V | 118422/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008452 | 800841.V | 118143/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008453 | 800841.V | 118144/2A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008454 | 800841.V | 118147/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008455 | 800848.V | 118430/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008456 | 800841.V | 118138/2A.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008457 | 800841.V | 118141/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008458 | 800848.V | 118426/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008459 | 800841.V | 118146/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008460 | 800841.V | 118140/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008461 | 800848.V | 118428/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008462 | 800841.V | 118143/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008463 | 800848.V | 118432/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007795 | 781297.V | 121342/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002184 | 800223.V | 112464/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008466 | 800841.V | 118136/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008467 | 800848.V | 118420/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008468 | 800841.V | 118142/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008469 | 800848.V | 118420/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008470 | 800848.V | 118421/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008471 | 800848.V | 118423/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008472 | 800848.V | 118429/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008473 | 800848.V | 118424/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008474 | 800848.V | 118428/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008475 | 800841.V | 118142/1A.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008476 | 800841.V | 118135/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008477 | 800841.V | 118146/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008478 | 800963.V | 119500/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008479 | 800964.V | 119897/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008480 | 800964.V | 119893/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008481 | 800964.V | 119895/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008482 | 800963.V | 119496/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008483 | 800963.V | 119499/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008484 | 800964.V | 119892/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008485 | 800964.V | 119890/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008486 | 800964.V | 119890/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008487 | 800964.V | 119894/1A.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008488 | 800964.V | 119894/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008489 | 800963.V | 119497/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008490 | 800963.V | 119493/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008491 | 800963.V | 119497/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008492 | 800963.V | 119500/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008493 | 800964.V | 119895/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008494 | 800964.V | 119902/1A.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008495 | 800963.V | 119496/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002115 | 800233.V | 112488/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008497 | 800963.V | 119499/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008498 | 800964.V | 119896/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008499 | 800964.V | 119898/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008500 | 800964.V | 119900/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008501 | 800963.V | 119495/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008502 | 800964.V | 119903/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008503 | 800963.V | 119495/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008504 | 800964.V | 119899/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008505 | 800963.V | 119493/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008506 | 800963.V | 119498/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008508 | 800963.V | 119494/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008509 | 800964.V | 119898/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008510 | 800963.V | 119492/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008511 | 800963.V | 119498/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008512 | 800963.V | 119492/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008513 | 800964.V | 119901/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008514 | 800964.V | 119901/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008515 | 800963.V | 119501/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008516 | 800964.V | 119891/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008517 | 800964.V | 119896/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008518 | 800964.V | 119891/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008519 | 800964.V | 119899/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008520 | 800963.V | 119501/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008521 | 800964.V | 119903/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008522 | 800964.V | 119893/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008523 | 800964.V | 119900/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008524 | 800963.V | 119502/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008525 | 800964.V | 119902/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008526 | 800964.V | 119897/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008527 | 800964.V | 119892/1A.V | 12120 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008528 | 800983.V | 119968/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008058 | 800965.V | 119516/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008057 | 800965.V | 119510/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008531 | 800995.V | 120703/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008532 | 800995.V | 120702/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008533 | 800995.V | 120701/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008534 | 800995.V | 120698/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008535 | 800995.V | 120691/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008536 | 800983.V | 119973/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008537 | 800995.V | 120690/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008538 | 800995.V | 120697/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008539 | 800995.V | 120701/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008540 | 800983.V | 119971/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008541 | 800983.V | 119971/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008542 | 800995.V | 120692/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008543 | 800995.V | 120690/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008544 | 800983.V | 119974/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008545 | 800983.V | 119970/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008546 | 800995.V | 120697/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008547 | 800983.V | 119972/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008548 | 800995.V | 120694/1.V | 12450 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008549 | 800995.V | 120694/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008550 | 800995.V | 120699/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008551 | 800995.V | 120696/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008552 | 800995.V | 120698/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008553 | 800995.V | 120703/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008554 | 800995.V | 120700/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008555 | 800995.V | 120695/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008556 | 800983.V | 119967/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008557 | 800995.V | 120700/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008558 | 800995.V | 120691/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008559 | 800995.V | 120695/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008560 | 800983.V | 119969/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007794 | 974992.V | 122003/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008562 | 800983.V | 119969/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008563 | 800995.V | 120696/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008564 | 800983.V | 119977/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008565 | 800995.V | 120702/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008566 | 800983.V | 119977/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.008567 | 800995.V | 120699/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008568 | 800983.V | 119974/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008569 | 800983.V | 119972/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008570 | 800983.V | 119975/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008571 | 800983.V | 119976/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008572 | 800983.V | 119975/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008573 | 800995.V | 120693/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008574 | 800983.V | 119970/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008575 | 800977.V | 119579/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008577 | 800977.V | 119575/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008578 | 800977.V | 119576/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008579 | 800977.V | 119570/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008580 | 800977.V | 119581/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008581 | 800977.V | 119576/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008582 | 800977.V | 119569/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008583 | 800977.V | 119577/1A.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008584 | 800977.V | 119569/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008585 | 800977.V | 119571/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008586 | 800977.V | 119580/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008587 | 800848.V | 118433/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008588 | 800976.V | 119556/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008589 | 800976.V | 119559/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008590 | 800976.V | 119553/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008591 | 800976.V | 119562/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008592 | 800976.V | 119563/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008593 | 800976.V | 119553/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008056 | 800965.V | 119514/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008603 | 800976.V | 119557/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008602 | 800976.V | 119556/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008055 | 800965.V | 119509/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007793 | 974992.V | 122004/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002183 | 800223.V | 112458/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008601 | 800976.V | 119558/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008600 | 800976.V | 119552/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008054 | 800965.V | 119509/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008599 | 800976.V | 119560/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008604 | 800976.V | 119557/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008605 | 800977.V | 119570/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008606 | 800977.V | 119568/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008607 | 800976.V | 119563/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008608 | 800976.V | 119551/1.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008609 | 800977.V | 119575/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008610 | 800976.V | 119561/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008611 | 800976.V | 119561/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008612 | 800977.V | 119574/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008613 | 800977.V | 119573/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008614 | 800977.V | 119581/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008615 | 800976.V | 119562/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008616 | 800977.V | 119580/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008617 | 800977.V | 119577/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008618 | 800976.V | 119552/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008619 | 781241.V | 120925/1A.V | 11750 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008620 | 781241.V | 120930/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008621 | 781241.V | 120936/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008622 | 781241.V | 120934/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008623 | 781241.V | 120928/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008624 | 781237.V | 120718/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008625 | 781241.V | 120932/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008598 | 800976.V | 119554/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008627 | 781241.V | 120938/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008628 | 781237.V | 120714/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008629 | 781241.V | 120936/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008630 | 781237.V | 120719/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008631 | 781237.V | 120716/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008632 | 781237.V | 120717/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008633 | 781237.V | 120715/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008634 | 781241.V | 120929/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008635 | 781237.V | 120711/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008636 | 781237.V | 120720/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008637 | 781237.V | 120710/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008638 | 781237.V | 120710/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008639 | 781237.V | 120711/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008640 | 781241.V | 120937/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008641 | 781241.V | 120935/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008642 | 781241.V | 120931/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008643 | 781241.V | 120925/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008644 | 781241.V | 120933/1.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008645 | 781241.V | 120935/1.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008646 | 781241.V | 120933/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008647 | 781241.V | 120937/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008648 | 781237.V | 120718/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008649 | 781241.V | 120928/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008650 | 781241.V | 120926/2.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008651 | 781237.V | 120713/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008652 | 781241.V | 120926/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008653 | 781237.V | 120715/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008654 | 781237.V | 120716/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008655 | 781241.V | 120930/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008656 | 781241.V | 120927/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008657 | 781237.V | 120717/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008053 | 780991.V | 118556/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007792 | 974992.V | 122006/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008660 | 781237.V | 120720/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008661 | 781241.V | 120927/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008662 | 781241.V | 120931/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008663 | 781237.V | 120713/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008664 | 781241.V | 120932/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008665 | 781241.V | 120934/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008666 | 781237.V | 120714/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008667 | 781237.V | 120719/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008668 | 780939.V | 118435/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008669 | 780932.V | 118402/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008670 | 780932.V | 118405/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008671 | 780939.V | 118439/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008672 | 780932.V | 118401/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008673 | 780932.V | 118401/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008674 | 780932.V | 118396/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008675 | 780939.V | 118435/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008676 | 780939.V | 118444/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008677 | 780939.V | 118444/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008678 | 780932.V | 118399/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008679 | 780932.V | 118400/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008680 | 780939.V | 118440/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008681 | 780939.V | 118443/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008682 | 780932.V | 118400/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008683 | 780932.V | 118405/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008684 | 780932.V | 118399/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008685 | 780939.V | 118437/1.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008686 | 780932.V | 118404/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008687 | 780932.V | 118403/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008689 | 780939.V | 118442/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008690 | 780939.V | 118442/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008597 | 800976.V | 119558/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008692 | 780932.V | 118404/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008693 | 780932.V | 118397/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008694 | 780939.V | 118439/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008695 | 780939.V | 118438/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008696 | 780939.V | 118443/1.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008697 | 780932.V | 118396/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008698 | 780939.V | 118441/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008699 | 780939.V | 118436/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008700 | 780932.V | 118398/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008701 | 780939.V | 118441/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008702 | 780932.V | 118397/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008703 | 780932.V | 118398/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008704 | 780939.V | 118436/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008705 | 780939.V | 118437/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008706 | 780939.V | 118438/2.V | 11710 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008707 | 800840.V | 118407/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008708 | 800840.V | 118417/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008709 | 800840.V | 118411/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008710 | 800840.V | 118416/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008711 | 800840.V | 118419/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008712 | 800840.V | 118415/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008713 | 800840.V | 118415/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008714 | 800840.V | 118406/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008715 | 800840.V | 118414/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008716 | 800840.V | 118416/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008717 | 800840.V | 118410/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008718 | 800840.V | 118411/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008719 | 800840.V | 118409/2.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008720 | 800840.V | 118413/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008721 | 800840.V | 118406/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008722 | 800840.V | 118410/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008596 | 800976.V | 119560/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008052 | 800965.V | 119505/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008725 | 800840.V | 118417/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008726 | 800840.V | 118418/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008727 | 800840.V | 118407/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008728 | 800840.V | 118418/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008729 | 800840.V | 118408/1.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008730 | 800840.V | 118408/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008731 | 800840.V | 118409/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008732 | 800840.V | 118412/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008733 | 800840.V | 118413/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008734 | 800840.V | 118414/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008735 | 800977.V | 119572/2.V | 12290 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008736 | 781329.V | 122109/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008737 | 781329.V | 122109/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008738 | 780973.V | 118227/2A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008739 | 780973.V | 118226/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008740 | 781329.V | 122121/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008741 | 781329.V | 122110/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008742 | 781329.V | 122122/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008743 | 781329.V | 122113/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008744 | 780973.V | 118232/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008745 | 780973.V | 118234/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008746 | 780973.V | 118239/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008747 | 780973.V | 118235/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008748 | 780973.V | 118230/2A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008749 | 780973.V | 118238/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008750 | 781329.V | 122119/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008751 | 780973.V | 118233/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008752 | 780973.V | 118231/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008753 | 780973.V | 118236/2A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008754 | 781329.V | 122120/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008755 | 781329.V | 122120/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008756 | 781329.V | 122111/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008757 | 781329.V | 122111/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008758 | 781329.V | 122122/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008759 | 781329.V | 122118/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008760 | 781329.V | 122112/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008761 | 781329.V | 122117/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008762 | 781329.V | 122119/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008763 | 781329.V | 122112/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008764 | 780973.V | 118238/1A.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008765 | 781329.V | 122116/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008766 | 780973.V | 118237/1A.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008767 | 781329.V | 122113/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008768 | 781329.V | 122121/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008769 | 781329.V | 122116/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008770 | 781329.V | 122118/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008771 | 780973.V | 118228/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008772 | 781329.V | 122114/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008773 | 781329.V | 122115/1A.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008774 | 781329.V | 122114/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008775 | 781329.V | 122117/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008776 | 780973.V | 118234/2A.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008777 | 780973.V | 118233/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008778 | 780973.V | 118228/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008779 | 780973.V | 118232/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008780 | 780973.V | 118237/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008781 | 780973.V | 118239/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008782 | 780973.V | 118231/2A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008783 | 780973.V | 118230/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008784 | 780973.V | 118236/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008785 | 781329.V | 122115/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008786 | 781329.V | 122110/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008595 | 800976.V | 119554/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008788 | 780973.V | 118229/2A.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008789 | 780973.V | 118227/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008790 | 780973.V | 118226/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008791 | 780970.V | 118214/2.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008792 | 780970.V | 118213/1.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008793 | 780970.V | 118213/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008794 | 780970.V | 118214/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008795 | 780970.V | 118216/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008796 | 780970.V | 118212/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008797 | 780970.V | 118215/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008798 | 780970.V | 118212/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008799 | 780970.V | 118225/2A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008800 | 800907.V | 118269/1A.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008801 | 780970.V | 118222/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008802 | 780970.V | 118222/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008803 | 780970.V | 118220/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008804 | 780970.V | 118221/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008805 | 780970.V | 118219/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008806 | 780970.V | 118221/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008807 | 780970.V | 118223/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008808 | 780970.V | 118224/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008809 | 780970.V | 118225/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008810 | 800907.V | 118267/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008811 | 800907.V | 118268/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008812 | 800907.V | 118268/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008813 | 800907.V | 118272/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008814 | 800907.V | 118258/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008815 | 800907.V | 118266/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008816 | 800907.V | 118267/2A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008817 | 800907.V | 118269/2A.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008818 | 800907.V | 118270/2A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008819 | 800907.V | 118270/1A.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008820 | 800907.V | 118266/2A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008821 | 800907.V | 118263/1.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008822 | 780970.V | 118217/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008823 | 780970.V | 118216/2A.V | 12480 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008824 | 780970.V | 118215/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008825 | 780970.V | 118220/2A.V | 12480 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008826 | 780970.V | 118217/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008827 | 780970.V | 118218/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008828 | 780970.V | 118219/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008829 | 800907.V | 118261/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008830 | 780970.V | 118218/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008831 | 800907.V | 118261/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008832 | 800907.V | 118262/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008833 | 800907.V | 118264/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008834 | 800907.V | 118260/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008835 | 800907.V | 118260/2A.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008836 | 780970.V | 118224/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008837 | 800907.V | 118262/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008838 | 800907.V | 118259/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008839 | 800907.V | 118259/2A.V | 11850 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008840 | 800907.V | 118272/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008841 | 800907.V | 118271/2A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008842 | 800907.V | 118271/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008843 | 800907.V | 118258/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008844 | 800907.V | 118264/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008845 | 800907.V | 118263/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008846 | 780977.V | 118254/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.008847 | 780977.V | 118249/2A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.008848 | 780977.V | 118253/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008849 | 780977.V | 118256/2A.V | 12450 | EC | PU
[9 empty] | 5021701 | 26.4.008850 | 780977.V | 118248/1.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.008594 | 800976.V | 119555/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008051 | 780991.V | 118554/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008853 | 780977.V | 118257/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008854 | 780977.V | 118252/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.008855 | 780977.V | 118255/2A.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008856 | 974770.V | 119538/1.V | 12450 | EC | PU
[9 empty] | 5021701 | 26.4.008857 | 974770.V | 119532/2.V | 12470 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008858 | 781079.V | 119603/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008859 | 781079.V | 119599/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008860 | 781079.V | 119598/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008861 | 781079.V | 119605/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008862 | 781079.V | 119598/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008863 | 781079.V | 119603/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008864 | 781079.V | 119605/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008865 | 781079.V | 119593/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008866 | 781079.V | 119596/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008867 | 781079.V | 119596/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008868 | 781079.V | 119599/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008869 | 781079.V | 119604/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008870 | 781079.V | 119606/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008871 | 781079.V | 119602/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008872 | 781079.V | 119601/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008873 | 781079.V | 119606/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008874 | 781079.V | 119600/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008875 | 781079.V | 119600/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008876 | 781079.V | 119593/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008877 | 974770.V | 119533/1.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008878 | 974770.V | 119533/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008879 | 974770.V | 119538/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008880 | 974770.V | 119531/1.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008881 | 974770.V | 119531/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008882 | 974770.V | 119534/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008883 | 974770.V | 119534/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008884 | 974770.V | 119535/2.V | 12450 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.008885 | 974770.V | 119537/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008886 | 974770.V | 119535/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008887 | 780977.V | 118248/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008888 | 974770.V | 119532/1.V | 12440 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.008889 | 974770.V | 119536/1.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008890 | 780977.V | 118249/1A.V | 12440 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008891 | 974770.V | 119537/1.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008892 | 974770.V | 119536/2.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.008903 | 800851.V | 118194/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008904 | 974720.V | 118503/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008905 | 974777.V | 119927/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008906 | 974777.V | 119928/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008907 | 974777.V | 119934/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008908 | 974777.V | 119926/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008909 | 974777.V | 119928/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008910 | 974777.V | 119929/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008911 | 974777.V | 119937/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008912 | 974777.V | 119931/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008913 | 974777.V | 119932/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008914 | 974777.V | 119926/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008915 | 974777.V | 119939/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008916 | 974777.V | 119938/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008917 | 781079.V | 119595/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008918 | 974777.V | 119930/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008919 | 974777.V | 119930/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008920 | 974777.V | 119935/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008921 | 781079.V | 119597/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008922 | 974777.V | 119933/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008923 | 781079.V | 119594/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008924 | 974777.V | 119936/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007791 | 974992.V | 122002/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008926 | 974777.V | 119927/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008927 | 974777.V | 119935/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008928 | 781079.V | 119602/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008929 | 781079.V | 119594/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008930 | 781079.V | 119595/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008931 | 974720.V | 118502/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008932 | 800851.V | 118196/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008933 | 974720.V | 118501/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008934 | 800851.V | 118196/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008935 | 974720.V | 118499/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008936 | 800851.V | 118191/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008937 | 800851.V | 118185/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008938 | 800851.V | 118190/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008939 | 800851.V | 118193/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008940 | 800851.V | 118194/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008941 | 800851.V | 118190/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008942 | 800851.V | 118184/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008943 | 800851.V | 118195/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008944 | 800851.V | 118187/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008945 | 800851.V | 118197/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008946 | 974720.V | 118498/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008947 | 974720.V | 118504/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008948 | 800851.V | 118184/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008949 | 800851.V | 118189/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008950 | 974720.V | 118500/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008951 | 974720.V | 118502/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008952 | 974720.V | 120851/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008953 | 974720.V | 118500/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008954 | 800851.V | 118185/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008955 | 974720.V | 120851/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008956 | 800851.V | 118189/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008957 | 800851.V | 118186/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008958 | 800851.V | 118195/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008959 | 800851.V | 118188/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008960 | 800851.V | 118192/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008961 | 800851.V | 118192/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008962 | 800851.V | 118197/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008963 | 800851.V | 118191/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008964 | 800851.V | 118193/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008965 | 800851.V | 118186/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008966 | 781079.V | 119604/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008967 | 974777.V | 119939/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008968 | 780977.V | 118251/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008969 | 780977.V | 118256/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008970 | 780977.V | 118250/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008971 | 800976.V | 119550/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008972 | 800977.V | 119571/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008973 | 800976.V | 119555/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008974 | 800976.V | 119550/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008975 | 800976.V | 119551/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008976 | 800977.V | 119573/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008977 | 800983.V | 119976/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008978 | 800977.V | 119578/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008979 | 800977.V | 119568/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008980 | 800977.V | 119574/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008981 | 780932.V | 118395/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008982 | 800977.V | 119579/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008983 | 780932.V | 118395/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008984 | 781237.V | 120712/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008985 | 780932.V | 118402/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008986 | 780977.V | 118254/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008987 | 780973.V | 118235/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008988 | 780977.V | 118255/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.002182 | 800223.V | 112462/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.002114 | 800233.V | 112487/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008991 | 974777.V | 119931/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008992 | 780977.V | 118250/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008993 | 974777.V | 119932/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008994 | 781079.V | 119597/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008995 | 974777.V | 119938/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008996 | 974777.V | 119933/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008997 | 974777.V | 119934/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008998 | 800851.V | 118187/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008999 | 974777.V | 119936/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.900028 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008274 | 781062.V | 119460/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.008272 | 781062.V | 119455/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | DT03610322 | 26.4.008507 | 800963.V | 119494/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | DT03610322 | 26.4.008285 | 975011.V | 122050/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008283 | 975011.V | 122055/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008113 | 800970.V | 119911/1A.V | 12450 | EC | PU | SEL | SI | SE
[9 empty] | DT03610322 | 26.4.002117 | 800233.V | 112490/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008327 | 975011.V | 122057/2.V | 11670 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007952 | 801198.V | 121330/1A.V | 10910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007773 | 801208.V | 122027/1A.V | 11570 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007736 | 781283.V | 121416/2.V | 11530 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA

## Pivot
| PO 5021701 | [7 empty] | PO 5021701 Totale | Totale complessivo
| 780325.V | 800222.V | 800223.V | 800229.V | 800232.V | 800233.V | 974058.V | 974062.V
ITP Steps.
Incoming Plate | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Pipe Forming | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Tack Welding | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
ID SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
OD SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
AUT1 | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Fluoroscopic |  |  | 3 | 1 | 1 | 1 | 4 | 2 | 12 | 12
Welding Repair |  | 2 |  | 1 |  |  | 1 |  | 4 | 4
MCE1 | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
MCE2
MCE Inspection | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
Straighness Re-work | 1 |  | 2 | 2 |  |  | 1 |  | 6 | 6
Hydro Test | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
AUT2
Phase Arr. | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
MUT_ | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
End UT | 27 | 13 | 19 | 17 | 24 | 16 | 15 | 26 | 157 | 157
X-Ray | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
OoR Pipe Body | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
Dimensional 1 | 25 | 12 | 18 | 15 | 24 | 16 | 15 | 25 | 150 | 150
Dimensional 2 | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
MPI | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
UT DHC | 25 | 12 | 17 | 15 | 24 | 16 | 14 | 24 | 147 | 147
Final Marking and Weighing | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149

## Chart
Este gráfico não está disponível na sua versão de Excel. Editar esta forma ou salvar esta pasta de trabalho em um formato de arquivo diferente quebrará o gráfico permanentemente.

## Repair
24OD x 1.268WT
REPAIR TABLE
DATE | Shift | Pipe Nº | Defect | Pipe Position (mm) | Extension (mm) | Remarks
2026-02-11 | 1 | 26.4.2089 | Weld heigh bead below the specified | 1200 | 300
2026-02-19 | 1 | 26.4.2205 | Slag Inclusion | 1450 | 100
2026-02-20 | 1 | 26.4.2207 | Underfill | 5510 | 130
2026-02-21 | 1 | 26.4.2252 | Stop/Start | 2320 | 200
2026-06-08 | 1 | 26.4.7866 | Weld Fail | 4600 | 200
2026-06-08 | 3 | 26.4.7838 | Weld Leak | 2500 | 200
2026-06-09 | 1 | 26.4.7840 | Slag Inclusion | 3360/5850 | 150/100
2026-06-10 | 1 | 26.4.7888 | Stop/Start | 8190 | 200
2026-06-10 | 1 | 26.4.7841 | Stop/Start | 2024 | 200
2026-06-10 | 1 | 26.4.7986 | Stop/Start | 9770 | 200
2026-06-10 | 1 | 26.4.7955 | Underfill | 3190 | 150
2026-06-10 | 1 | 26.4.8007 | Underfill | 9100 | 150
2026-06-10 | 1 | 26.4.8071 | Stop/Start | 2830 | 200
2026-06-10 | 3 | 26.4.8118 | Stop/Start | 7340 | 180
2026-06-10 | 3 | 26.4.8117 | Stop/Start | 3930 | 170
2026-06-11 | 3 | 26.4.8219 | Stop/Start | 11900 | 200
2026-06-12 | 1 | 24.6.8204 | Stop/Start | 6720 | 250
2026-06-12 | 3 | 24.6.8231 | Stop/Start | 5900/6500 | 100/100
2026-06-15 | 3 | 26.4.8344 | Stop/Start | 6400 | 200
2026-06-15 | 3 | 26.4.8222 | Stop/Start | 5100 | 200
2026-06-15 | 3 | 26.4.8313 | Stop/Start | 3560 | 200
2026-06-15 | 3 | 26.4.8360 | Stop/Start | 11630 | 150
2026-06-16 | 1 | 26.4.8326 | Stop/Start | 4600 | 300
2026-06-17 | 1 | 26.4.8456 | Stop/Start | 10570 | 300
2026-06-17 | 1 | 26.4.8401 | Stop/Start | 6300 | 300
2026-06-17 | 1 | 26.4.8406 | Underfill | 7775/9425/10340 | 150/150/150
2026-06-17 | 1 | 26.4.8519 | Pore | 9380 | 150
2026-06-17 | 3 | 26.4.8615 | Stop/Start | 3250 | 250
2026-06-18 | 1 | 26.4.8641 | Slag Inclusion | 2200 | 150
2026-06-18 | 3 | 26.4.8644 | Stop/Start | 4600 | 150
2026-06-18 | 3 | 26.4.8642 | Stop/Start | 2500 | 100
2026-06-19 | 3 | 26.4.8823 | Stop/Start | 1300 | 200
2026-06-19 | 3 | 26.4.8768 | Stop/Start | 3600 | 200
2026-06-19 | 3 | 26.4.8754 | Slag Inclusion | 6750 | 80

## Rejection
24OD x 1.268WT
REJECTION TABLE
DATE | Shift | Pipe Nº | Defect | Remarks
2026-02-11 | 1 | 26.4.2095 | Burn Through | MPQT Pipe (NCR-001)
2026-02-23 | 1 | 26.4.2094 | Pore | 2350x50mm
2026-02-23 | 1 | 26.4.2250 | WT Below Spec | 8100x640mm
2026-03-10 | 1 | 26.4.2114 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2185 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2107 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2145 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2148 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2144 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2149 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2180 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2115 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2086 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-04-22 | 1 | 26.4.2156 | Sample Removal | NA
2026-05-19 | 1 | 26.4.2117 | CVN Rejection | (NCR-004)
2026-06-02 | 2 | 26.4.7733 | Tack Weld Parameter | (NCR-009)
2026-06-09 | 1 | 26.4.7701 | Slag Inclusion | NA
2026-06-09 | 3 | 26.4.7859 | Slag Inclusion | NA
2026-06-10 | 1 | 26.4.7736 | Wall TKS Below the Spec. | NA
2026-06-11 | 2 | 26.4.8113 | Tack Weld Parameter | (NCR-009)
2026-06-12 | 1 | 26.4.7952 | MCE Mark
2026-06-13 | 3 | 26.4.7773 | Wall TKS Below the Spec.
2026-06-18 | 1 | 26.4.8540 | Wall TKS Below the Spec.
2026-06-18 | 3 | 26.4.8688 | Wall TKS Below the Spec.
2026-06-20 | 1 | 26.4.8181 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8194 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8200 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8201 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8205 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8206 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8208 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8250 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8251 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8260 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8264 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8267 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8269 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8270 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8273 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8275 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8276 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8285 | Bolt Mark | NCR-11
2026-06-20 | 1 | 26.4.8283 | Stamp Damage | NCR-11
2026-06-20 | 1 | 26.4.8360 | Stamp Damage | NCR-11
2026-06-20 | 1 | 26.4.8507 | Stamp Damage | NCR-11