## Dashboard
SAKARYA PROJECT - INSPECTION & TEST PLAN — PIPE PRODUCTION TRACKING
Input | 170
Seq. n° | ITP Step | Section | Count | Yield vs Input | Loss vs Input | Cumul. Loss | Remarks
1 | Incoming Plate | Forming | 170 | 100% | 0 | 0
2 | Pipe Forming | Forming | 170 | 100% | 0 | 0
3 | Tack Welding | Forming | 170 | 100% | 0 | 0
4 | ID SAWL | Forming | 170 | 100% | 0 | 0
5 | OD SAWL | Forming | 170 | 100% | 0 | 0
6 | AUT1 | Welding & NDT | 170 | 100% | 0 | 0
7 | Fluoroscopic | Welding & NDT | 12 | 7.059% | 158 | 158
8 | Welding Repair | Welding & NDT | 4 | 2.353% | 4 | 4
9 | MCE1 | Mechanical | 164 | 96.47% | 6 | 6
10 | MCE2 | Mechanical | 0 | — | — | —
11 | MCE Inspection | Mechanical | 164 | 96.47% | 6 | 6
12 | Straightness Re-work | Mechanical | 6 | — | — | —
13 | Hydro Test | Testing | 158 | 92.94% | 12 | 12
14 | AUT2 | Testing | 0 | — | — | —
15 | Phase Arr. | Testing | 158 | 92.94% | 12 | 12
16 | MUT | Testing | 158 | 92.94% | 12 | 12
17 | End UT | Testing | 157 | 92.35% | 13 | 13
18 | X-Ray | Testing | 156 | 91.76% | 14 | 14
19 | OoR Pipe Body | Dimensional & Final | 156 | 91.76% | 14 | 14
20 | Dimensional 1 | Dimensional & Final | 150 | 88.24% | 20 | 20
21 | Dimensional 2 | Dimensional & Final | 149 | 87.65% | 21 | 21
22 | MPI | Dimensional & Final | 149 | 87.65% | 21 | 21
23 | UT DHC | Dimensional & Final | 147 | 86.47% | 23 | 23
24 | Final Mark & Weigh | Dimensional & Final | 149 | 87.65% | 21 | 21
SUMMARY
Total Pipes |  |  |  | 170
Total pipes Accepted |  |  |  | 149
Overall Status % |  |  |  | 87.65%
Welding Repair |  |  |  | 47

## MPQT - WPQT
Overview MPQT / WPQT SAWL Line Pipe - Lab Tests Control Table SAKARYA PROJECT
OD X WT (in X in) | WPS Nº | Pipe Nº | Heat N° | Tenaris Labs Report | Chemical Compos. Analysis |  | Tensile Tests | [8 empty] | Transversal Compression Test |  | BM CVN Impact Testing -30°C |  | CVN Impact Testing of the Weld Seam @ -30°C | [12 empty] | CVN Impact Testing Transition Curve Base Metal @ +20°C to -120°C |  | Drop Weight Tear Testing (DWTT) |  | CTOD (AF) |  |  | CTOD (AC) |  |  | Grain Size BM | Guided Bend Tests |  |  | VicKers Hardness Tests |  |  | Macrographic Test | Flux Humidity (Karl Fischer) | Ring Splitting Test |  | HIC |  | SSC |  | Remarks
[5 empty] | BM | WM | Longitudinal BM | Longitudinal BM (Coated) | Transversal BM | Transversal BM (Coated) | Transversal WM | Transversal WM (DNV) | Transversal WM (Coated) | ID and OD All Weld | All Weld (Coated) | Without Inline Heat Treatment | Inline Heat Treatment (Coated) | AF | Coated | OD Weld Metal | OD Weld FL | OD Weld FL +2mm | OD Weld FL +5mm | Root Weld Metal | Root Weld FL | Root Weld FL +2mm | Root Weld FL +5mm | ID Weld Metal | ID Weld FL | ID Weld FL +2mm | ID Weld FL +5mm | WM (Coated) | AF | AF (Aged) | AF | Transition Curve | BM | WM | HAZ | BM | WM | HAZ |  | OD | ID | Side | BM | HAZ | WM | Interpenetration | WPQT | AF | AC | BM | WM | BM | WM
[5 empty] | 1/Pipe |  | All | All | All | All | All | WPQT Pipes | All | All | All | All |  | All |  | All | [12 empty] | All |  | All |  | All |  |  | All |  |  | All | All |  |  | All |  |  | All |  | All | All | All
24 x 1.268 | 3973 | 26.4.002096 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Border Line *CVN ID Fusino Line Rejected with single results 26J. *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002097 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 & IR-08 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *CVN ID Fusino Line Rejected with single results 29J *ReTest performed as per NCR-003 and approved for both Test
| 3973 | 26.4.002098 (AF) | 800223.V |  | IR-05 | IR-05 | IR-05 | N/A | IR-05 | N/A | IR-05 | N/A | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10
| 3974 | 26.4.002240 (AF) | 974058.V |  | IR-05 | IR-05 | IR-05 & IR-08 | N/A | IR-05 | N/A | IR-05 | IR-17 | N/A | IR-05 | N/A | IR-07 | N/A | IR-05 | N/A | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | N/A | IR-08 | IR-08 | IR-06 | IR-10 | IR-07 | IR-07 | IR-07 | N/A | N/A | N/A | IR-09 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | IR-05 | Approved | IR-07 | N/A | IR-07 | IR-07 | IR-10 | IR-10 | *RT05/Rm Longitudinal BM Tensile at Rejected *ReTest performed as per NCR-003 and approved
| 3973 | 26.4.002099 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002100 (AC) | 800223.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A
| 3973 | 26.4.002101 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
| 3973 | 26.4.002243 (AC) | 974058.V |  | N/A | N/A | N/A | IR-13 | N/A | IR-13 | N/A | N/A | IR-13 | N/A | IR-13 | N/A | IR-14 | N/A | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-14 | IR-14 | IR-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Approved | N/A | IR-14 | N/A | N/A | N/A | N/A | RT0.5/Rm for “AS FABRICATES” MPQT is: 0.93 however for the “AS COATED” in the QCP is specifying Informative
Repair Qualification
24 x 1.268 (STOP/START) | WPS-3973 | 26.4. 2128 (INT) | 800232.V |  |  |  | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-19 |  |  | N/A | IR-19 |  |  | N/A | IR-19 | IR-19 | IR-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | IR-18 | IR-18 | IR-18 | IR-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 26.4.2128 (EXT) |  |  |  |  | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-19 | IR-19 | IR-19 | N/A | IR-19 |  |  | N/A | IR-19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | IR-18 | IR-18 | IR-18 | IR-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OD 24 x 1.268 (rWPS) | WPS-265 (SHALLOW) | 26.4. 2128 |  |  |  |  | N/A | N/A | N/A | N/A | IR-20 |  | N/A |  | N/A | N/A | N/A | N/A | N/A | IR-20 | IR-20 | IR-20 | IR-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IR-20 | [6 empty] | N/A |  | N/A | N/A | Ongoing | N/A | Started on Jun. 18th 2026
| WPS-266 (DEEP) | [5 empty] | N/A | N/A | N/A | N/A | IR-20 |  | N/A | IR-20 | N/A | N/A | N/A | N/A | N/A | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | IR-20 |  |  |  |  | N/A |  | N/A | N/A | Ongoing | N/A | Started on Jun. 18th 2026
ID 24 x 1.268 (rWPS) | WPS-265 (SHALLOW) | 26.4. 2205 | 800222.V |  |  |  | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A
| WPS-266 (DEEP) | [5 empty] | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A

## 24 X 1.268 OFF
SAKARYA PROJECT - Overview Mass Production for SAWL Line Pipe - Lab Tests Control Table
OD24in X WT1.268in
OD X WT | Pipe Nº | Heat Plate N° | Chemical Compos. Analysis |  | Tensile Tests |  |  |  | Transversal Compression Test | BM CVN Impact Testing -30°C | CVN Impact Testing of the Weld Seam @ -30°C | [8 empty] | Drop Weight Tear Testing (DWTT) | Grain Size BM | Guided Bend Tests |  | VicKers Hardness Tests |  |  | Macrographic Test | HIC |  | Remarks
|  |  | BM | BM | Longitudinal BM | Transversal BM | Transversal WM | Transversal WM (Coated) | Inline Heat Treatment | AF | WM OD | WD ID | WM Root | FL OD | FL ID | FL Root | FL + 2 OD | FL + 2 ID | FL + 2 Root | BM |  | OD | ID | BM | HAZ | WM | Interpenetration | BM | WM
|  |  | 1/Pipe |  | 1/Heat | 1/Heat | 1/Heat | All | 4/Heat 20 1/Heat | 1/Heat | 1/Heat | [8 empty] | 1/Heat | 1 / 5 Heats | 1/Heat |  | 1/Heat |  |  | 1/Shift | 1 /Heat (first five Heat, than 1 / 10)
36 x 0.406 | 11646 | 780325 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at OD FL+2mm (NCR-004) - Re-test performed and approved
|  | 780932 | IR-21 | IR-21 | IR-21 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22
|  | 780939 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-22 | IR-22 | IR-22
780942
780943
780944
|  | 780970 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21
|  | 780973 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 780977 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-21
|  | 780978 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 780979 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22
|  | 780991 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 / IR-21 | IR-20 | IR-20 / IR-21 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 780992 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 / IR-21 | IR-20 / IR-21 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21
|  | 780993 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 / IR-21 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 780995 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 / IR-21 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 |  |  |  | CVN Reest at the same Pipe Rejected
780996
781001
|  | 781004 | IR-21 |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-21
|  | 781034 | IR-21 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781035 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  | IR-22 | IR-22 | IR-22
|  | 781040 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781052 | IR-21 |  | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22
|  | 781062 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 781068 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 781079 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-21 | IR-21 | IR-21
781080
781082
|  | 781083 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 781085 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 781086 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 781090 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 781237 | IR-21 | IR-21 | IR-21 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781241 | IR-21 | IR-21 | IR-21 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-21 | IR-21 | IR-21 | IR-21
|  | 781242 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781243 | IR-22 | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781250 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781251 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781253 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-21
|  | 781254 | IR-21 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 781266 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  | IR-22 | IR-22 | IR-22
|  | 781267 | IR-22 |  | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-21
|  | 781268 | IR-22 |  | IR-22
|  | 781276 |  |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22 |  |  |  | IR-22
781277
|  | 781278 |  |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22
|  | 781282 | IR-22 |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22
|  | 781283 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-20 | IR-19 | IR-20 | IR-19 | IR-19 | IR-19 | IR-21 |  | IR-20 | IR-20 |  |  |  | IR-20
|  | 781297 | IR-19 | IR-19 | IR-21 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 / IR-21 | IR-19 | IR-19 | IR-19 | IR-19 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
781306
781310
781313
|  | 781329 | IR-21 |  | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 |  |  |  | IR-21
782314
782398
782675
782709
782716
782717
782718
782719
782722
782724
782725
782732
782921
782922
782923
782924
782934
782936
782937
782938
782941
782942
782944
782947
782949
782950
782952
782953
782955
782957
782962
782965
782966
782969
782970
783055
783061
783065
783069
783070
783075
783077
783078
783087
783088
783089
783094
783095
783330
783332
783334
783337
783338
783341
783342
783343
783347
783348
783354
783355
783358
783368
783369
783370
783371
783372
783378
783380
783386
783391
783542
783543
783544
783545
783546
783547
783576
783580
783581
783589
783606
783607
783610
783613
783621
783632
783804
783805
783810
784029
784030
784033
784036
784038
784043
784056
784057
784061
784085
784089
784090
784097
784117
784126
784128
784129
784130
784133
784296
784300
784301
784302
784303
784304
784305
784315
784334
784335
784337
784338
784339
784342
784343
784344
784345
784348
784351
784386
784388
784389
784404
784405
784577
784579
784585
784619
784620
784621
784623
784624
784648
784649
784650
784653
784656
784660
784661
784662
784664
784668
784676
784677
784679
784681
784682
784683
784686
784687
784688
784872
784873
784876
784877
784889
784890
784891
784892
784910
784913
784917
784918
785189
785190
785191
785193
785200
785201
785203
785204
785205
785249
785250
785251
785257
785261
785262
785273
785282
785283
785582
785583
785598
785601
785605
785606
785607
785632
785844
785851
786002
786008
786011
|  | 800222 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio FL (NCR-004) - Re-test performed and approved
800223
|  | 800229 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 / IR-15 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersection, on the NCR-004 Tenaris have informed that the CVN specimen of Intersevtion WM, was with the notch on the wrong sectiom and it is a FL Re-test performed and approved
|  | 800232 | IR-06 | IR-09 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08
|  | 800233 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 IR-15 IR-17 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08 | CVN Failure at Intersectio ID and OD FL (NCR-004) - Re-test performed Rejected on the same pipe (26.4.2117). Retest Performed and approved in two addtional Pipes from the same Test unit and approved (26.4.2147 and 2152)
|  | 800840 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800841 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800848 | IR-21 | IR-21 | IR-20 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 / IR-21 |  | IR-22 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800851 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 800907 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-22 | IR-22 | IR-22
|  | 800908 | IR-22 |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22 |  |  |  | IR-22
|  | 800942 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22
|  | 800943 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 | IR-20 / IR-21 | IR-20 | IR-20 | IR-21 | IR-20 | IR-21 | IR-22 | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 800957 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 800958 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20
|  | 800959 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-20 | IR-21 | IR-21 | IR-21 | IR-21 | IR-22 | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800963 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21
|  | 800964 | IR-21 | IR-21 | IR-20 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800965 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 | IR-22 | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 |  | IR-22 | IR-22
|  | 800970 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-20 | IR-21 | IR-20 | IR-20 | IR-20 | IR-21 | IR-20 | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 800976 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
|  | 800977 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21
800979
800980
|  | 800983 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 / IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-22 | IR-22 | IR-22 | IR-21
|  | 800995 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 |  | IR-21 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-21 | IR-21 | IR-22 | IR-22 | IR-22
801143
801144
|  | 801152 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22
|  | 801153 | IR-22 |  | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22 |  |  |  | IR-22
|  | 801169 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 801174 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-20 / IR-21 | IR-20 / IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21
801189
|  | 801193 |  |  | IR-22
|  | 801194 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
801196
|  | 801197 | IR-21 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  |  |  | IR-22 | IR-22 | IR-22 | IR-21
|  | 801198 | IR-20 | IR-21 | IR-20 | IR-21 | IR-21 |  |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-21 | IR-20 | IR-21 | IR-20 | IR-20 | IR-20 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-20
801206
|  | 801208 | IR-19 | IR-19 | IR-21 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
801211
|  | 801219 | IR-19 | IR-19 | IR-20 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 | IR-19 / IR-21 | IR-19 | IR-19 | IR-19 | IR-21 |  | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-20 | IR-22 | IR-22
801223
801231
801232
801234
801237
802262
802263
802264
802270
802271
802272
802355
802358
802367
802369
802381
802385
802389
802390
802391
802586
802588
802589
802593
802594
802595
802917
802918
802921
802924
802952
802953
802967
802968
802970
802971
803142
803143
803144
803145
803147
803148
803151
803163
803164
803167
803171
803259
803263
803274
803275
803281
803285
803286
803291
803293
803579
803589
803596
803599
803622
803627
803816
803819
803846
803851
803857
804234
804244
804289
804296
804313
804318
804321
804341
804361
804362
804365
804366
804367
804390
804391
804392
804410
804411
804416
804592
804593
804595
804607
804608
804609
804618
804638
804643
804657
804658
804665
804666
804667
804681
804682
804685
804868
804872
804874
804884
804889
804891
804902
804906
804910
805195
805203
805246
805247
805249
805257
805258
805259
805260
805269
805270
805271
805273
805278
805568
805569
805577
805578
805593
805596
805597
805857
805858
805860
805861
805862
805865
805870
805873
805879
805883
805886
805887
805908
806038
806039
806041
806049
806055
806057
806086
806087
806088
806089
806090
806093
806094
806116
806122
806123
806124
806126
806127
806445
974058
|  | 974062 | IR-06 | IR-06 | IR-11 | IR-09 | IR-09 |  |  | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-11 | IR-09 | IR-11 | IR-09 | IR-09 | IR-06 | IR-06 | IR-06 | IR-06 | IR-08 | IR-08
974649
|  | 974683 |  |  | IR-22
|  | 974686 |  |  | IR-22
974689
974711
974719
|  | 974720 | IR-21 |  | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 974750 | IR-21 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 974765 | IR-21 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
|  | 974770 | IR-21 |  | IR-21 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-21 / IR-21 |  | IR-21 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | [6 empty] | CVN Reest at the same Pipe Rejected
|  | 974777 | IR-21 | IR-21 | IR-22 | IR-21 | IR-21 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-21 | IR-21 | IR-22 | IR-22 | IR-22
|  | 974783 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | [6 empty] | IR-22 |  | IR-22 | [5 empty] | IR-22 | IR-22 |  |  |  | IR-22
|  | 974794 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22
|  | 974803 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 | IR-21
|  | 974807 | IR-22 | IR-22 | IR-22 | IR-22 | IR-22 |  |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 | IR-22 |  | IR-22 |  |  | IR-22 | IR-22 | IR-22 | IR-22 | IR-22
974972
974979
|  | 974992 | IR-19 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-19 | IR-19 | IR-20 | IR-19 | IR-20 / IR-21 | IR-20 | IR-20 / IR-21 | IR-19 | IR-20 | IR-19 | IR-21 | IR-22 | IR-20 | IR-20 | IR-21 | IR-21 | IR-21
|  | 975002 | IR-19 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-19 | IR-21 | IR-19 | IR-19 | IR-19 | IR-21 | IR-19 | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21 | IR-20
|  | 975011 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-20
|  | 975015 | IR-20 | IR-20 | IR-21 | IR-20 | IR-20 |  |  | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 | IR-21 |  | IR-20 | IR-20 | IR-21 | IR-21 | IR-21
975829
975830
975834
975843
975924
975938
975939
975940
975943
975944
975945
975946
975949
975953
975954
975960
975964
975965
976154
976155
976156
976487
976511
976512
976514
976515
976516
976519
976524
976525
976526
976722
976731
976836
976839
976842
976846
976849
976854
976857
976860
977156
977169
977170
977194
977200
977201
977205
977206
977405
977406
977407
977408
977411
977419
977440
977443
977448
977450
977451
977458
977459
977460
977463
977643
977645
977646
977869
977870
977874
977884
977886
977889
977892
977895
977896
977898
977899
977901
977905
977906
977929
977931
977935
977937
977939
977942
977945
977947
977949
977950
977951
977952
977960
977962
977964
977965
977966
978133
978136
978141
978146
978147
978160
978162
978197
978204
978205
978214
978215
978217
978255
978429
978431
978434
978435
978472
978499
978515
978516
978521
978749
978753
978967
979033
979156
979157
979158
979165
979173
979174
979175
979208
979209
979441
979444
979446
979454
979458
979459
979462
979466
979482
979483
979484
979602
979603
979604
979608
979611
979615
979616
979619
979620
979621
979622
979625
979655
979662
979686
979688
979689
979999
980001
980002
980003
980004
980005
980006
980008

## PO5021701
Totale | [7 empty] | 170 |  |  |  |  | 0 | 2602 | 2569 | 2562 | 2506 | 2478 | 2463 | 19 | 84 | 1915 | 2366 | 28 | 2352 | 2350 | 2343 | 2327 | 2323 | 2320 | 2300 | 2245 | 2227 | 2216 | 1302
Seq. N° | Tenaris Batch | Pipe Dimensional | Pipe Std | Pipe Number | Heat Number | Plate Number | Pipe length | Total Pipes | Tenaris Lote | Pipe N° | Heat N° | Plate N° | Pipe length2 | Plate Entrance | Pipe Forming | Tack Welding | ID SAWL | OD SAWL | AUT1 in House | Fluoroscopic/TOFD In House | Repair | MCE 1 | MCE 2 | Straighness Re-work | Hydrostatic Test | Phase Array | MUT | Pipe End UT | X-Ray | OoR Pipe Body | Dimensional 1 | Dimensional 2 | MPI | Final Marking and Weighing | UT DHC
1 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002086 | 800229.V | 112430/2.V | 12350 | 1 | 4RF0050216 | 26.4.008820 | 800907.V | 118266/2A.V | 10560 | EC | PU | SEL
2 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002211 | 800222.V | 112447/1.V | 12450 | 1 | 4RF0150217 | 26.4.008272 | 781062.V | 119455/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
3 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002085 | 800229.V | 112426/2.V | 12380 | 1 | 4RF0150217 | 26.4.008264 | 781062.V | 119459/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
4 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002089 | 800229.V | 112427/1.V | 12470 | 1 | 4RF0150217 | 26.4.008273 | 781062.V | 119460/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
5 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002090 | 800229.V | 112432/1.V | 12360 | 1 | 4RF0150217 | 26.4.008194 | 801174.V | 120813/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
6 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002147 | 800233.V | 112487/2.V | 12460 | 1 | 4RF0150217 | 26.4.008215 | 801174.V | 120812/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
7 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002092 | 800229.V | 112424/1.V | 12360 | 1 | 4RF0150217 | 26.4.008263 | 781062.V | 119463/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
8 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002088 | 800229.V | 112426/1.V | 12430 | 1 | 4RF0150217 | 26.4.008195 | 801174.V | 120819/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
9 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002094 | 800229.V | 112430/1.V | 12470 | 1 | 4RF0150217 | 26.4.008193 | 801174.V | 120817/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
10 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002095 | 974058.V | 112411/1.V | 12460 | 1 | 4RF0150217 | 26.4.008217 | 801174.V | 120824/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
11 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002096 | 974058.V | 112412/2.V | 12470 | 1 | 4RF0150217 | 26.4.008249 | 781062.V | 119457/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
12 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002097 | 800223.V | 112460/1.V | 12370 | 1 | 4RF0150217 | 26.4.008245 | 975015.V | 121403/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
13 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002098 | 800223.V | 112459/2.V | 12370 | 1 | 4RF0150217 | 26.4.008243 | 975015.V | 121394/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
14 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002115 | 800233.V | 112488/2.V | 12450 | 1 | 4RF0150217 | 26.4.008259 | 975015.V | 121395/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
15 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002100 | 800223.V | 112460/2.V | 12470 | 1 | 4RF0150217 | 26.4.008269 | 781062.V | 119455/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
16 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002101 | 974058.V | 112412/1.V | 12460 | 1 | 4RF0150217 | 26.4.008275 | 781062.V | 119457/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
17 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002102 | 974058.V | 112411/2.V | 12460 | 1 | 4RF0150217 | 26.4.008183 | 801174.V | 120816/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
18 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002103 | 800229.V | 112427/2.V | 12440 | 1 | 4RF0150217 | 26.4.008237 | 781062.V | 119450/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
19 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002093 | 800229.V | 112425/2.V | 12440 | 1 | 4RF0150217 | 26.4.008181 | 801169.V | 120794/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA
20 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002105 | 800229.V | 112425/1.V | 12340 | 1 | 4RF0150217 | 26.4.008209 | 801169.V | 120796/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
21 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002106 | 800229.V | 112422/2.V | 12320 | 1 | 4RF0150217 | 26.4.008246 | 975015.V | 121405/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
22 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002107 | 800229.V | 112423/2.V | 12370 | 1 | 4RF0150217 | 26.4.008265 | 781062.V | 119453/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
23 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002108 | 800229.V | 112424/2.V | 12330 | 1 | 4RF0150217 | 26.4.008208 | 801169.V | 120796/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
24 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002109 | 800229.V | 112428/2.V | 12470 | 1 | 4RF0150217 | 26.4.009781 | 974683.V | 118480/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
25 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002110 | 800229.V | 112423/1.V | 12300 | 1 | 4RF0150217 | 26.4.008206 | 801169.V | 120797/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX
26 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002111 | 800229.V | 112431/1.V | 12440 | 1 | 4RF0150217 | 26.4.008187 | 801169.V | 120795/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
27 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002112 | 800229.V | 112428/1.V | 12440 | 1 | 4RF0150217 | 26.4.008184 | 801169.V | 120791/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
28 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002113 | 800229.V | 112429/2.V | 12470 | 1 | 4RF0150217 | 26.4.007859 | 975002.V | 121347/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
29 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002114 | 800233.V | 112487/1.V | 12450 | 1 | 4RF0150217 | 26.4.008306 | 975011.V | 122051/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
30 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002099 | 800223.V | 112459/1.V | 12460 | 1 | 4RF0150217 | 26.4.008202 | 801174.V | 120821/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
31 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002116 | 800233.V | 112485/2.V | 12020 | 1 | 4RF0150217 | 26.4.008244 | 975015.V | 121399/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
32 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002117 | 800233.V | 112490/1.V | 12020 | 1 | 4RF0150217 | 26.4.002156 | 780325.V | 112409/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB |  |  |  |  | DHC
33 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002118 | 800232.V | 112444/2.V | 12470 | 1 | 4RF0150217 | 26.4.008252 | 781062.V | 119456/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
34 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002119 | 800233.V | 112483/1.V | 12450 | 1 | 4RF0150217 | 26.4.008199 | 801174.V | 120821/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
35 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002120 | 800232.V | 112437/2.V | 12450 | 1 | 4RF0150217 | 26.4.008207 | 801169.V | 120793/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
36 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002121 | 800232.V | 112441/2.V | 12450 | 1 | 4RF0150217 | 26.4.009861 | 780942.V | 118449/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
37 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002122 | 800232.V | 112434/2.V | 12450 | 1 | 4RF0150217 | 26.4.008266 | 781062.V | 119459/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
38 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002123 | 800232.V | 112437/1.V | 12450 | 1 | 4RF0150217 | 26.4.008189 | 801174.V | 120818/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
39 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002124 | 800232.V | 112436/2.V | 12450 | 1 | 4RF0150217 | 26.4.008251 | 781062.V | 119452/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
40 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002125 | 800232.V | 112442/1.V | 12450 | 1 | 4RF0150217 | 26.4.008260 | 781062.V | 119452/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
41 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002104 | 800229.V | 112429/1.V | 12430 | 1 | 4RF0150217 | 26.4.008271 | 781062.V | 119461/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
42 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002127 | 800232.V | 112436/1.V | 12450 | 1 | 4RF0150217 | 26.4.008191 | 801174.V | 120813/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
43 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002128 | 800232.V | 112434/1.V | 12450 | 1 | 4RF0150217 | 26.4.008205 | 801169.V | 120797/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
44 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002129 | 800232.V | 112433/2.V | 12450 | 1 | 4RF0150217 | 26.4.009464 | 974794.V | 120885/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
45 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002130 | 800232.V | 112444/1.V | 12450 | 1 | 4RF0150217 | 26.4.007733 | 781283.V | 121420/1.V | 12460 | EC | PU | SEL
46 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002131 | 800232.V | 112438/1.V | 12450 | 1 | 4RF0150217 | 26.4.002250 | 974058.V | 112414/1.V | 12460 | EC | PU | SEL | SI | SE | U1
47 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002132 | 800232.V | 112440/2.V | 12450 | 1 | 4RF0150217 | 26.4.008688 | 780939.V | 118434/1.V | 12460 | EC | PU | SEL | SI | SE
48 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002133 | 800232.V | 112441/1.V | 12450 | 1 | 4RF0150217 | 26.4.008190 | 801169.V | 120794/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
49 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002134 | 800232.V | 112443/2.V | 12450 | 1 | 4RF0150217 | 26.4.008268 | 781062.V | 119454/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
50 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002135 | 800232.V | 112445/2.V | 12450 | 1 | 4RF0150217 | 26.4.008274 | 781062.V | 119460/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
51 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002136 | 800232.V | 112435/1.V | 12450 | 1 | 4RF0150217 | 26.4.008197 | 801174.V | 120825/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
52 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002137 | 800232.V | 112445/1.V | 12450 | 1 | 4RF0150217 | 26.4.008200 | 801174.V | 120820/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
53 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002138 | 800232.V | 112440/1.V | 12450 | 1 | 4RF0150217 | 26.4.008270 | 781062.V | 119463/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
54 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002139 | 800232.V | 112435/2.V | 12450 | 1 | 4RF0150217 | 26.4.008201 | 801174.V | 120814/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
55 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002140 | 800232.V | 112439/2.V | 12450 | 1 | 4RF0150217 | 26.4.008576 | 800977.V | 119578/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
56 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002141 | 800232.V | 112438/2.V | 12450 | 1 | 4RF0150217 | 26.4.008185 | 801174.V | 120824/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
57 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002142 | 800232.V | 112443/1.V | 12450 | 1 | 4RF0150217 | 26.4.008258 | 975015.V | 121399/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
58 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002143 | 800232.V | 112442/2.V | 12450 | 1 | 4RF0150217 | 26.4.008196 | 801174.V | 120819/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
59 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002144 | 800233.V | 112484/2.V | 12470 | 1 | 4RF0150217 | 26.4.008276 | 975015.V | 121396/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
60 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002145 | 800233.V | 112486/1.V | 12470 | 1 | 4RF0150217 | 26.4.008267 | 781062.V | 119453/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
61 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002146 | 800233.V | 112484/1.V | 12450 | 1 | 4RF0150217 | 26.4.008261 | 975015.V | 121397/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
62 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002091 | 800229.V | 112431/2.V | 12360 | 1 | 4RF0150217 | 26.4.008540 | 800983.V | 119971/2.V | 12460 | EC | PU | SEL | SI | SE
63 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002148 | 800233.V | 112490/2.V | 12450 | 1 | 4RF0150217 | 26.4.008248 | 781062.V | 119454/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
64 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002149 | 800233.V | 112483/2.V | 12450 | 1 | 4RF0150217 | 26.4.008250 | 781062.V | 119450/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
65 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002150 | 800233.V | 112489/1.V | 12450 | 1 | 4RF0150217 | 26.4.008043 | 800965.V | 119508/1.V | 12470 | EC | PU | SEL | SI | SE | U1
66 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002151 | 800233.V | 112485/1.V | 12450 | 1 | 4RF0150217 | 26.4.008279 | 781052.V | 119836/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
67 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002152 | 800233.V | 112489/2.V | 12450 | 1 | 4RF0150217 | 26.4.008186 | 801174.V | 120818/1A.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
68 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002153 | 800233.V | 112486/2.V | 12450 | 1 | 4RF0150217 | 26.4.008210 | 801169.V | 120793/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
69 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002154 | 780325.V | 112403/1.V | 12470 | 1 | 4RF0150217 | 26.4.008257 | 975015.V | 121398/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
70 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002155 | 780325.V | 112405/2.V | 12450 | 1 | 4RF0150217 | 26.4.008192 | 801169.V | 120792/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
71 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002156 | 780325.V | 112409/2.V | 12040 | 1 | 4RF0150217 | 26.4.008198 | 801174.V | 120825/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
72 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002157 | 780325.V | 112406/2.V | 12480 | 1 | 4RF0150217 | 26.4.008182 | 801174.V | 120820/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
73 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002158 | 780325.V | 112407/2.V | 12450 | 1 | 4RF0150217 | 26.4.008548 | 800995.V | 120694/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB
74 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002159 | 780325.V | 112405/1.V | 12450 | 1 | 4RF0150217 | 26.4.008262 | 975015.V | 121397/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
75 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002160 | 780325.V | 112397/2.V | 12450 | 1 | 4RF0150217 | 26.4.009356 | 780978.V | 118520/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX
76 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002161 | 780325.V | 112404/2.V | 12450 | 1 | 4RF0150217 | 26.4.009564 | 781268.V | 121011/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
77 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002162 | 800233.V | 112488/1.V | 12450 | 1 | 4RF0150217 | 26.4.008203 | 801169.V | 120795/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM |  | DHC
78 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002163 | 780325.V | 112404/1.V | 12450 | 1 | 4RF0150217 | 26.4.008307 | 975011.V | 122047/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
79 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002164 | 780325.V | 112408/1.V | 12450 | 1 | 4RF0150217 | 26.4.008188 | 801174.V | 120823/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
80 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002165 | 780325.V | 112408/2.V | 12450 | 1 | 4RF0150217 | 26.4.009073 | 781034.V | 119435/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
81 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002166 | 780325.V | 112400/2.V | 12450 | 1 | 4RF0150217 | 26.4.008254 | 975015.V | 121393/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
82 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002167 | 780325.V | 112399/2.V | 12450 | 1 | 4RF0150217 | 26.4.008247 | 975015.V | 121405/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
83 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002168 | 780325.V | 112401/2.V | 12450 | 1 | 4RF0150217 | 26.4.008253 | 781062.V | 119456/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
84 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002126 | 800232.V | 112439/1.V | 12450 | 1 | 5021601 | 26.4.002179 | 800223.V | 112461/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
85 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002170 | 780325.V | 112403/2.V | 12450 | 1 | 5021601 | 26.4.002090 | 800229.V | 112432/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
86 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002171 | 780325.V | 112401/1.V | 12070 | 1 | 5021601 | 26.4.002170 | 780325.V | 112403/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
87 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002172 | 780325.V | 112402/2.V | 12450 | 1 | 5021601 | 26.4.002238 | 974058.V | 112416/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
88 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002173 | 780325.V | 112399/1.V | 12450 | 1 | 5021601 | 26.4.002113 | 800229.V | 112429/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | [9 empty] | BA
89 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002174 | 974062.V | 112482/1.V | 12450 | 1 | 5021601 | 26.4.009205 | 781266.V | 120992/2.V | 10550 | EC | PU | SEL | [6 empty] | EX2
90 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002175 | 974062.V | 112470/2.V | 12450 | 1 | 5021701 | 26.4.002123 | 800232.V | 112437/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
91 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002176 | 974062.V | 112478/1.V | 12460 | 1 | 5021701 | 26.4.002252 | 974058.V | 112418/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
92 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002177 | 974062.V | 112481/2.V | 12460 | 1 | 5021701 | 26.4.002121 | 800232.V | 112441/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
93 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002178 | 800223.V | 112461/2.V | 12450 | 1 | 5021701 | 26.4.002119 | 800233.V | 112483/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
94 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002179 | 800223.V | 112461/1.V | 12460 | 1 | 5021701 | 26.4.007968 | 780993.V | 118569/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
95 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002180 | 800223.V | 112463/2.V | 12450 | 1 | 5021701 | 26.4.002243 | 974058.V | 113145/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
96 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002181 | 800223.V | 112464/2.V | 12460 | 1 | 5021701 | 26.4.002116 | 800233.V | 112485/2.V | 11820 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
97 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002182 | 800223.V | 112462/2.V | 12450 | 1 | 5021701 | 26.4.002114 | 800233.V | 112487/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
98 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002183 | 800223.V | 112458/2.V | 12450 | 1 | 5021701 | 26.4.002234 | 800222.V | 112450/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
99 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002184 | 800223.V | 112464/1.V | 12450 | 1 | 5021701 | 26.4.002111 | 800229.V | 112431/1.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
100 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002185 | 800223.V | 112463/1.V | 12450 | 1 | 5021701 | 26.4.002109 | 800229.V | 112428/2.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
101 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002186 | 800223.V | 112454/2.V | 12450 | 1 | 5021701 | 26.4.008465 | 800848.V | 118421/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
102 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002187 | 800223.V | 112458/1.V | 12470 | 1 | 5021701 | 26.4.007935 | 801198.V | 121332/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
103 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002188 | 800223.V | 112455/2.V | 12450 | 1 | 5021701 | 26.4.002226 | 974062.V | 112469/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
104 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002189 | 800223.V | 112456/1.V | 12460 | 1 | 5021701 | 26.4.002107 | 800229.V | 112423/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
105 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002190 | 800223.V | 112454/1.V | 12470 | 1 | 5021701 | 26.4.002106 | 800229.V | 112422/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
106 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002191 | 800223.V | 112462/1.V | 12460 | 1 | 5021701 | 26.4.002222 | 974062.V | 112480/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
107 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002192 | 800223.V | 112455/1.V | 12470 | 1 | 5021701 | 26.4.002105 | 800229.V | 112425/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
108 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002193 | 800223.V | 112457/2.V | 12450 | 1 | 5021701 | 26.4.002104 | 800229.V | 112429/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
109 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002194 | 780325.V | 112397/1.V | 12460 | 1 | 5021701 | 26.4.007919 | 800957.V | 119864/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
110 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002195 | 800223.V | 112457/1.V | 12460 | 1 | 5021701 | 26.4.009393 | 780978.V | 118522/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
111 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002196 | 780325.V | 112402/1.V | 12450 | 1 | 5021701 | 26.4.002108 | 800229.V | 112424/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
112 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002197 | 780325.V | 112400/1.V | 12460 | 1 | 5021701 | 26.4.002230 | 974062.V | 112475/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
113 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002198 | 780325.V | 112398/1.V | 12450 | 1 | 5021701 | 26.4.002110 | 800229.V | 112423/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
114 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002199 | 780325.V | 112398/2.V | 12450 | 1 | 5021701 | 26.4.007951 | 801198.V | 121330/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
115 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002200 | 780325.V | 112410/2.V | 12470 | 1 | 5021701 | 26.4.002112 | 800229.V | 112428/1.V | 12040 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
116 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002201 | 780325.V | 112409/1.V | 12450 | 1 | 5021701 | 26.4.002239 | 974058.V | 112416/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
117 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002202 | 780325.V | 112407/1.V | 12450 | 1 | 5021701 | 26.4.002115 | 800233.V | 112488/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
118 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002203 | 780325.V | 112410/1.V | 12450 | 1 | 5021701 | 26.4.008530 | 800995.V | 120693/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
119 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002204 | 800222.V | 112448/1.V | 12460 | 1 | 5021701 | 26.4.002118 | 800232.V | 112444/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
120 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002205 | 800222.V | 112449/1.V | 12460 | 1 | 5021701 | 26.4.002247 | 800222.V | 112451/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
121 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002206 | 800222.V | 112448/2.V | 12480 | 1 | 5021701 | 26.4.002120 | 800232.V | 112437/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
122 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002207 | 800222.V | 112452/1.V | 12450 | 1 | 5021701 | 26.4.007985 | 780993.V | 118561/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
123 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002208 | 800222.V | 112447/2.V | 12470 | 1 | 5021701 | 26.4.002122 | 800232.V | 112434/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
124 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002209 | 800222.V | 112446/1.V | 12460 | 1 | 5021701 | 26.4.007730 | 781283.V | 121418/1.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
125 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002210 | 800222.V | 112446/2.V | 12450 | 1 | 5021701 | 26.4.002124 | 800232.V | 112436/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
126 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002087 | 800229.V | 112432/2.V | 12470 | 1 | 5021701 | 26.4.002218 | 974062.V | 112474/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
127 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002212 | 974062.V | 112471/2.V | 12470 | 1 | 5021701 | 26.4.002103 | 800229.V | 112427/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
128 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002213 | 974062.V | 112475/2.V | 12460 | 1 | 5021701 | 26.4.002102 | 974058.V | 112411/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
129 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002214 | 974062.V | 112473/1.V | 12460 | 1 | 5021701 | 26.4.002214 | 974062.V | 112473/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
130 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002215 | 974062.V | 112477/1.V | 12460 | 1 | 5021701 | 26.4.002101 | 974058.V | 112412/1.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
131 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002216 | 974062.V | 112476/1.V | 12460 | 1 | 5021701 | 26.4.002100 | 800223.V | 112460/2.V | 12320 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
132 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002217 | 974062.V | 112476/2.V | 12460 | 1 | 5021701 | 26.4.008401 | 781086.V | 120902/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
133 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002218 | 974062.V | 112474/2.V | 12370 | 1 | 5021701 | 26.4.007903 | 800957.V | 119870/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
134 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002219 | 974062.V | 112474/1.V | 12460 | 1 | 5021701 | 26.4.002210 | 800222.V | 112446/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
135 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002220 | 974062.V | 112470/1.V | 12470 | 1 | 5021701 | 26.4.002099 | 800223.V | 112459/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
136 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002221 | 974062.V | 112471/1.V | 12450 | 1 | 5021701 | 26.4.002098 | 800223.V | 112459/2.V | 12340 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | [7 empty] | DHC
137 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002222 | 974062.V | 112480/2.V | 12450 | 1 | 5021701 | 26.4.002206 | 800222.V | 112448/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
138 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002223 | 974062.V | 112472/2.V | 12380 | 1 | 5021701 | 26.4.002097 | 800223.V | 112460/1.V | 12300 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | [7 empty] | DHC
139 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002224 | 974062.V | 112473/2.V | 12450 | 1 | 5021701 | 26.4.002096 | 974058.V | 112412/2.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | [7 empty] | DHC
140 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002225 | 974062.V | 112478/2.V | 12450 | 1 | 5021701 | 26.4.007886 | 800957.V | 119867/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
141 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002226 | 974062.V | 112469/2.V | 12450 | 1 | 5021701 | 26.4.002202 | 780325.V | 112407/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
142 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002227 | 974062.V | 112482/2.V | 12450 | 1 | 5021701 | 26.4.002095 | 974058.V | 112411/1.V | 12460 | EC | PU | SEL | SI | SE | U1
143 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002228 | 974062.V | 112479/1.V | 12460 | 1 | 5021701 | 26.4.002094 | 800229.V | 112430/1.V | 11360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE
144 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002229 | 974062.V | 112469/1.V | 12450 | 1 | 5021701 | 26.4.002198 | 780325.V | 112398/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
145 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002230 | 974062.V | 112475/1.V | 12450 | 1 | 5021701 | 26.4.002093 | 800229.V | 112425/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
146 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002231 | 974062.V | 112479/2.V | 12450 | 1 | 5021701 | 26.4.002092 | 800229.V | 112424/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
147 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002232 | 974062.V | 112477/2.V | 12470 | 1 | 5021701 | 26.4.009133 | 974765.V | 119919/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
148 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002233 | 974062.V | 112472/1.V | 12470 | 1 | 5021701 | 26.4.009132 | 974765.V | 119915/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
149 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002234 | 800222.V | 112450/1.V | 12450 | 1 | 5021701 | 26.4.008337 | 781085.V | 120895/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
150 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002235 | 800222.V | 112451/1.V | 12450 | 1 | 5021701 | 26.4.007870 | 801219.V | 122060/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
151 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002236 | 974058.V | 112417/1.V | 12470 | 1 | 5021701 | 26.4.002194 | 780325.V | 112397/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
152 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002237 | 974058.V | 112413/2.V | 12480 | 1 | 5021701 | 26.4.002091 | 800229.V | 112431/2.V | 12040 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
153 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002238 | 974058.V | 112416/1.V | 12460 | 1 | 5021701 | 26.4.002089 | 800229.V | 112427/1.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
154 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002239 | 974058.V | 112416/2.V | 12470 | 1 | 5021701 | 26.4.002190 | 800223.V | 112454/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
155 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002240 | 974058.V | 113145/2.V | 12450 | 1 | 5021701 | 26.4.002088 | 800229.V | 112426/1.V | 11840 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
156 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002241 | 974058.V | 112415/2.V | 12450 | 1 | 5021701 | 26.4.002087 | 800229.V | 112432/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
157 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002242 | 974058.V | 112418/1.V | 12450 | 1 | 5021701 | 26.4.007852 | 801219.V | 122061/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
158 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002243 | 974058.V | 113145/1.V | 12450 | 1 | 5021701 | 26.4.002186 | 800223.V | 112454/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
159 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002244 | 800222.V | 112450/2.V | 12450 | 1 | 5021701 | 26.4.002086 | 800229.V | 112430/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
160 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002245 | 800222.V | 112452/2.V | 12470 | 1 | 5021701 | 26.4.002085 | 800229.V | 112426/2.V | 12130 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
161 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002246 | 800222.V | 112453/2.V | 12480 | 1 | 5021701 | 26.4.007844 | 975002.V | 121351/1A.V | 12150 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
162 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002247 | 800222.V | 112451/2.V | 12470 | 1 | 5021701 | 26.4.002182 | 800223.V | 112462/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
163 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002248 | 974058.V | 112415/1.V | 12450 | 1 | 5021701 | 26.4.002180 | 800223.V | 112463/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
164 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002249 | 800222.V | 112449/2.V | 12450 | 1 | 5021701 | 26.4.009003 | 801194.V | 121971/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
165 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002250 | 974058.V | 112414/1.V | 12460 | 1 | 5021701 | 26.4.008232 | 975015.V | 121406/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
166 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002251 | 974058.V | 112417/2.V | 12460 | 1 | 5021701 | 26.4.007836 | 975002.V | 121356/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
167 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002252 | 974058.V | 112418/2.V | 12450 | 1 | 5021701 | 26.4.002177 | 974062.V | 112481/2.V | 12440 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
168 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002253 | 974058.V | 112414/2.V | 12450 | 1 | 5021701 | 26.4.002176 | 974062.V | 112478/1.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
169 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002254 | 974058.V | 112413/1.V | 12450 | 1 | 5021701 | 26.4.007832 | 801219.V | 122071/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
170 | 5021701 | 609.600mm / 32.200mm | DNV-ST-F101-2021 x 450 SFDU | 26.4.002169 | 780325.V | 112406/1.V | 12470 | 1 | 5021701 | 26.4.002175 | 974062.V | 112470/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002174 | 974062.V | 112482/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008213 | 801174.V | 120822/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007828 | 975002.V | 121350/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009004 | 801197.V | 121986/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002178 | 800223.V | 112461/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007840 | 975002.V | 121355/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.002181 | 800223.V | 112464/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008286 | 975011.V | 122054/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002183 | 800223.V | 112458/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002184 | 800223.V | 112464/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002185 | 800223.V | 112463/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008302 | 975011.V | 122058/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002187 | 800223.V | 112458/1.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002188 | 800223.V | 112455/2.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002189 | 800223.V | 112456/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007862 | 975002.V | 121355/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002191 | 800223.V | 112462/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002192 | 800223.V | 112455/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002193 | 800223.V | 112457/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008338 | 781068.V | 119544/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002195 | 800223.V | 112457/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002196 | 780325.V | 112402/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002197 | 780325.V | 112400/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007878 | 800943.V | 119469/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002199 | 780325.V | 112398/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002200 | 780325.V | 112410/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002201 | 780325.V | 112409/1.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008369 | 781085.V | 120889/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002203 | 780325.V | 112410/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002204 | 800222.V | 112448/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.002205 | 800222.V | 112449/1.V | 12460 | EC | PU | SEL | SI | SE | U1 | FL | REP | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.007895 | 800943.V | 119471/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002207 | 800222.V | 112452/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.002208 | 800222.V | 112447/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002209 | 800222.V | 112446/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009262 | 781243.V | 120941/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002211 | 800222.V | 112447/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002212 | 974062.V | 112471/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002213 | 974062.V | 112475/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007911 | 800957.V | 119875/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002215 | 974062.V | 112477/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002216 | 974062.V | 112476/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002217 | 974062.V | 112476/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008433 | 800841.V | 118141/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002219 | 974062.V | 112474/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002220 | 974062.V | 112470/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002221 | 974062.V | 112471/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007927 | 800943.V | 119472/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002223 | 974062.V | 112472/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002224 | 974062.V | 112473/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002225 | 974062.V | 112478/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009394 | 801152.V | 120959/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002227 | 974062.V | 112482/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002228 | 974062.V | 112479/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002229 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007943 | 801198.V | 121331/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002231 | 974062.V | 112479/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002232 | 974062.V | 112477/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002233 | 974062.V | 112472/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008497 | 800963.V | 119499/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002235 | 800222.V | 112451/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002236 | 974058.V | 112417/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002237 | 974058.V | 112413/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007960 | 801198.V | 121325/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002240 | 974058.V | 113145/2.V | 12210 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | [7 empty] | DHC
[9 empty] | 5021701 | 26.4.002241 | 974058.V | 112415/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002242 | 974058.V | 112418/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009523 | 781282.V | 121957/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002244 | 800222.V | 112450/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002245 | 800222.V | 112452/2.V | 11810 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002246 | 800222.V | 112453/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007977 | 780993.V | 118565/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002248 | 974058.V | 112415/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002249 | 800222.V | 112449/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002251 | 974058.V | 112417/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008564 | 800983.V | 119977/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002253 | 974058.V | 112414/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002254 | 974058.V | 112413/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007729 | 781283.V | 121411/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007994 | 780992.V | 118291/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007731 | 781283.V | 121419/1.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007732 | 781283.V | 121409/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007734 | 781283.V | 121420/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002173 | 780325.V | 112399/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002172 | 780325.V | 112402/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007824 | 801219.V | 122063/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002171 | 780325.V | 112401/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002169 | 780325.V | 112406/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008934 | 800851.V | 118196/2A.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008168 | 800959.V | 119887/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007820 | 781297.V | 121336/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002168 | 780325.V | 112401/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002167 | 780325.V | 112399/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007816 | 781297.V | 121335/1A.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.002166 | 780325.V | 112400/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002165 | 780325.V | 112408/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008151 | 800959.V | 119876/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007812 | 974992.V | 122000/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002164 | 780325.V | 112408/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002163 | 780325.V | 112404/1.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008879 | 974770.V | 119538/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008144 | 800958.V | 119486/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008138 | 800959.V | 119881/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010170 | 974979.V | 121271/2.V | 12470 | EC
[9 empty] | 5021701 | 26.4.008857 | 974770.V | 119532/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008135 | 800959.V | 119880/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008867 | 781079.V | 119596/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008863 | 781079.V | 119603/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008137 | 800959.V | 119879/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002159 | 780325.V | 112405/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007799 | 781297.V | 121338/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002158 | 780325.V | 112407/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002157 | 780325.V | 112406/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008119 | 781083.V | 120866/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007795 | 781297.V | 121342/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002155 | 780325.V | 112405/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002154 | 780325.V | 112403/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007791 | 974992.V | 122002/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002153 | 800233.V | 112486/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002151 | 800233.V | 112485/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008791 | 780970.V | 118214/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008102 | 800970.V | 119907/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007787 | 781297.V | 121338/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002150 | 800233.V | 112489/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007786 | 781297.V | 121333/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007785 | 781297.V | 121337/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002149 | 800233.V | 112483/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007784 | 781297.V | 121345/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008094 | 781083.V | 120865/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007783 | 781297.V | 121334/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002148 | 800233.V | 112490/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010042 | 801232.V | 122096/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007788 | 781297.V | 121344/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007789 | 781297.V | 121336/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007790 | 781297.V | 121344/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008110 | 800970.V | 119905/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007792 | 974992.V | 122006/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007793 | 974992.V | 122004/1A.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  |  | DHC
[9 empty] | 5021701 | 26.4.007794 | 974992.V | 122003/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008824 | 780970.V | 118215/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007796 | 974992.V | 122003/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007797 | 781297.V | 121345/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007798 | 781297.V | 121341/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008127 | 800959.V | 119878/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007800 | 781297.V | 121340/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007801 | 781297.V | 121339/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007802 | 781297.V | 121346/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010171 | 974649.V | 118159/1A.V | 12460 | EC
[9 empty] | 5021701 | 26.4.007805 | 974992.V | 122005/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008864 | 781079.V | 119605/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008872 | 781079.V | 119601/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007808 | 974992.V | 122001/2.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008878 | 974770.V | 119533/2.V | 11750 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 |  |  |  | DHC
[9 empty] | 5021701 | 26.4.007810 | 974992.V | 122006/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007811 | 974992.V | 122002/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008890 | 780977.V | 118249/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007813 | 974992.V | 121999/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007814 | 974992.V | 122001/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007815 | 781297.V | 121335/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008160 | 800959.V | 119879/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007817 | 781297.V | 121334/1A.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007818 | 781297.V | 121337/1A.V | 12050 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007819 | 781297.V | 121342/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008936 | 800851.V | 118191/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007821 | 781297.V | 121346/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007822 | 975002.V | 121360/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007823 | 801219.V | 122060/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008176 | 800959.V | 119884/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007825 | 801219.V | 122066/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007826 | 801219.V | 122066/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007827 | 975002.V | 121354/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008968 | 780977.V | 118251/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007829 | 975002.V | 121350/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007830 | 975002.V | 121358/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007831 | 975002.V | 121358/2.V | 11860 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008224 | 781062.V | 119462/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007833 | 801219.V | 122069/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007834 | 801219.V | 122073/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007835 | 975002.V | 121347/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008233 | 975015.V | 121400/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007837 | 975002.V | 121356/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007838 | 975002.V | 121360/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.007839 | 975002.V | 121352/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008241 | 975015.V | 121396/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007841 | 975002.V | 121357/1A.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.007842 | 975002.V | 121353/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007843 | 975002.V | 121351/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009035 | 801194.V | 121981/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007845 | 801219.V | 122072/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007846 | 801219.V | 122072/1.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007847 | 801219.V | 122067/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007848 | 801219.V | 122071/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007849 | 801219.V | 122070/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007850 | 801219.V | 122073/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007851 | 801219.V | 122065/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009067 | 781004.V | 118276/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007853 | 801219.V | 122062/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007855 | 801219.V | 122064/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007856 | 801219.V | 122068/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007857 | 801219.V | 122068/1.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007858 | 801219.V | 122069/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007860 | 975002.V | 121353/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007861 | 975002.V | 121348/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008320 | 781052.V | 119837/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007863 | 975002.V | 121352/2.V | 12100 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007864 | 975002.V | 121359/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007865 | 975002.V | 121354/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007866 | 801219.V | 122065/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.007867 | 801219.V | 122064/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007868 | 801219.V | 122067/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007869 | 801219.V | 122061/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009134 | 974750.V | 119526/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007871 | 801219.V | 122070/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007872 | 801219.V | 122063/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007873 | 975002.V | 121359/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007874 | 975002.V | 121349/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007875 | 975002.V | 121349/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007876 | 800957.V | 119868/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007877 | 800957.V | 119873/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008353 | 781085.V | 120892/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007879 | 800943.V | 119476/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007880 | 800957.V | 119869/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007881 | 800943.V | 119477/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007882 | 800943.V | 119471/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007883 | 800957.V | 119862/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007884 | 800943.V | 119475/1.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007885 | 800943.V | 119474/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009196 | 781267.V | 120806/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007888 | 800957.V | 119866/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.007889 | 800957.V | 119871/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007890 | 800943.V | 119464/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007891 | 800957.V | 119867/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007892 | 800957.V | 119870/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007893 | 800957.V | 119869/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007894 | 800957.V | 119872/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008385 | 781090.V | 120689/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007896 | 800943.V | 119466/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007897 | 800943.V | 119470/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007898 | 800943.V | 119470/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007899 | 800957.V | 119866/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007900 | 800943.V | 119465/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007901 | 800943.V | 119465/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007902 | 800957.V | 119871/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009263 | 781242.V | 120735/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007904 | 800943.V | 119464/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007905 | 800957.V | 119873/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007906 | 800943.V | 119473/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007907 | 800957.V | 119863/1A.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007908 | 800943.V | 119468/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007909 | 800943.V | 119474/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007910 | 800943.V | 119467/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008417 | 781086.V | 120906/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007912 | 800957.V | 119865/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007913 | 800957.V | 119874/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.007914 | 800957.V | 119875/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007915 | 800957.V | 119865/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007916 | 800957.V | 119868/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007917 | 800943.V | 119476/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007918 | 800943.V | 119477/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009326 | 781251.V | 120774/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007920 | 800943.V | 119468/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007921 | 800943.V | 119466/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007922 | 800957.V | 119874/1A.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007923 | 800943.V | 119469/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007924 | 800957.V | 119863/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007925 | 800957.V | 119872/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007926 | 800943.V | 119467/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008449 | 800848.V | 118431/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007928 | 800957.V | 119864/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007929 | 800943.V | 119475/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007930 | 800943.V | 119472/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007931 | 801198.V | 121322/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007932 | 801198.V | 121324/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007933 | 801198.V | 121319/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007934 | 801198.V | 121319/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008466 | 800841.V | 118136/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007936 | 801198.V | 121327/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007937 | 801198.V | 121322/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007938 | 801198.V | 121328/1A.V | 11890 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007939 | 801198.V | 121328/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007940 | 801198.V | 121329/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007941 | 801198.V | 121323/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007942 | 801198.V | 121320/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008481 | 800964.V | 119895/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007944 | 801198.V | 121320/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007945 | 801198.V | 121323/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007946 | 801198.V | 121329/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007947 | 801198.V | 121332/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007948 | 801198.V | 121327/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007949 | 801198.V | 121326/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007950 | 801198.V | 121331/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009457 | 800942.V | 119853/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007953 | 780993.V | 118572/1.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007954 | 780993.V | 118569/2.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007955 | 780993.V | 118570/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.007956 | 780993.V | 118562/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007957 | 801198.V | 121321/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007958 | 801198.V | 121321/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007959 | 801198.V | 121325/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008514 | 800964.V | 119901/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007961 | 780993.V | 118572/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007962 | 780993.V | 118564/2.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007963 | 780993.V | 118568/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007964 | 780993.V | 118574/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007965 | 780993.V | 118573/1.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007966 | 780993.V | 118570/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007967 | 780993.V | 118562/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009524 | 781282.V | 121960/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.007969 | 780993.V | 118564/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007970 | 801198.V | 121324/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007971 | 801198.V | 121326/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007972 | 780993.V | 118563/2.V | 12470 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.007973 | 780993.V | 118563/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007974 | 780993.V | 118566/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007975 | 780993.V | 118567/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008547 | 800983.V | 119972/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007978 | 780993.V | 118566/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007979 | 780993.V | 118567/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007980 | 780993.V | 118571/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007981 | 780993.V | 118573/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007982 | 780993.V | 118568/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007983 | 780993.V | 118571/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007984 | 780993.V | 118561/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009589 | 781278.V | 121947/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007986 | 780993.V | 118574/2.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.007987 | 780995.V | 118301/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007988 | 780995.V | 118309/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007989 | 780995.V | 118309/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007990 | 780992.V | 118290/2.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007991 | 780995.V | 118307/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007992 | 780992.V | 118295/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008581 | 800977.V | 119576/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.007995 | 780992.V | 118294/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007996 | 780992.V | 118294/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007997 | 780992.V | 118298/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007998 | 780992.V | 118288/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007999 | 780995.V | 118308/1.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008000 | 780992.V | 118288/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008001 | 780995.V | 118313/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007782 | 781297.V | 121339/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007781 | 781297.V | 121333/2.V | 11870 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002146 | 800233.V | 112484/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007780 | 801208.V | 122024/1A.V | 12050 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008759 | 781329.V | 122118/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008086 | 780991.V | 118558/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007779 | 801208.V | 122024/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002145 | 800233.V | 112486/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007778 | 801208.V | 122019/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007777 | 801208.V | 122031/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002144 | 800233.V | 112484/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007776 | 801208.V | 122020/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008078 | 800965.V | 119515/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007775 | 801208.V | 122020/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002143 | 800232.V | 112442/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007774 | 781283.V | 121410/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007772 | 801208.V | 122029/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002142 | 800232.V | 112443/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007771 | 801208.V | 122029/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009915 | 780996.V | 118575/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009914 | 781001.V | 118173/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008727 | 800840.V | 118407/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008070 | 800965.V | 119516/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007770 | 781283.V | 121408/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002141 | 800232.V | 112438/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007769 | 781283.V | 121414/1.V | 12010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007768 | 801208.V | 122030/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002140 | 800232.V | 112439/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007767 | 781283.V | 121409/1.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008062 | 800965.V | 119510/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007765 | 781283.V | 121413/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002139 | 800232.V | 112435/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007763 | 781283.V | 121411/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007762 | 781283.V | 121410/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002138 | 800232.V | 112440/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007761 | 781283.V | 121414/2.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008694 | 780939.V | 118439/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008054 | 800965.V | 119509/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007760 | 781283.V | 121419/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002137 | 800232.V | 112445/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008053 | 780991.V | 118556/2.V | 11800 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008052 | 800965.V | 119505/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007759 | 781283.V | 121408/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008051 | 780991.V | 118554/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008050 | 800965.V | 119504/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007758 | 801208.V | 122021/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002136 | 800232.V | 112435/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008049 | 780991.V | 118560/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009849 | 780943.V | 118464/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008055 | 800965.V | 119509/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008056 | 800965.V | 119514/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008057 | 800965.V | 119510/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008058 | 800965.V | 119516/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008059 | 800965.V | 119514/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008060 | 800965.V | 119508/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008061 | 780991.V | 118555/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008711 | 800840.V | 118419/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008063 | 800965.V | 119507/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008064 | 780991.V | 118556/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008065 | 800965.V | 119504/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008066 | 780991.V | 118555/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008067 | 780991.V | 118553/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008068 | 780991.V | 118553/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008069 | 800965.V | 119505/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008728 | 800840.V | 118418/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008071 | 800965.V | 119513/2.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008072 | 800965.V | 119513/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008073 | 800965.V | 119512/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008074 | 800965.V | 119511/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008075 | 800965.V | 119506/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008076 | 800965.V | 119511/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008077 | 800965.V | 119507/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008743 | 781329.V | 122113/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008079 | 780991.V | 118551/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008080 | 780991.V | 118557/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008081 | 975002.V | 121348/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008082 | 800965.V | 119503/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008083 | 800965.V | 119515/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008084 | 780991.V | 118551/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008085 | 780991.V | 118552/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009978 | 801231.V | 122087/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008087 | 780991.V | 118552/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008088 | 780991.V | 118560/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008089 | 780991.V | 118558/1.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008090 | 780991.V | 118557/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008091 | 780991.V | 118559/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008092 | 780991.V | 118550/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008093 | 781083.V | 120867/2.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008775 | 781329.V | 122117/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008095 | 781083.V | 120869/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008096 | 781083.V | 120869/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008097 | 781083.V | 120867/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008098 | 781083.V | 120868/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008099 | 800970.V | 119905/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008100 | 781083.V | 120868/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008101 | 800970.V | 119907/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010043 | 801232.V | 122106/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008103 | 781083.V | 120864/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008104 | 781083.V | 120870/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008105 | 800970.V | 119906/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008106 | 800970.V | 119910/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008107 | 800970.V | 119910/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008108 | 800970.V | 119911/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008109 | 800970.V | 119908/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008807 | 780970.V | 118223/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008111 | 800970.V | 119904/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008112 | 800970.V | 119909/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008114 | 800970.V | 119904/2.V | 11750 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008115 | 781083.V | 120870/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008116 | 781083.V | 120864/1A.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008117 | 781083.V | 120865/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008118 | 781083.V | 120866/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.010106 | 974649.V | 118154/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008120 | 781083.V | 120871/1A.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008121 | 800970.V | 119906/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008122 | 781083.V | 120871/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008123 | 800970.V | 119908/1A.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008124 | 800970.V | 119909/1A.V | 12200 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008125 | 800958.V | 119482/1.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008126 | 800958.V | 119485/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008840 | 800907.V | 118272/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008128 | 800958.V | 119481/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008129 | 800958.V | 119479/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008130 | 800958.V | 119479/1.V | 11770 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008131 | 800958.V | 119489/1.V | 12390 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008132 | 800958.V | 119488/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008133 | 800959.V | 119880/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008134 | 800958.V | 119491/2.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008858 | 781079.V | 119603/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002160 | 780325.V | 112397/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007804 | 974992.V | 122005/1A.V | 11790 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008140 | 800958.V | 119486/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008865 | 781079.V | 119593/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008048 | 780991.V | 118559/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002161 | 780325.V | 112404/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008871 | 781079.V | 119602/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008873 | 781079.V | 119606/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008880 | 974770.V | 119531/1.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | [7 empty] | DHC
[9 empty] | 5021701 | 26.4.002162 | 800233.V | 112488/1.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007809 | 974992.V | 122004/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008147 | 800959.V | 119886/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008148 | 800959.V | 119888/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008149 | 800958.V | 119490/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008150 | 800958.V | 119491/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008891 | 974770.V | 119537/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008153 | 800958.V | 119490/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008154 | 800959.V | 119885/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008155 | 800959.V | 119878/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008156 | 800959.V | 119886/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008157 | 800958.V | 119487/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008158 | 800959.V | 119888/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008159 | 800958.V | 119487/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008918 | 974777.V | 119930/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008161 | 800958.V | 119485/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008162 | 800958.V | 119478/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008163 | 800958.V | 119481/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008164 | 800958.V | 119483/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008165 | 800959.V | 119889/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008166 | 800959.V | 119889/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008167 | 800959.V | 119887/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007757 | 801208.V | 122018/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008169 | 800959.V | 119877/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008170 | 800959.V | 119877/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008171 | 800959.V | 119882/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008172 | 800959.V | 119883/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008173 | 800958.V | 119478/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008174 | 800959.V | 119885/1A.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008175 | 800959.V | 119882/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008952 | 974720.V | 120851/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008177 | 800958.V | 119488/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008178 | 800958.V | 119480/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008179 | 800959.V | 119883/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008180 | 800958.V | 119480/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008204 | 801174.V | 120822/2.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008211 | 801174.V | 120823/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008212 | 801169.V | 120791/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008970 | 780977.V | 118250/1A.V | 12460 | EC | PU | SEL | SI | SE |  |  | REP
[9 empty] | 5021701 | 26.4.008214 | 801174.V | 120812/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008216 | 801174.V | 120817/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008219 | 801174.V | 120816/2.V | 11770 | EC | PU | SEL | SI | SE | U1 |  | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008220 | 801169.V | 120792/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008221 | 781062.V | 119462/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008222 | 781062.V | 119461/1.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008223 | 781062.V | 119458/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008985 | 780932.V | 118402/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008225 | 781062.V | 119451/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008226 | 781062.V | 119451/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008227 | 975015.V | 121401/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008228 | 975015.V | 121406/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008229 | 975015.V | 121402/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008230 | 975015.V | 121402/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008231 | 975015.V | 121393/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008047 | 780991.V | 118550/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009005 | 801197.V | 121991/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008234 | 975015.V | 121400/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008235 | 975015.V | 121404/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008236 | 781062.V | 119458/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008238 | 975015.V | 121401/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008239 | 975015.V | 121394/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008240 | 975015.V | 121404/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009019 | 801197.V | 121985/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008242 | 975015.V | 121403/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008277 | 781052.V | 119846/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008278 | 781052.V | 119842/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008280 | 781052.V | 119842/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008281 | 975011.V | 122052/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008282 | 975011.V | 122050/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008284 | 975011.V | 122054/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009036 | 801197.V | 121988/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008287 | 781052.V | 119843/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008288 | 781052.V | 119843/1A.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008289 | 781052.V | 119838/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008290 | 781052.V | 119839/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008291 | 781052.V | 119835/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008292 | 781052.V | 119840/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008293 | 781052.V | 119837/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008294 | 781052.V | 119836/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008295 | 781052.V | 119838/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008296 | 975011.V | 122057/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008297 | 975011.V | 122056/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008298 | 975011.V | 122046/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008299 | 975011.V | 122046/2.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008300 | 975011.V | 122055/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008301 | 975011.V | 122049/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009068 | 781034.V | 119441/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008303 | 975011.V | 122053/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008304 | 975011.V | 122058/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008305 | 975011.V | 122059/1A.V | 11820 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008308 | 975011.V | 122051/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008309 | 975011.V | 122047/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008310 | 975011.V | 122052/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008311 | 975011.V | 122048/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008312 | 975011.V | 122048/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008313 | 975011.V | 122056/1A.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008314 | 975011.V | 122053/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008315 | 975011.V | 122059/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008316 | 781052.V | 119839/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008317 | 781052.V | 119846/1A.V | 11700 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008318 | 781052.V | 119841/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008319 | 781052.V | 119845/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009100 | 974765.V | 119920/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008321 | 781052.V | 119835/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008322 | 781052.V | 119834/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008323 | 781052.V | 119847/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008324 | 781052.V | 119834/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008325 | 781052.V | 119845/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008326 | 781052.V | 119847/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008328 | 975011.V | 122049/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008329 | 781052.V | 119841/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008330 | 781052.V | 119840/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008331 | 781052.V | 119844/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008332 | 781052.V | 119844/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008333 | 781068.V | 119540/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008334 | 781068.V | 119546/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008335 | 781068.V | 119539/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008336 | 781068.V | 119539/1.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008677 | 780939.V | 118444/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009135 | 974750.V | 119524/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008339 | 781085.V | 120888/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008340 | 781085.V | 120895/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008341 | 781085.V | 120891/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008342 | 781085.V | 120894/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008343 | 781085.V | 120888/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008344 | 781085.V | 120891/1.V | 12450 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008345 | 781085.V | 120889/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008346 | 781085.V | 120887/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008347 | 781085.V | 120894/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008348 | 781085.V | 120890/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008349 | 781085.V | 120896/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008350 | 781085.V | 120896/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008351 | 781085.V | 120887/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008352 | 781085.V | 120892/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009164 | 781254.V | 120779/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008354 | 781085.V | 120893/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008355 | 781085.V | 120893/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008356 | 781068.V | 119547/1.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008357 | 781068.V | 119549/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008358 | 781085.V | 120886/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008359 | 781085.V | 120890/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008360 | 781068.V | 119545/1.V | 12200 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008361 | 781085.V | 120886/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008362 | 781068.V | 119546/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008363 | 781068.V | 119547/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008364 | 781068.V | 119545/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008365 | 781068.V | 119541/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008366 | 781068.V | 119548/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008367 | 781068.V | 119542/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008368 | 781068.V | 119548/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009197 | 781267.V | 120800/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008370 | 781068.V | 119541/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008371 | 781068.V | 119542/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008372 | 781068.V | 119543/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008373 | 781068.V | 119549/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008374 | 781068.V | 119543/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008375 | 781068.V | 119544/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008376 | 781086.V | 120904/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008377 | 781086.V | 120901/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008378 | 781086.V | 120908/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008379 | 781090.V | 120684/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008380 | 781090.V | 120689/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008381 | 781090.V | 120678/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008382 | 781086.V | 120910/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008383 | 781090.V | 120678/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008384 | 781086.V | 120902/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009229 | 781040.V | 119449/2.V | 11840 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008386 | 781086.V | 120897/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008387 | 781086.V | 120910/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008388 | 781090.V | 120685/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008389 | 781090.V | 120677/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008390 | 781090.V | 120681/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008391 | 781090.V | 120687/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008392 | 781090.V | 120676/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008393 | 781090.V | 120685/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008394 | 781086.V | 120904/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008395 | 781090.V | 120676/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008396 | 781090.V | 120683/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008397 | 781090.V | 120679/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008398 | 781086.V | 120909/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008399 | 781086.V | 120907/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008400 | 781086.V | 120903/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008046 | 780991.V | 118554/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008402 | 781086.V | 120900/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008403 | 781086.V | 120909/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008404 | 781086.V | 120900/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008405 | 781086.V | 120908/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008406 | 781086.V | 120905/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008407 | 781086.V | 120898/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008408 | 781090.V | 120681/2.V | 12110 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008409 | 781086.V | 120906/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008410 | 781090.V | 120680/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008411 | 781090.V | 120688/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008412 | 781090.V | 120687/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008413 | 781090.V | 120680/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008414 | 781090.V | 120679/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008415 | 781090.V | 120682/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008416 | 781090.V | 120677/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009294 | 974803.V | 120675/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008418 | 781090.V | 120683/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008419 | 781090.V | 120682/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008420 | 781090.V | 120686/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008421 | 781090.V | 120684/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008422 | 781090.V | 120688/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008423 | 781086.V | 120898/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008424 | 781086.V | 120897/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008425 | 781086.V | 120899/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008426 | 781086.V | 120905/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008427 | 781086.V | 120899/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008428 | 781090.V | 120686/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008429 | 781086.V | 120903/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008430 | 800841.V | 118134/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008431 | 800841.V | 118136/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008432 | 800841.V | 118140/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009327 | 781250.V | 120965/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008434 | 800841.V | 118139/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008435 | 800841.V | 118134/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008436 | 800841.V | 118145/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008437 | 800841.V | 118145/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008438 | 800848.V | 118430/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008439 | 800841.V | 118139/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008440 | 800848.V | 118429/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008441 | 800848.V | 118433/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008442 | 800848.V | 118423/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008443 | 800848.V | 118425/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008444 | 800848.V | 118426/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008445 | 800848.V | 118424/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008446 | 800841.V | 118147/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008447 | 800841.V | 118137/2A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008448 | 800848.V | 118425/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009359 | 780979.V | 118319/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008450 | 800848.V | 118422/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008451 | 800848.V | 118422/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008452 | 800841.V | 118143/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008453 | 800841.V | 118144/2A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH
[9 empty] | 5021701 | 26.4.008454 | 800841.V | 118147/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008455 | 800848.V | 118430/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008456 | 800841.V | 118138/2A.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008457 | 800841.V | 118141/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008458 | 800848.V | 118426/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008459 | 800841.V | 118146/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008460 | 800841.V | 118140/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008461 | 800848.V | 118428/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008462 | 800841.V | 118143/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008463 | 800848.V | 118432/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008464 | 800848.V | 118432/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007756 | 781283.V | 121412/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009395 | 801152.V | 120954/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008467 | 800848.V | 118420/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008468 | 800841.V | 118142/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008469 | 800848.V | 118420/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008470 | 800848.V | 118421/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008471 | 800848.V | 118423/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008472 | 800848.V | 118429/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008473 | 800848.V | 118424/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008474 | 800848.V | 118428/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008475 | 800841.V | 118142/1A.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008476 | 800841.V | 118135/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008477 | 800841.V | 118146/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008478 | 800963.V | 119500/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008479 | 800964.V | 119897/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008480 | 800964.V | 119893/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009425 | 801152.V | 120952/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008482 | 800963.V | 119496/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008483 | 800963.V | 119499/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008484 | 800964.V | 119892/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008485 | 800964.V | 119890/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008486 | 800964.V | 119890/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008487 | 800964.V | 119894/1A.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008488 | 800964.V | 119894/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008489 | 800963.V | 119497/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008490 | 800963.V | 119493/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008491 | 800963.V | 119497/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008492 | 800963.V | 119500/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008493 | 800964.V | 119895/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008494 | 800964.V | 119902/1A.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008495 | 800963.V | 119496/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008496 | 800963.V | 119502/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009458 | 800942.V | 119855/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008498 | 800964.V | 119896/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008499 | 800964.V | 119898/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008500 | 800964.V | 119900/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008501 | 800963.V | 119495/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008502 | 800964.V | 119903/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008503 | 800963.V | 119495/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008504 | 800964.V | 119899/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008505 | 800963.V | 119493/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008506 | 800963.V | 119498/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008508 | 800963.V | 119494/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008509 | 800964.V | 119898/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008510 | 800963.V | 119492/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008511 | 800963.V | 119498/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008512 | 800963.V | 119492/2.V | 12090 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.008513 | 800964.V | 119901/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009491 | 974783.V | 119953/2.V | 12440 | EC | PU | SEL | SI | SE | U1 | FL | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008515 | 800963.V | 119501/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008516 | 800964.V | 119891/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008517 | 800964.V | 119896/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008518 | 800964.V | 119891/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008519 | 800964.V | 119899/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008520 | 800963.V | 119501/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008521 | 800964.V | 119903/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008522 | 800964.V | 119893/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008523 | 800964.V | 119900/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008524 | 800963.V | 119502/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008525 | 800964.V | 119902/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008526 | 800964.V | 119897/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008527 | 800964.V | 119892/1A.V | 12120 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008528 | 800983.V | 119968/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008529 | 800995.V | 120692/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.002135 | 800232.V | 112445/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008531 | 800995.V | 120703/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008532 | 800995.V | 120702/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008533 | 800995.V | 120701/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008534 | 800995.V | 120698/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008535 | 800995.V | 120691/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008536 | 800983.V | 119973/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008537 | 800995.V | 120690/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008538 | 800995.V | 120697/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008539 | 800995.V | 120701/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008541 | 800983.V | 119971/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008542 | 800995.V | 120692/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008543 | 800995.V | 120690/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008544 | 800983.V | 119974/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008545 | 800983.V | 119970/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008546 | 800995.V | 120697/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009556 | 781268.V | 121011/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008549 | 800995.V | 120694/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008550 | 800995.V | 120699/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008551 | 800995.V | 120696/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008552 | 800995.V | 120698/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008553 | 800995.V | 120703/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008554 | 800995.V | 120700/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008555 | 800995.V | 120695/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008556 | 800983.V | 119967/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008557 | 800995.V | 120700/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008558 | 800995.V | 120691/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008559 | 800995.V | 120695/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008560 | 800983.V | 119969/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008561 | 800983.V | 119967/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008562 | 800983.V | 119969/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008563 | 800995.V | 120696/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009590 | 781278.V | 121952/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008565 | 800995.V | 120702/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008566 | 800983.V | 119977/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008567 | 800995.V | 120699/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008568 | 800983.V | 119974/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008569 | 800983.V | 119972/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008570 | 800983.V | 119975/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008571 | 800983.V | 119976/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008572 | 800983.V | 119975/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008573 | 800995.V | 120693/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008574 | 800983.V | 119970/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008575 | 800977.V | 119579/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008577 | 800977.V | 119575/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008578 | 800977.V | 119576/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008579 | 800977.V | 119570/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008580 | 800977.V | 119581/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009622 | 781242.V | 120743/1A.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008582 | 800977.V | 119569/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008583 | 800977.V | 119577/1A.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008584 | 800977.V | 119569/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008585 | 800977.V | 119571/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008586 | 800977.V | 119580/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008587 | 800848.V | 118433/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008588 | 800976.V | 119556/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008589 | 800976.V | 119559/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008590 | 800976.V | 119553/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008591 | 800976.V | 119562/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008592 | 800976.V | 119563/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008593 | 800976.V | 119553/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008594 | 800976.V | 119555/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008595 | 800976.V | 119554/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008596 | 800976.V | 119560/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008045 | 800965.V | 119512/2.V | 12070 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008042 | 800965.V | 119506/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007755 | 801208.V | 122019/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008041 | 780992.V | 118289/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008040 | 780992.V | 118300/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007754 | 801208.V | 122022/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002134 | 800232.V | 112443/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008039 | 780992.V | 118299/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008038 | 780995.V | 118302/1.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007753 | 801208.V | 122023/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008037 | 780995.V | 118305/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009786 | 800980.V | 119582/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009785 | 800979.V | 119958/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008661 | 781241.V | 120927/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008036 | 780995.V | 118311/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007752 | 801208.V | 122023/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002133 | 800232.V | 112441/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008035 | 780995.V | 118314/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008034 | 780995.V | 118312/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007751 | 801208.V | 122031/1A.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.008033 | 780995.V | 118304/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008031 | 780995.V | 118310/1.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007750 | 801208.V | 122030/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002132 | 800232.V | 112440/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008030 | 780995.V | 118303/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008029 | 780995.V | 118307/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007749 | 801208.V | 122027/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008028 | 780992.V | 118300/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008645 | 781241.V | 120935/1.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008027 | 780995.V | 118303/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007748 | 781283.V | 121418/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002131 | 800232.V | 112438/1.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008026 | 780992.V | 118296/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008025 | 780992.V | 118296/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007747 | 781283.V | 121407/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008640 | 781241.V | 120937/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008639 | 781237.V | 120711/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008024 | 780995.V | 118306/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008638 | 781237.V | 120710/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008637 | 781237.V | 120710/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008023 | 780992.V | 118298/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007746 | 781283.V | 121407/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002130 | 800232.V | 112444/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008636 | 781237.V | 120720/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008641 | 781241.V | 120935/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008642 | 781241.V | 120931/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008643 | 781241.V | 120925/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008644 | 781241.V | 120933/1.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009752 | 974686.V | 118496/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008646 | 781241.V | 120933/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008647 | 781241.V | 120937/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008648 | 781237.V | 120718/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008649 | 781241.V | 120928/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008650 | 781241.V | 120926/2.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008651 | 781237.V | 120713/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008652 | 781241.V | 120926/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008653 | 781237.V | 120715/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008654 | 781237.V | 120716/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008655 | 781241.V | 120930/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008656 | 781241.V | 120927/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008657 | 781237.V | 120717/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008658 | 781241.V | 120929/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008659 | 781237.V | 120712/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008660 | 781237.V | 120720/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008635 | 781237.V | 120711/1.V | 12050 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008662 | 781241.V | 120931/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008663 | 781237.V | 120713/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008664 | 781241.V | 120932/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008665 | 781241.V | 120934/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008666 | 781237.V | 120714/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008667 | 781237.V | 120719/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008668 | 780939.V | 118435/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008669 | 780932.V | 118402/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008670 | 780932.V | 118405/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008671 | 780939.V | 118439/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008672 | 780932.V | 118401/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008673 | 780932.V | 118401/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008674 | 780932.V | 118396/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008675 | 780939.V | 118435/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008676 | 780939.V | 118444/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009817 | 781080.V | 119988/1.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008678 | 780932.V | 118399/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008679 | 780932.V | 118400/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008680 | 780939.V | 118440/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008681 | 780939.V | 118443/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008682 | 780932.V | 118400/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008683 | 780932.V | 118405/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008684 | 780932.V | 118399/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008685 | 780939.V | 118437/1.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008686 | 780932.V | 118404/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008687 | 780932.V | 118403/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008689 | 780939.V | 118442/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008690 | 780939.V | 118442/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008691 | 780932.V | 118403/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008692 | 780932.V | 118404/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008693 | 780932.V | 118397/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009850 | 780943.V | 118463/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008695 | 780939.V | 118438/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008696 | 780939.V | 118443/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008697 | 780932.V | 118396/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008698 | 780939.V | 118441/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008699 | 780939.V | 118436/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008700 | 780932.V | 118398/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008701 | 780939.V | 118441/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008702 | 780932.V | 118397/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008703 | 780932.V | 118398/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008704 | 780939.V | 118436/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008705 | 780939.V | 118437/2.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008707 | 800840.V | 118407/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008708 | 800840.V | 118417/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008709 | 800840.V | 118411/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008710 | 800840.V | 118416/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009882 | 780942.V | 118458/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008712 | 800840.V | 118415/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008713 | 800840.V | 118415/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008714 | 800840.V | 118406/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008715 | 800840.V | 118414/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008716 | 800840.V | 118416/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008717 | 800840.V | 118410/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008718 | 800840.V | 118411/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008719 | 800840.V | 118409/2.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008720 | 800840.V | 118413/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008721 | 800840.V | 118406/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008722 | 800840.V | 118410/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008723 | 800840.V | 118419/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008724 | 800840.V | 118412/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008725 | 800840.V | 118417/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008726 | 800840.V | 118418/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008022 | 780995.V | 118312/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009916 | 780996.V | 118582/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008729 | 800840.V | 118408/1.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008730 | 800840.V | 118408/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008731 | 800840.V | 118409/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008732 | 800840.V | 118412/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008733 | 800840.V | 118413/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008734 | 800840.V | 118414/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008735 | 800977.V | 119572/2.V | 12290 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008736 | 781329.V | 122109/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008737 | 781329.V | 122109/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008738 | 780973.V | 118227/2A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008739 | 780973.V | 118226/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008740 | 781329.V | 122121/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008741 | 781329.V | 122110/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008742 | 781329.V | 122122/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009946 | 780996.V | 118583/1.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008744 | 780973.V | 118232/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008745 | 780973.V | 118234/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008746 | 780973.V | 118239/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008747 | 780973.V | 118235/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008748 | 780973.V | 118230/2A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008749 | 780973.V | 118238/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008750 | 781329.V | 122119/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008751 | 780973.V | 118233/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008752 | 780973.V | 118231/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008753 | 780973.V | 118236/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008754 | 781329.V | 122120/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008755 | 781329.V | 122120/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008756 | 781329.V | 122111/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008757 | 781329.V | 122111/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008758 | 781329.V | 122122/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009979 | 801231.V | 122084/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008760 | 781329.V | 122112/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008761 | 781329.V | 122117/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008762 | 781329.V | 122119/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008763 | 781329.V | 122112/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008764 | 780973.V | 118238/1A.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008765 | 781329.V | 122116/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008766 | 780973.V | 118237/1A.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.008767 | 781329.V | 122113/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008768 | 781329.V | 122121/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008769 | 781329.V | 122116/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008770 | 781329.V | 122118/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008771 | 780973.V | 118228/1A.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008772 | 781329.V | 122114/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008773 | 781329.V | 122115/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008774 | 781329.V | 122114/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010010 | 974719.V | 118200/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008776 | 780973.V | 118234/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008777 | 780973.V | 118233/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008778 | 780973.V | 118228/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008779 | 780973.V | 118232/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008780 | 780973.V | 118237/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008781 | 780973.V | 118239/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008782 | 780973.V | 118231/2A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008783 | 780973.V | 118230/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008784 | 780973.V | 118236/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008785 | 781329.V | 122115/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008786 | 781329.V | 122110/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008787 | 780973.V | 118229/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008788 | 780973.V | 118229/2A.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008789 | 780973.V | 118227/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008790 | 780973.V | 118226/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008634 | 781241.V | 120929/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008792 | 780970.V | 118213/1.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008793 | 780970.V | 118213/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008794 | 780970.V | 118214/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008795 | 780970.V | 118216/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008796 | 780970.V | 118212/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008797 | 780970.V | 118215/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008798 | 780970.V | 118212/2A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008799 | 780970.V | 118225/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008800 | 800907.V | 118269/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 | FL | REP |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008801 | 780970.V | 118222/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008802 | 780970.V | 118222/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008803 | 780970.V | 118220/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008804 | 780970.V | 118221/2A.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008805 | 780970.V | 118219/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008806 | 780970.V | 118221/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010074 | 801237.V | 121438/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008808 | 780970.V | 118224/2A.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008809 | 780970.V | 118225/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008810 | 800907.V | 118267/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008811 | 800907.V | 118268/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008812 | 800907.V | 118268/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008813 | 800907.V | 118272/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008814 | 800907.V | 118258/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008815 | 800907.V | 118266/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008816 | 800907.V | 118267/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008817 | 800907.V | 118269/2A.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008818 | 800907.V | 118270/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008819 | 800907.V | 118270/1A.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008821 | 800907.V | 118263/1.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008822 | 780970.V | 118217/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008823 | 780970.V | 118216/2A.V | 12480 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.010107 | 974649.V | 118161/2A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008825 | 780970.V | 118220/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008826 | 780970.V | 118217/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008827 | 780970.V | 118218/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008828 | 780970.V | 118219/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008829 | 800907.V | 118261/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008830 | 780970.V | 118218/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008831 | 800907.V | 118261/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008832 | 800907.V | 118262/1.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008833 | 800907.V | 118264/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008834 | 800907.V | 118260/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008835 | 800907.V | 118260/2A.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008836 | 780970.V | 118224/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008837 | 800907.V | 118262/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008838 | 800907.V | 118259/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008839 | 800907.V | 118259/2A.V | 11850 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010138 | 974979.V | 121279/1.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008841 | 800907.V | 118271/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008842 | 800907.V | 118271/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008843 | 800907.V | 118258/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008844 | 800907.V | 118264/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008845 | 800907.V | 118263/2.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008846 | 780977.V | 118254/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008847 | 780977.V | 118249/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008849 | 780977.V | 118256/2A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008850 | 780977.V | 118248/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008851 | 780977.V | 118253/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008852 | 780977.V | 118257/2A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008853 | 780977.V | 118257/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008854 | 780977.V | 118252/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008855 | 780977.V | 118255/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 | FL | REP
[9 empty] | 5021701 | 26.4.008856 | 974770.V | 119538/1.V | 11710 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008633 | 781237.V | 120715/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010172 | 974649.V | 118149/2A.V | 12460 | EC
[9 empty] | 5021701 | 26.4.008859 | 781079.V | 119599/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007803 | 781297.V | 121340/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008861 | 781079.V | 119605/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008862 | 781079.V | 119598/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008141 | 800958.V | 119484/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008868 | 781079.V | 119599/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008139 | 800959.V | 119881/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008866 | 781079.V | 119596/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008021 | 780995.V | 118305/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007745 | 801208.V | 122022/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008869 | 781079.V | 119604/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008870 | 781079.V | 119606/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007806 | 974992.V | 121999/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008142 | 800958.V | 119484/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008143 | 800958.V | 119483/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008874 | 781079.V | 119600/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008875 | 781079.V | 119600/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008876 | 781079.V | 119593/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008632 | 781237.V | 120717/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008145 | 800958.V | 119489/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008146 | 800958.V | 119482/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008881 | 974770.V | 119531/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008882 | 974770.V | 119534/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008883 | 974770.V | 119534/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008884 | 974770.V | 119535/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008885 | 974770.V | 119537/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008886 | 974770.V | 119535/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008887 | 780977.V | 118248/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008888 | 974770.V | 119532/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008889 | 974770.V | 119536/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008631 | 781237.V | 120716/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008020 | 780992.V | 118297/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008892 | 974770.V | 119536/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008903 | 800851.V | 118194/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008904 | 974720.V | 118503/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008905 | 974777.V | 119927/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008907 | 974777.V | 119934/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008908 | 974777.V | 119926/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008910 | 974777.V | 119929/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008911 | 974777.V | 119937/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008912 | 974777.V | 119931/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008913 | 974777.V | 119932/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008914 | 974777.V | 119926/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008915 | 974777.V | 119939/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008916 | 974777.V | 119938/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008917 | 781079.V | 119595/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008630 | 781237.V | 120719/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008919 | 974777.V | 119930/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008920 | 974777.V | 119935/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008921 | 781079.V | 119597/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008922 | 974777.V | 119933/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008923 | 781079.V | 119594/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008924 | 974777.V | 119936/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008925 | 974777.V | 119929/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008926 | 974777.V | 119927/2.V | 11790 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008927 | 974777.V | 119935/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008928 | 781079.V | 119602/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008929 | 781079.V | 119594/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008930 | 781079.V | 119595/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008931 | 974720.V | 118502/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008932 | 800851.V | 118196/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008933 | 974720.V | 118501/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009721 | 801144.V | 120727/1A.V | 12080 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009720 | 801144.V | 120730/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008937 | 800851.V | 118185/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008938 | 800851.V | 118190/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008939 | 800851.V | 118193/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008940 | 800851.V | 118194/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008941 | 800851.V | 118190/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008942 | 800851.V | 118184/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008943 | 800851.V | 118195/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008945 | 800851.V | 118197/2A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008946 | 974720.V | 118498/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008947 | 974720.V | 118504/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008948 | 800851.V | 118184/2A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008949 | 800851.V | 118189/2A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008950 | 974720.V | 118500/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008951 | 974720.V | 118502/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008629 | 781241.V | 120936/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008953 | 974720.V | 118500/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008954 | 800851.V | 118185/2A.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.008955 | 974720.V | 120851/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008956 | 800851.V | 118189/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008957 | 800851.V | 118186/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008958 | 800851.V | 118195/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008959 | 800851.V | 118188/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008960 | 800851.V | 118192/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008961 | 800851.V | 118192/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008962 | 800851.V | 118197/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008963 | 800851.V | 118191/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008964 | 800851.V | 118193/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008965 | 800851.V | 118186/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008966 | 781079.V | 119604/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008967 | 974777.V | 119939/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008019 | 780995.V | 118310/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007744 | 801208.V | 122025/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008971 | 800976.V | 119550/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008972 | 800977.V | 119571/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008973 | 800976.V | 119555/2.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008974 | 800976.V | 119550/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008975 | 800976.V | 119551/2.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008976 | 800977.V | 119573/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008977 | 800983.V | 119976/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008978 | 800977.V | 119578/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008979 | 800977.V | 119568/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008980 | 800977.V | 119574/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008981 | 780932.V | 118395/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008982 | 800977.V | 119579/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008983 | 780932.V | 118395/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008984 | 781237.V | 120712/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002129 | 800232.V | 112433/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008986 | 780977.V | 118254/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008987 | 780973.V | 118235/1A.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008988 | 780977.V | 118255/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008989 | 780977.V | 118252/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008990 | 974777.V | 119937/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008992 | 780977.V | 118250/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008993 | 974777.V | 119932/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008994 | 781079.V | 119597/2.V | 12140 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008995 | 974777.V | 119938/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008996 | 974777.V | 119933/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008997 | 974777.V | 119934/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008998 | 800851.V | 118187/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008999 | 974777.V | 119936/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009000 | 801197.V | 121988/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009002 | 801197.V | 121993/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008628 | 781237.V | 120714/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008627 | 781241.V | 120938/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008018 | 780992.V | 118293/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009006 | 801194.V | 121979/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009007 | 801197.V | 121987/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009008 | 801194.V | 121979/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009009 | 801194.V | 121983/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009010 | 801197.V | 121990/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009011 | 801197.V | 121986/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009012 | 974720.V | 118498/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009013 | 974720.V | 118499/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009014 | 974720.V | 118503/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009015 | 974720.V | 118504/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009016 | 974720.V | 118501/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009017 | 801194.V | 121984/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009018 | 801197.V | 121989/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008626 | 781241.V | 120938/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009020 | 801197.V | 121987/1.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009021 | 801194.V | 121984/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009022 | 801194.V | 121980/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009023 | 801194.V | 121972/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009024 | 801197.V | 121998/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009025 | 801197.V | 121996/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009026 | 801194.V | 121973/1A.V | 12260 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009027 | 801197.V | 121991/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009028 | 801197.V | 121994/2.V | 11990 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009029 | 801197.V | 121998/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009030 | 801197.V | 121985/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009031 | 801194.V | 121976/1A.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009032 | 801194.V | 121980/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009033 | 801197.V | 121990/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009034 | 801197.V | 121995/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008625 | 781241.V | 120932/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008017 | 780992.V | 118299/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009037 | 780970.V | 118223/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009038 | 801197.V | 121997/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009039 | 801194.V | 121982/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009040 | 801194.V | 121972/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009041 | 801197.V | 121997/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009042 | 801194.V | 121978/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009043 | 801194.V | 121971/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009044 | 801194.V | 121975/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009045 | 801194.V | 121975/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009046 | 801197.V | 121996/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009047 | 801197.V | 121994/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009048 | 801194.V | 121974/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009049 | 801194.V | 121981/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 | FL | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009050 | 801194.V | 121977/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009051 | 801194.V | 121977/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009052 | 801194.V | 121974/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009053 | 801197.V | 121995/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009054 | 801197.V | 121992/1.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009055 | 801194.V | 121983/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009056 | 801197.V | 121992/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009057 | 781004.V | 118282/2A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009058 | 781034.V | 119439/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009059 | 781034.V | 119440/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009060 | 781034.V | 119437/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009061 | 781034.V | 119437/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009062 | 781004.V | 118286/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009063 | 781004.V | 118276/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009064 | 781004.V | 118281/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009065 | 781004.V | 118278/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009066 | 781004.V | 118282/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007743 | 801208.V | 122021/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008624 | 781237.V | 120718/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009069 | 781034.V | 119431/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009070 | 781034.V | 119433/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009071 | 781034.V | 119432/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009072 | 781004.V | 118275/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009074 | 781034.V | 119441/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009075 | 781004.V | 118274/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009076 | 781004.V | 118279/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009077 | 781004.V | 118280/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009078 | 781004.V | 118279/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009079 | 781004.V | 118285/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009080 | 781004.V | 118283/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009081 | 781034.V | 119440/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009082 | 781004.V | 118280/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009083 | 781004.V | 118274/2A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009084 | 781004.V | 118284/2A.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009085 | 781034.V | 119438/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009086 | 781034.V | 119435/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009087 | 781034.V | 119431/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009088 | 781004.V | 118275/1A.V | 12460 | EC
[9 empty] | 5021701 | 26.4.009089 | 781034.V | 119436/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009090 | 781034.V | 119439/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009091 | 781034.V | 119433/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009092 | 781034.V | 119436/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009093 | 781034.V | 119434/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009094 | 781034.V | 119434/1A.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009095 | 781004.V | 118284/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009096 | 781004.V | 118283/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009097 | 781004.V | 118285/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009098 | 781004.V | 118273/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009099 | 781004.V | 118273/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008623 | 781241.V | 120928/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009101 | 974765.V | 119924/1.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009102 | 974765.V | 119917/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009103 | 974765.V | 119916/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009104 | 974750.V | 119520/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009105 | 974765.V | 119922/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009106 | 974765.V | 119917/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009107 | 974765.V | 119923/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009108 | 974750.V | 119522/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009109 | 974765.V | 119924/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009110 | 974750.V | 119523/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009111 | 974750.V | 119522/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009112 | 974750.V | 119525/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009113 | 974750.V | 119529/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009114 | 974750.V | 119528/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009115 | 974750.V | 119529/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009116 | 974765.V | 119919/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009117 | 974750.V | 119523/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009118 | 974765.V | 119921/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009119 | 974750.V | 119524/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009120 | 974750.V | 119525/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009121 | 974750.V | 119517/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009122 | 974765.V | 119920/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009123 | 974750.V | 119518/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009124 | 974750.V | 119519/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009125 | 974765.V | 119918/1A.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009126 | 974750.V | 119517/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009127 | 974750.V | 119530/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009128 | 974765.V | 119925/2.V | 12450 | EC | PU | SEL | SI | SE | U1 | FL | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009129 | 974750.V | 119527/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009130 | 974750.V | 119530/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009131 | 974765.V | 119922/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008016 | 780992.V | 118295/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008622 | 781241.V | 120934/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008621 | 781241.V | 120936/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008015 | 780992.V | 118293/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009136 | 974765.V | 119923/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009137 | 974750.V | 119519/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009138 | 974750.V | 119521/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009139 | 974750.V | 119526/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009140 | 974750.V | 119520/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009141 | 974750.V | 119527/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009142 | 974750.V | 119521/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009143 | 974765.V | 119918/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009144 | 974765.V | 119915/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009145 | 974750.V | 119528/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009146 | 974765.V | 119925/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009147 | 781254.V | 120778/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009148 | 781254.V | 120784/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009149 | 781253.V | 120983/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009150 | 781253.V | 120978/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009151 | 781253.V | 120976/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009152 | 781254.V | 120782/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009153 | 781253.V | 120979/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009154 | 781253.V | 120976/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009155 | 781253.V | 120980/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009156 | 781253.V | 120979/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009157 | 781253.V | 120975/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009158 | 781253.V | 120975/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009159 | 781254.V | 120778/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009160 | 781253.V | 120986/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009161 | 781254.V | 120781/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009162 | 781254.V | 120780/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009163 | 781254.V | 120780/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.007742 | 801208.V | 122025/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009165 | 781254.V | 120781/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009166 | 781254.V | 120779/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009167 | 781253.V | 120984/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009168 | 781253.V | 120981/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009169 | 781253.V | 120988/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009170 | 781253.V | 120981/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009171 | 781254.V | 120782/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009172 | 781254.V | 120783/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009173 | 781253.V | 120987/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009174 | 781253.V | 120987/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009175 | 781253.V | 120985/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009176 | 781253.V | 120985/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009177 | 781253.V | 120982/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009178 | 781253.V | 120983/1.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009179 | 781253.V | 120982/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009180 | 781254.V | 120777/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009181 | 781267.V | 120807/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009182 | 781266.V | 121000/1.V | 12460 | EC
[9 empty] | 5021701 | 26.4.009183 | 781267.V | 120801/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009184 | 781266.V | 120989/2.V | 11840 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009185 | 781266.V | 120993/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009186 | 781267.V | 120801/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009187 | 781266.V | 120990/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009188 | 781267.V | 120809/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009189 | 781267.V | 120802/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009190 | 781266.V | 120991/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009191 | 781267.V | 120806/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009192 | 781266.V | 120991/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009193 | 781267.V | 120807/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009194 | 781267.V | 120811/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009195 | 781266.V | 120994/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002128 | 800232.V | 112434/1.V | 12470 | EC | PU | SEL | SI | SE | U1 | FL |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.008620 | 781241.V | 120930/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009198 | 781267.V | 120800/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009199 | 781267.V | 120799/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009200 | 781267.V | 120799/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009201 | 781267.V | 120805/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009202 | 781267.V | 120810/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009203 | 781266.V | 120997/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009204 | 781266.V | 120998/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009206 | 781266.V | 120998/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009207 | 781267.V | 120803/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009208 | 781266.V | 120990/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009209 | 781266.V | 120992/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009210 | 781267.V | 120798/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009211 | 781266.V | 120999/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009212 | 781266.V | 120999/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009213 | 781266.V | 121001/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009214 | 781266.V | 121002/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009215 | 781267.V | 120804/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009216 | 781267.V | 120798/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009217 | 781267.V | 120804/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009218 | 781267.V | 120802/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009219 | 781267.V | 120811/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009220 | 781267.V | 120810/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009221 | 781267.V | 120803/1A.V | 12130 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009222 | 781267.V | 120808/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009223 | 781267.V | 120808/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009224 | 781040.V | 119448/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009225 | 781040.V | 119448/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009226 | 781035.V | 119828/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009227 | 781035.V | 119828/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009228 | 781035.V | 119829/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008619 | 781241.V | 120925/1A.V | 11750 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009230 | 781035.V | 119831/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009231 | 781040.V | 119447/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009232 | 781040.V | 119447/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009233 | 781040.V | 119443/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009234 | 781035.V | 119833/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009235 | 781035.V | 119829/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009236 | 781040.V | 119449/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009238 | 781040.V | 119445/1A.V | 12450 | EC | PU | SEL | SI | SE |  |  | REP
[9 empty] | 5021701 | 26.4.009239 | 781040.V | 119445/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009240 | 781035.V | 119822/1A.V | 11810 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009241 | 781035.V | 119827/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009242 | 781040.V | 119446/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009243 | 781040.V | 119446/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009244 | 781035.V | 119833/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009245 | 781040.V | 119442/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009246 | 781035.V | 119830/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009247 | 781035.V | 119830/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009248 | 781035.V | 119823/1A.V | 12150 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009249 | 781035.V | 119822/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009250 | 781035.V | 119832/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009251 | 781243.V | 120939/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009252 | 781242.V | 120746/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009253 | 781035.V | 119832/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009254 | 781243.V | 120940/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009255 | 781242.V | 120735/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009256 | 781242.V | 120746/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009257 | 781242.V | 120747/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009258 | 781242.V | 120739/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009259 | 781242.V | 120737/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009260 | 781242.V | 120736/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009261 | 781242.V | 120737/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008014 | 780992.V | 118292/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008618 | 800976.V | 119552/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009264 | 781243.V | 120942/1.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009265 | 781242.V | 120738/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009266 | 781242.V | 120739/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009267 | 781242.V | 120741/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009268 | 781242.V | 120740/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009269 | 781243.V | 120939/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009270 | 781242.V | 120741/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009271 | 781242.V | 120744/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009272 | 781242.V | 120736/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009273 | 781242.V | 120745/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009274 | 781242.V | 120747/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009275 | 781242.V | 120748/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009276 | 781242.V | 120748/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009277 | 781243.V | 120940/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009278 | 781243.V | 120941/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009279 | 781243.V | 120945/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009280 | 781243.V | 120942/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009281 | 781243.V | 120944/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009282 | 781243.V | 120945/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009283 | 781242.V | 120742/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009284 | 781243.V | 120944/1.V | 12240 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009285 | 781242.V | 120743/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009286 | 781242.V | 120742/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009287 | 781242.V | 120744/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009288 | 974803.V | 120673/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009289 | 974803.V | 120670/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009290 | 974803.V | 120671/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009291 | 974803.V | 120672/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009292 | 974803.V | 120665/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009293 | 974803.V | 120664/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008617 | 800977.V | 119577/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009295 | 974803.V | 120668/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009296 | 974803.V | 120674/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009297 | 974803.V | 120672/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009298 | 974803.V | 120669/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009299 | 974803.V | 120666/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009300 | 974803.V | 120663/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009301 | 974803.V | 120675/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009302 | 974803.V | 120673/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009303 | 974807.V | 120708/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009304 | 974803.V | 120668/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009305 | 974803.V | 120666/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009306 | 974803.V | 120669/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009307 | 974803.V | 120674/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009308 | 974807.V | 120705/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009309 | 974807.V | 120705/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009310 | 974807.V | 120706/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009311 | 974807.V | 120706/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009312 | 974807.V | 120709/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009313 | 974803.V | 120671/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009314 | 974807.V | 120704/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009315 | 781035.V | 119825/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009316 | 781035.V | 119826/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009317 | 781035.V | 119820/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009318 | 781035.V | 119824/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009319 | 781035.V | 119821/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009320 | 781250.V | 120962/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009321 | 781250.V | 120967/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009322 | 781251.V | 120774/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009323 | 781251.V | 120763/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009324 | 781250.V | 120972/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009325 | 781250.V | 120972/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008013 | 780992.V | 118289/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007741 | 801208.V | 122018/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009328 | 781251.V | 120769/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009329 | 781251.V | 120776/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009330 | 781250.V | 120971/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009331 | 781250.V | 120971/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009332 | 781250.V | 120969/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009333 | 781250.V | 120963/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009334 | 781250.V | 120970/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009335 | 781251.V | 120769/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009336 | 781250.V | 120968/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009337 | 781251.V | 120768/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009338 | 781251.V | 120764/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  | REP |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009339 | 781250.V | 120970/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009340 | 781251.V | 120767/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009341 | 781251.V | 120763/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009342 | 781251.V | 120768/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009343 | 781251.V | 120766/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009344 | 781250.V | 120973/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009345 | 781251.V | 120766/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009346 | 781251.V | 120772/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009347 | 781251.V | 120765/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009348 | 781250.V | 120964/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009349 | 781251.V | 120764/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009350 | 781251.V | 120767/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009351 | 781251.V | 120771/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009352 | 781251.V | 120770/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009353 | 781251.V | 120773/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009354 | 781250.V | 120974/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009355 | 780978.V | 118524/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009357 | 780979.V | 118321/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009358 | 780978.V | 118520/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008616 | 800977.V | 119580/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009360 | 780979.V | 118319/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009361 | 780978.V | 118519/1.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009362 | 780978.V | 118514/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009363 | 780979.V | 118315/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009364 | 780978.V | 118519/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009365 | 780979.V | 118322/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009366 | 780979.V | 118320/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009367 | 780979.V | 118316/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009368 | 780978.V | 118516/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009369 | 780978.V | 118518/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009370 | 780978.V | 118521/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009371 | 780978.V | 118521/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009372 | 780978.V | 118518/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009373 | 780979.V | 118322/1.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009374 | 780978.V | 118523/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009375 | 780978.V | 118523/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009376 | 780978.V | 118515/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009377 | 780978.V | 118524/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009378 | 780978.V | 118522/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009379 | 780979.V | 118317/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009380 | 780978.V | 118513/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009382 | 780978.V | 118514/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009383 | 780979.V | 118318/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009385 | 780979.V | 118324/2.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009386 | 780979.V | 118315/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009387 | 780978.V | 118515/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009388 | 780978.V | 118512/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009389 | 780979.V | 118316/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009390 | 780979.V | 118320/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009391 | 780979.V | 118324/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009392 | 780978.V | 118517/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008615 | 800976.V | 119562/2.V | 12470 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.008011 | 780992.V | 118287/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008614 | 800977.V | 119581/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009396 | 801153.V | 120749/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009397 | 801152.V | 120956/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009398 | 801153.V | 120752/1A.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009399 | 801153.V | 120758/2.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009400 | 801153.V | 120750/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009401 | 801153.V | 120754/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009402 | 801152.V | 120960/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009403 | 801153.V | 120762/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009404 | 801152.V | 120954/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009405 | 801153.V | 120757/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009406 | 801153.V | 120750/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009407 | 801152.V | 120957/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009408 | 801152.V | 120950/1.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009409 | 801153.V | 120761/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009410 | 801153.V | 120762/1A.V | 12440 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009411 | 801153.V | 120756/1A.V | 12440 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009412 | 801153.V | 120751/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009413 | 801153.V | 120755/2.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009414 | 801153.V | 120761/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009415 | 801152.V | 120953/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009416 | 801152.V | 120955/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009417 | 801153.V | 120760/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009418 | 801152.V | 120956/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009419 | 801153.V | 120751/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009420 | 801153.V | 120752/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009421 | 801152.V | 120951/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009422 | 801152.V | 120960/1.V | 12440 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009423 | 800942.V | 119848/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009424 | 801152.V | 120951/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009687 | 781268.V | 121005/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009426 | 800942.V | 119856/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009427 | 800942.V | 119850/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009428 | 800942.V | 119856/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009429 | 800942.V | 119858/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009430 | 800942.V | 119858/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009431 | 800908.V | 118536/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009432 | 800942.V | 119848/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009433 | 800908.V | 118530/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009434 | 800908.V | 118535/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009435 | 800908.V | 118528/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009436 | 800908.V | 118529/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009437 | 800942.V | 119855/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009438 | 800942.V | 119853/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009439 | 800942.V | 119850/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009440 | 800942.V | 119852/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009441 | 800908.V | 118538/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009442 | 801153.V | 120760/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009443 | 801153.V | 120756/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009444 | 800908.V | 118533/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009445 | 800942.V | 119854/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009446 | 800908.V | 118527/2.V | 12060 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009447 | 800908.V | 118528/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009448 | 800908.V | 118527/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009449 | 800908.V | 118529/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009450 | 800942.V | 119851/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009451 | 800942.V | 119849/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009452 | 800942.V | 119852/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.009453 | 800942.V | 119851/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009454 | 800942.V | 119857/1A.V | 12440 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009455 | 800942.V | 119857/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009456 | 800908.V | 118538/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008613 | 800977.V | 119573/1A.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008010 | 780992.V | 118290/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009459 | 800942.V | 119849/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009460 | 800908.V | 118536/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009461 | 974794.V | 120880/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009462 | 974794.V | 120884/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009463 | 974794.V | 120874/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009465 | 974794.V | 120877/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009466 | 974794.V | 120874/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009467 | 974794.V | 120872/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009468 | 974794.V | 120880/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009469 | 974794.V | 120879/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009470 | 974794.V | 120877/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009471 | 974794.V | 120876/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009472 | 974794.V | 120876/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009473 | 974783.V | 119942/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009474 | 974794.V | 120875/1A.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009475 | 974794.V | 120883/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009476 | 974794.V | 120883/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009477 | 974794.V | 120879/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009478 | 974794.V | 120885/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009479 | 974794.V | 120882/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009480 | 974783.V | 119949/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009481 | 974783.V | 119947/1.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009482 | 974794.V | 120882/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009483 | 974783.V | 119949/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009484 | 974794.V | 120881/2.V | 12460 | EC | PU | SEL | SI | SE |  |  | REP
[9 empty] | 5021701 | 26.4.009485 | 974794.V | 120881/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009486 | 974783.V | 119943/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009488 | 974783.V | 119940/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009489 | 974783.V | 119943/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009490 | 974783.V | 119950/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007740 | 801208.V | 122028/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009492 | 974783.V | 119953/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009493 | 974783.V | 119952/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009494 | 974794.V | 120872/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009495 | 974794.V | 120878/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009496 | 974783.V | 119946/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009497 | 974794.V | 120878/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009498 | 974783.V | 119944/1.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009499 | 974783.V | 119942/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009500 | 974783.V | 119945/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009501 | 974783.V | 119941/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009502 | 781282.V | 121961/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009503 | 974783.V | 119940/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009504 | 781278.V | 121951/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009505 | 781282.V | 121963/2.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009506 | 781278.V | 121949/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009507 | 781278.V | 121956/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009508 | 781278.V | 121944/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009509 | 781282.V | 121963/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009510 | 781278.V | 121944/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009511 | 781278.V | 121945/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009512 | 781282.V | 121968/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009513 | 781278.V | 121946/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009514 | 781278.V | 121948/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009515 | 781282.V | 121958/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009516 | 781282.V | 121959/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009517 | 781282.V | 121970/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009518 | 781282.V | 121957/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009519 | 781282.V | 121964/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009520 | 781278.V | 121945/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009521 | 781282.V | 121959/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.009522 | 781278.V | 121950/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.002127 | 800232.V | 112436/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008612 | 800977.V | 119574/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009525 | 781278.V | 121947/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009526 | 781278.V | 121946/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009527 | 781282.V | 121960/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009528 | 781282.V | 121969/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009529 | 781282.V | 121970/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009531 | 781282.V | 121966/2.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.009532 | 781282.V | 121969/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009533 | 781282.V | 121967/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009534 | 781282.V | 121967/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.009535 | 781282.V | 121966/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009536 | 781278.V | 121951/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.009537 | 781278.V | 121948/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009538 | 781282.V | 121962/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009539 | 781278.V | 121953/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009540 | 781278.V | 121943/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009541 | 781276.V | 121936/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009542 | 781276.V | 121937/1A.V | 12300 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009543 | 781268.V | 121008/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009544 | 781276.V | 121942/2.V | 12200 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009545 | 781276.V | 121941/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009546 | 781276.V | 121942/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009547 | 781276.V | 121935/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009548 | 781276.V | 121938/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009549 | 781268.V | 121015/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009550 | 781268.V | 121009/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009551 | 781268.V | 121008/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009552 | 781268.V | 121010/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009553 | 781268.V | 121007/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009554 | 781268.V | 121007/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009555 | 781268.V | 121005/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008611 | 800976.V | 119561/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009557 | 781268.V | 121009/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009558 | 781268.V | 121006/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009559 | 781276.V | 121936/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009560 | 781276.V | 121941/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009561 | 781276.V | 121933/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009562 | 781278.V | 121943/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009563 | 781282.V | 121962/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009565 | 781268.V | 121012/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009566 | 781268.V | 121016/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009567 | 781268.V | 121015/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009568 | 781276.V | 121937/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009569 | 781268.V | 121010/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009570 | 781278.V | 121954/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009571 | 781276.V | 121938/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009572 | 781282.V | 121958/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009573 | 781276.V | 121932/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009574 | 781278.V | 121950/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009575 | 781268.V | 121003/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009576 | 781278.V | 121955/2.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009577 | 781276.V | 121934/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX
[9 empty] | 5021701 | 26.4.009578 | 781268.V | 121016/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009579 | 781268.V | 121004/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009580 | 781268.V | 121003/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009581 | 781282.V | 121965/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009582 | 781268.V | 121006/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.009583 | 974783.V | 119948/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009584 | 781278.V | 121949/1A.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009585 | 781278.V | 121954/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009586 | 781282.V | 121964/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009587 | 781282.V | 121965/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009588 | 781278.V | 121953/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008009 | 780992.V | 118297/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008610 | 800976.V | 119561/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009591 | 781278.V | 121955/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009592 | 781278.V | 121956/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.009593 | 974783.V | 119952/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009594 | 781278.V | 121952/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009595 | 974783.V | 119950/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009596 | 974783.V | 119944/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009597 | 974783.V | 119945/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009598 | 974783.V | 119951/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009599 | 974783.V | 119941/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009600 | 781282.V | 121968/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2
[9 empty] | 5021701 | 26.4.009601 | 974783.V | 119947/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.009603 | 780978.V | 118517/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009604 | 780978.V | 118512/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009605 | 780979.V | 118317/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009606 | 800942.V | 119860/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009607 | 800908.V | 118530/2.V | 12480 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009608 | 800942.V | 119859/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009609 | 974794.V | 120873/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009610 | 974794.V | 120884/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009611 | 974794.V | 120873/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009612 | 974794.V | 120875/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009613 | 800942.V | 119860/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009614 | 800908.V | 118537/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009615 | 800908.V | 118525/2.V | 12370 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009616 | 800908.V | 118537/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009617 | 800908.V | 118525/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009618 | 781250.V | 120966/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009619 | 780979.V | 118323/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009620 | 781251.V | 120772/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009621 | 780979.V | 118323/1.V | 12340 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.008609 | 800977.V | 119575/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009623 | 781243.V | 120946/2.V | 12350 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009624 | 781250.V | 120961/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009625 | 781243.V | 120943/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009626 | 781242.V | 120745/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009627 | 781242.V | 120738/1A.V | 12330 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009628 | 801152.V | 120952/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009629 | 801153.V | 120753/1A.V | 12430 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009630 | 801153.V | 120753/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009631 | 800908.V | 118526/2.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009632 | 801153.V | 120754/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009633 | 801152.V | 120959/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009634 | 801152.V | 120950/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009635 | 801153.V | 120749/1A.V | 12210 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009636 | 801152.V | 120958/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009637 | 800942.V | 119859/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009638 | 800942.V | 119861/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009639 | 800908.V | 118535/2.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009640 | 800908.V | 118534/2.V | 12480 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009641 | 781251.V | 120775/1A.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009642 | 781035.V | 119823/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009643 | 781250.V | 120974/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009644 | 781040.V | 119444/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009645 | 974807.V | 120704/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009646 | 801152.V | 120953/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009647 | 781035.V | 119826/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009648 | 781250.V | 120963/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.009649 | 781251.V | 120776/2.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009650 | 781250.V | 120965/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009651 | 974807.V | 120708/1.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009652 | 974803.V | 120670/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009653 | 974807.V | 120707/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.008008 | 780995.V | 118301/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007739 | 801208.V | 122028/2.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008608 | 800976.V | 119551/1.V | 12170 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008607 | 800976.V | 119563/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008007 | 780992.V | 118287/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.008606 | 800977.V | 119568/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008605 | 800977.V | 119570/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008006 | 780995.V | 118313/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007738 | 781283.V | 121415/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002126 | 800232.V | 112439/1.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009670 | 801193.V | 121304/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009669 | 801189.V | 121284/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008604 | 800976.V | 119557/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009668 | 801189.V | 121285/1A.V | 12450 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.009667 | 801189.V | 121288/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008603 | 800976.V | 119557/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009671 | 801193.V | 121302/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009672 | 801189.V | 121284/2.V | 12450 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009673 | 801193.V | 121303/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009674 | 801193.V | 121300/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009675 | 801193.V | 121298/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009676 | 801193.V | 121297/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009677 | 781276.V | 121935/2.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009678 | 801193.V | 121303/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009679 | 781276.V | 121939/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009680 | 781268.V | 121012/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009681 | 781268.V | 121013/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009682 | 781276.V | 121939/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009683 | 781276.V | 121934/2.V | 12180 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009684 | 781276.V | 121932/1A.V | 11820 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009685 | 781268.V | 121004/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009686 | 781276.V | 121940/2.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008005 | 780995.V | 118302/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009688 | 781268.V | 121014/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009689 | 781276.V | 121940/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009690 | 801189.V | 121289/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009691 | 781268.V | 121013/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009692 | 801193.V | 121301/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009693 | 801189.V | 121286/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009694 | 801193.V | 121301/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009695 | 801193.V | 121295/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009696 | 801193.V | 121298/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009697 | 801189.V | 121286/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009699 | 801193.V | 121302/1A.V | 12270 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009700 | 801193.V | 121300/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009701 | 801189.V | 121290/1A.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009702 | 801189.V | 121290/2.V | 12190 | EC | PU | SEL | SI | SE | U1 |  | REP | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009703 | 801189.V | 121289/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009704 | 801193.V | 121296/2.V | 11840 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009705 | 801189.V | 121288/1A.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009706 | 801189.V | 121285/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009707 | 801144.V | 120731/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009708 | 801193.V | 121299/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009709 | 801144.V | 120732/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009710 | 801144.V | 120728/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009711 | 801143.V | 120917/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009712 | 801143.V | 120918/1A.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009713 | 801193.V | 121296/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009714 | 801193.V | 121297/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009715 | 801144.V | 120724/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009716 | 801193.V | 121299/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009717 | 801144.V | 120729/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009718 | 801144.V | 120724/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009719 | 801144.V | 120730/1A.V | 12030 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009666 | 781243.V | 120946/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009665 | 781242.V | 120740/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.009722 | 801143.V | 120919/1A.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009723 | 801143.V | 120912/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009724 | 801144.V | 120727/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009725 | 801143.V | 120915/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009726 | 801143.V | 120915/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009727 | 801143.V | 120911/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009728 | 801144.V | 120732/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009729 | 801144.V | 120725/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009730 | 801144.V | 120725/1A.V | 12460 | EC | PU | SEL |  |  |  |  | REP
[9 empty] | 5021701 | 26.4.009731 | 801143.V | 120920/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009732 | 801143.V | 120921/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009733 | 801143.V | 120913/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009734 | 801144.V | 120733/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009735 | 801143.V | 120920/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009736 | 801143.V | 120921/1A.V | 12050 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009737 | 801193.V | 121304/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009738 | 801144.V | 120734/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009739 | 801143.V | 120913/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009740 | 801143.V | 120914/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009741 | 801143.V | 120919/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009742 | 801143.V | 120911/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009743 | 801143.V | 120912/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009744 | 974686.V | 118497/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009745 | 974686.V | 118494/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009746 | 974683.V | 118480/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009747 | 974686.V | 118492/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009748 | 974683.V | 118483/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009749 | 974686.V | 118486/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009750 | 974686.V | 118488/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009751 | 974686.V | 118492/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008602 | 800976.V | 119556/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009753 | 974686.V | 118491/1.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009754 | 974683.V | 118476/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009755 | 974686.V | 118493/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009756 | 974686.V | 118484/2.V | 12470 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009757 | 974686.V | 118486/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009758 | 974686.V | 118490/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009759 | 974686.V | 118487/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009760 | 974683.V | 118477/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009761 | 801144.V | 120728/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009762 | 801144.V | 120731/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009763 | 974686.V | 118489/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009764 | 974686.V | 118489/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009765 | 974686.V | 118494/2.V | 12470 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.009766 | 974686.V | 118495/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009767 | 974683.V | 118479/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009768 | 974686.V | 118495/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009769 | 974683.V | 118477/2.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009770 | 974683.V | 118481/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009771 | 974683.V | 118483/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009772 | 974683.V | 118478/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009773 | 974686.V | 118484/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009774 | 974683.V | 118482/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009775 | 974686.V | 118490/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009776 | 974686.V | 118485/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009777 | 974686.V | 118496/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009778 | 974686.V | 118491/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009779 | 974686.V | 118497/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009780 | 974686.V | 118493/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009782 | 800980.V | 119590/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009783 | 800980.V | 119584/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.009784 | 800979.V | 119963/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009664 | 800908.V | 118534/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009663 | 974803.V | 120667/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.009787 | 800979.V | 119963/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009788 | 800980.V | 119583/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009789 | 800980.V | 119583/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009790 | 800979.V | 119965/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009791 | 800980.V | 119591/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009792 | 800979.V | 119965/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009793 | 800980.V | 119584/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009794 | 800979.V | 119957/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009795 | 800979.V | 119961/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009796 | 800980.V | 123560/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009797 | 800979.V | 119957/2.V | 12230 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009798 | 800980.V | 119590/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009799 | 800980.V | 123560/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009800 | 800980.V | 119588/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009801 | 800980.V | 123561/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009802 | 800980.V | 123561/1A.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009803 | 800980.V | 119589/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009804 | 800979.V | 119955/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009805 | 800980.V | 119591/2.V | 12220 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009806 | 800979.V | 119966/1.V | 11840 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009807 | 800979.V | 119955/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009808 | 800979.V | 119966/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009809 | 800980.V | 119588/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009810 | 781082.V | 120863/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009811 | 781082.V | 120863/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009812 | 781082.V | 120861/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009813 | 781082.V | 120856/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009814 | 781080.V | 119981/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009815 | 781082.V | 120862/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009816 | 781080.V | 119978/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008601 | 800976.V | 119558/1.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009818 | 781080.V | 119990/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009819 | 781082.V | 120858/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009820 | 781082.V | 120858/1A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009821 | 781082.V | 120862/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009822 | 781080.V | 119988/2.V | 12360 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009823 | 781080.V | 119983/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009824 | 781080.V | 119989/2.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009825 | 781080.V | 119982/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009826 | 781080.V | 119984/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009827 | 781080.V | 119982/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009828 | 781082.V | 122613/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009829 | 781080.V | 119984/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009830 | 781080.V | 119989/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009831 | 781082.V | 120860/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009832 | 781082.V | 120853/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009833 | 781080.V | 119990/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009834 | 781080.V | 119978/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009835 | 781080.V | 119979/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009836 | 781082.V | 120854/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009837 | 781082.V | 120853/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009838 | 781080.V | 119981/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009839 | 781082.V | 120854/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009840 | 780942.V | 118451/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009841 | 780943.V | 118467/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009842 | 780942.V | 118453/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009843 | 780942.V | 118453/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009844 | 780942.V | 118457/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009845 | 780942.V | 118454/2.V | 12470 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009846 | 780942.V | 118456/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009847 | 780942.V | 118456/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009848 | 780942.V | 118455/1.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008004 | 780995.V | 118308/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.007737 | 781283.V | 121416/1.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009851 | 780943.V | 118469/1.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009852 | 780943.V | 118469/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009853 | 780943.V | 118465/2.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009854 | 780943.V | 118468/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009855 | 780943.V | 118468/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009856 | 780943.V | 118470/1.V | 12240 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009857 | 780942.V | 118455/2.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009858 | 780943.V | 118470/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009859 | 780943.V | 118471/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009860 | 780942.V | 118449/1.V | 12210 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009862 | 780942.V | 118461/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009863 | 780943.V | 118465/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009864 | 780942.V | 118448/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009865 | 780943.V | 118462/1.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009866 | 780943.V | 118464/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009867 | 781082.V | 120857/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009868 | 781082.V | 120855/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009869 | 781082.V | 120855/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009870 | 781080.V | 120852/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009871 | 781080.V | 119983/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009872 | 781082.V | 120856/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009873 | 781080.V | 119980/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009874 | 781082.V | 120861/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009875 | 780943.V | 118462/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009876 | 780942.V | 118448/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009877 | 780943.V | 119743/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009878 | 780943.V | 118472/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009879 | 780942.V | 118458/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009880 | 780943.V | 119743/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009881 | 780943.V | 118466/1.V | 12290 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009662 | 974803.V | 120667/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.009883 | 780942.V | 118460/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009884 | 780942.V | 118460/1.V | 12350 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009885 | 780943.V | 118467/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009886 | 780942.V | 118461/2.V | 12480 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.009887 | 780943.V | 118466/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009888 | 780943.V | 118471/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009889 | 780942.V | 118452/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.009890 | 780942.V | 118457/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009891 | 780942.V | 118452/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009892 | 780942.V | 118451/1.V | 12190 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009893 | 780942.V | 118459/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009894 | 780943.V | 118463/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009895 | 780943.V | 118472/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009896 | 780942.V | 118454/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009897 | 780944.V | 118168/2A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009898 | 780944.V | 118166/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009899 | 780944.V | 118164/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009900 | 780944.V | 118162/2A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009901 | 780944.V | 118167/1A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009902 | 780944.V | 118163/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009903 | 780944.V | 118163/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009904 | 780944.V | 118162/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009905 | 780944.V | 118169/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009906 | 780944.V | 118166/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009907 | 780944.V | 118169/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009908 | 781001.V | 118177/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009909 | 781001.V | 118174/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009910 | 781001.V | 118182/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009911 | 781001.V | 118177/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009912 | 781001.V | 118181/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009913 | 781001.V | 118179/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009660 | 974803.V | 120663/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008600 | 800976.V | 119552/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009659 | 781035.V | 119820/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.009917 | 780996.V | 118588/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009918 | 780996.V | 118576/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009919 | 781001.V | 118180/2A.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009920 | 974649.V | 118154/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009921 | 780996.V | 118588/2.V | 12280 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009922 | 781001.V | 118180/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009923 | 781001.V | 118179/2A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009924 | 781001.V | 118176/1A.V | 12200 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009925 | 781001.V | 118173/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009926 | 781001.V | 118175/2A.V | 12120 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009927 | 781001.V | 118183/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009928 | 781001.V | 118183/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009929 | 780944.V | 118165/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009930 | 780944.V | 118165/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009931 | 780996.V | 118577/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009932 | 780996.V | 118579/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009933 | 780996.V | 118579/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009934 | 780996.V | 118585/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009935 | 780996.V | 118578/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009936 | 974649.V | 118159/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009937 | 974649.V | 118156/2A.V | 12470 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.009938 | 974649.V | 118155/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009939 | 780996.V | 118575/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009940 | 974649.V | 118156/1A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.009941 | 780996.V | 118585/1.V | 12250 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009942 | 780996.V | 118586/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009943 | 974649.V | 118151/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009944 | 780996.V | 118578/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009945 | 780996.V | 118587/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009658 | 781035.V | 119821/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.009947 | 974649.V | 118148/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009948 | 974649.V | 118153/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009949 | 974649.V | 118157/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009950 | 974649.V | 118150/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009951 | 780996.V | 118581/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009952 | 974689.V | 118243/2A.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009953 | 974689.V | 118247/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009954 | 974689.V | 118247/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009955 | 974711.V | 118539/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009956 | 974711.V | 118543/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009957 | 974689.V | 118243/1A.V | 11920 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009958 | 974711.V | 118540/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009959 | 974711.V | 118540/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009960 | 974711.V | 118542/2.V | 12160 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009961 | 974711.V | 118543/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009962 | 974689.V | 118245/1A.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009963 | 974689.V | 118244/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009964 | 974711.V | 119715/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009965 | 974689.V | 118242/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009966 | 974689.V | 118241/1A.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.009967 | 974689.V | 118242/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.009968 | 974689.V | 118241/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009969 | 974689.V | 118244/1A.V | 12200 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009970 | 974689.V | 118245/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009971 | 974711.V | 119715/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009972 | 974689.V | 118240/2A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009973 | 974719.V | 118206/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009974 | 974719.V | 118204/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009975 | 801231.V | 122086/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009976 | 974719.V | 118204/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009977 | 801231.V | 122085/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.008599 | 800976.V | 119560/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008003 | 780995.V | 118304/1.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.009980 | 801231.V | 122085/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009981 | 974719.V | 118205/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009982 | 974719.V | 118202/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009983 | 801231.V | 122089/2.V | 12400 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.009984 | 801231.V | 122091/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009985 | 801231.V | 122091/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009986 | 801231.V | 122092/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009987 | 801231.V | 122090/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009988 | 801231.V | 122088/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009989 | 974719.V | 118208/1A.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009990 | 801231.V | 122090/1.V | 11980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009991 | 974719.V | 118205/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009992 | 974711.V | 118542/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009993 | 974711.V | 118541/1.V | 12460 | EC
[9 empty] | 5021701 | 26.4.009994 | 974711.V | 118541/2.V | 12330 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009995 | 974711.V | 118539/1.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009996 | 974689.V | 118240/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009997 | 974689.V | 118246/1.V | 12460 | EC
[9 empty] | 5021701 | 26.4.009998 | 974689.V | 118246/2.V | 12470 | EC
[9 empty] | 5021701 | 26.4.009999 | 974719.V | 118211/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.010000 | 974719.V | 118209/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010001 | 974719.V | 118198/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.010002 | 974719.V | 118209/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010003 | 974719.V | 118203/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010004 | 974719.V | 118207/2A.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010005 | 974719.V | 118201/2A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010006 | 974719.V | 118210/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010007 | 974719.V | 118198/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010008 | 974719.V | 118200/2A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010009 | 974719.V | 118206/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009657 | 974807.V | 120709/1.V | 12180 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010011 | 801231.V | 122092/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010012 | 974719.V | 118202/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010013 | 801231.V | 122088/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010014 | 801231.V | 122094/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010015 | 974719.V | 118201/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010016 | 801231.V | 122093/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010017 | 801231.V | 122089/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010018 | 974719.V | 118211/2A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010019 | 801206.V | 122011/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010020 | 801206.V | 122007/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.010021 | 801206.V | 122015/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010022 | 801206.V | 122015/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010023 | 801206.V | 122017/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010024 | 801206.V | 122007/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010025 | 801206.V | 122009/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010026 | 801206.V | 122017/1A.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010027 | 801223.V | 122081/1.V | 12460 | EC | PU | SEL | SI |  |  |  | REP
[9 empty] | 5021701 | 26.4.010028 | 801223.V | 122074/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010029 | 801223.V | 122076/1.V | 12320 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010030 | 801206.V | 122008/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010031 | 801223.V | 122080/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010032 | 801223.V | 122076/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  | REP
[9 empty] | 5021701 | 26.4.010033 | 801223.V | 122079/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010034 | 801223.V | 122078/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010035 | 801223.V | 122074/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010036 | 801223.V | 122075/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.010037 | 801223.V | 122077/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010038 | 801232.V | 122106/2.V | 12340 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010039 | 974972.V | 120827/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010040 | 974972.V | 120830/2.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010041 | 801232.V | 122101/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009656 | 974803.V | 120662/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008598 | 800976.V | 119554/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010044 | 801232.V | 122102/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010045 | 801232.V | 122105/1A.V | 12380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.010046 | 801232.V | 122103/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010047 | 801232.V | 122104/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010048 | 801232.V | 122108/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010049 | 801232.V | 122104/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010050 | 801232.V | 122095/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010051 | 974972.V | 120828/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010052 | 801232.V | 122102/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010053 | 801232.V | 122100/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010054 | 801232.V | 122099/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010055 | 801232.V | 122103/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010056 | 801232.V | 122100/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010057 | 974972.V | 120829/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010058 | 801232.V | 122097/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.010059 | 801232.V | 122099/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010060 | 974972.V | 120833/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010061 | 974972.V | 120826/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010062 | 801232.V | 122107/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010063 | 801232.V | 122097/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010064 | 801232.V | 122098/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.010065 | 801232.V | 122107/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010066 | 801237.V | 121442/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM
[9 empty] | 5021701 | 26.4.010067 | 801237.V | 121439/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010068 | 801237.V | 121439/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010069 | 801237.V | 121436/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010070 | 801237.V | 121436/2.V | 12020 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.010071 | 801237.V | 121435/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | 5021701 | 26.4.010072 | 801237.V | 121438/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010073 | 801237.V | 121435/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.009655 | 974803.V | 120664/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010075 | 801237.V | 121440/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010076 | 801237.V | 121437/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010077 | 801237.V | 121442/1A.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1
[9 empty] | 5021701 | 26.4.010078 | 801237.V | 121440/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010079 | 801237.V | 121441/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010080 | 781310.V | 121374/1.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010081 | 781310.V | 121373/1.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010082 | 801237.V | 121441/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010083 | 801237.V | 121437/2.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010084 | 781310.V | 121377/1.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010085 | 781310.V | 121372/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010086 | 974972.V | 120826/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE
[9 empty] | 5021701 | 26.4.010087 | 974972.V | 120832/2.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010088 | 801232.V | 122105/2.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.010089 | 801232.V | 122098/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010090 | 781310.V | 121377/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010091 | 781310.V | 121375/2.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2
[9 empty] | 5021701 | 26.4.010092 | 781310.V | 121371/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010093 | 781310.V | 121376/2.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2
[9 empty] | 5021701 | 26.4.010094 | 781310.V | 121371/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010095 | 781310.V | 121374/2.V | 12410 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010096 | 781310.V | 121376/1.V | 12450 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA
[9 empty] | 5021701 | 26.4.010097 | 781310.V | 121378/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN
[9 empty] | 5021701 | 26.4.010098 | 781310.V | 121375/1.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB
[9 empty] | 5021701 | 26.4.010099 | 801223.V | 122078/1.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010100 | 801223.V | 122077/2.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010101 | 974649.V | 118148/2A.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010102 | 974649.V | 118153/1A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010103 | 974649.V | 118151/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.010104 | 974649.V | 118160/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010105 | 974649.V | 118152/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.009654 | 781035.V | 119824/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.008597 | 800976.V | 119558/2.V | 12310 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010108 | 974649.V | 118149/1A.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010109 | 974649.V | 118160/2A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010110 | 780996.V | 118587/2.V | 12470 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010111 | 780996.V | 118576/2.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010112 | 974649.V | 118158/2A.V | 12460 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010113 | 780996.V | 118581/1.V | 12450 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010114 | 974649.V | 118155/2A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.010115 | 780996.V | 118580/2.V | 12440 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010116 | 780996.V | 118586/1.V | 12450 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010117 | 801206.V | 122011/1A.V | 12470 | EC | PU | SEL | SI | SE | U1
[9 empty] | 5021701 | 26.4.010118 | 974719.V | 118199/2A.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010119 | 974719.V | 118210/1A.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010120 | 974972.V | 120830/1A.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010121 | 801206.V | 122009/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.010122 | 974719.V | 118208/2A.V | 12480 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010123 | 974719.V | 118203/1A.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010124 | 974649.V | 118158/1A.V | 12460 | EC | PU | SEL | SI | SE
[9 empty] | 5021701 | 26.4.010125 | 781001.V | 118176/2A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010126 | 781001.V | 118174/2A.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010127 | 974979.V | 121269/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010128 | 974979.V | 121275/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010129 | 974979.V | 121274/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010130 | 974979.V | 121272/2.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010131 | 974979.V | 121273/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010132 | 974979.V | 121274/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010133 | 974979.V | 121270/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010134 | 974979.V | 121269/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010135 | 974979.V | 121281/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010136 | 781306.V | 121366/1.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010137 | 974979.V | 121276/1A.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.008002 | 780995.V | 118311/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.010139 | 974979.V | 121282/2.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010140 | 974979.V | 121270/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010141 | 781306.V | 121365/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010142 | 781306.V | 121363/1A.V | 11990 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010143 | 781306.V | 121365/1.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010144 | 781306.V | 121368/2.V | 11760 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010145 | 781306.V | 121367/1.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010146 | 781306.V | 121361/2.V | 12460 | EC | PU | SEL | SI
[9 empty] | 5021701 | 26.4.010147 | 781306.V | 121364/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.010148 | 781306.V | 121361/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.010149 | 781306.V | 121362/1A.V | 12350 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010150 | 781306.V | 121362/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.010151 | 974979.V | 121271/1A.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.010152 | 974979.V | 121272/1A.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010153 | 974979.V | 121275/1A.V | 12450 | EC | PU
[9 empty] | 5021701 | 26.4.010154 | 781306.V | 121366/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010155 | 781306.V | 121367/2.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010156 | 781306.V | 121363/2.V | 12470 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010157 | 974979.V | 121279/2.V | 12460 | EC | PU
[9 empty] | 5021701 | 26.4.010158 | 974979.V | 121278/1A.V | 12360 | EC | PU
[9 empty] | 5021701 | 26.4.010159 | 974979.V | 121277/2.V | 12480 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010160 | 974979.V | 121273/1A.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010161 | 974979.V | 121280/1A.V | 12460 | EC
[9 empty] | 5021701 | 26.4.010162 | 974979.V | 121276/2.V | 12460 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010163 | 974979.V | 121282/1A.V | 12450 | EC | PU | SEL
[9 empty] | 5021701 | 26.4.010164 | 974979.V | 121280/2.V | 12460 | EC
[9 empty] | 5021701 | 26.4.010165 | 781306.V | 121364/1.V | 12460 | EC
[9 empty] | 5021701 | 26.4.010166 | 974979.V | 121278/2.V | 12470 | EC
[9 empty] | 5021701 | 26.4.010167 | 974979.V | 121281/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.010168 | 781306.V | 121368/1.V | 12250 | EC
[9 empty] | 5021701 | 26.4.010169 | 974649.V | 118161/1A.V | 12450 | EC
[9 empty] | 5021701 | 26.4.007735 | 781283.V | 121415/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | PDES | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.002125 | 800232.V | 112442/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.008136 | 800959.V | 119884/2.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | 5021701 | 26.4.010173 | 974649.V | 118157/2A.V | 12470 | EC
[9 empty] | 5021701 | 26.4.900028 | 974062.V | 112469/1.V | 4380 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.900029 | 974062.V | 112469/1.V | 3540 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | 5021701 | 26.4.008860 | 781079.V | 119598/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | DT03610322 | 26.4.009661 | 974807.V | 120707/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.009602 | 780979.V | 118321/1.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.009530 | 781282.V | 121961/1A.V | 12440 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.009001 | 801194.V | 121976/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008969 | 780977.V | 118256/1A.V | 11970 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.008877 | 974770.V | 119533/1.V | 11930 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008848 | 780977.V | 118253/1A.V | 12430 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.008507 | 800963.V | 119494/1.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 | [7 empty] | IF1 | IF2
[9 empty] | DT03610322 | 26.4.008285 | 975011.V | 122050/2.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008283 | 975011.V | 122055/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008218 | 801174.V | 120814/1A.V | 12460 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | DT03610322 | 26.4.008152 | 800959.V | 119876/2.V | 10980 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.008113 | 800970.V | 119911/1A.V | 12450 | EC | PU | SEL | SI | SE
[9 empty] | DT03610322 | 26.4.008032 | 780995.V | 118314/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | DT03610322 | 26.4.008012 | 780992.V | 118291/2.V | 12370 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2
[9 empty] | DT03610322 | 26.4.007887 | 800957.V | 119862/1A.V | 12420 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 |  | BA
[9 empty] | DT03610322 | 26.4.002117 | 800233.V | 112490/1.V | 11830 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA | DHC
[9 empty] | NXU0150217 | 26.4.009384 | 780979.V | 118318/1.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.009237 | 781035.V | 119827/1A.V | 11910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.008944 | 800851.V | 118187/2A.V | 11940 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.008906 | 974777.V | 119928/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.008044 | 800965.V | 119503/2.V | 11950 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.007993 | 780992.V | 118292/2.V | 11960 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.007976 | 780993.V | 118565/2.V | 11800 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | NXU0150217 | 26.4.007807 | 974992.V | 122000/2.V | 12000 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.009487 | 974783.V | 119946/1.V | 10660 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.009381 | 780978.V | 118513/2.V | 10080 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008991 | 974777.V | 119931/1.V | 11520 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008935 | 974720.V | 118499/2.V | 10400 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008909 | 974777.V | 119928/1.V | 11510 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008706 | 780939.V | 118438/2.V | 11640 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.008327 | 975011.V | 122057/2.V | 11670 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007952 | 801198.V | 121330/1A.V | 10910 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007773 | 801208.V | 122027/1A.V | 11570 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.007736 | 781283.V | 121416/2.V | 11530 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.002152 | 800233.V | 112489/2.V | 11520 | EC | PU | SEL | SI | SE | U1 |  |  |  | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.009698 | 801189.V | 121283/2.V | 10010 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA
[9 empty] | QXU0150217 | 26.4.002147 | 800233.V | 112487/2.V | 11550 | EC | PU | SEL | SI | SE | U1 |  |  | SMS | EX2 |  | TH | UTPA | UTMAN | UE | RX | LIMAB | IF1 | IF2 | PM | BA

## Pivot
| PO 5021701 | [7 empty] | PO 5021701 Totale | Totale complessivo
| 780325.V | 800222.V | 800223.V | 800229.V | 800232.V | 800233.V | 974058.V | 974062.V
ITP Steps.
Incoming Plate | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Pipe Forming | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Tack Welding | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
ID SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
OD SAWL | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
AUT1 | 28 | 15 | 21 | 21 | 25 | 16 | 18 | 26 | 170 | 170
Fluoroscopic |  |  | 3 | 1 | 1 | 1 | 4 | 2 | 12 | 12
Welding Repair |  | 2 |  | 1 |  |  | 1 |  | 4 | 4
MCE1 | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
MCE2
MCE Inspection | 28 | 13 | 21 | 20 | 24 | 16 | 16 | 26 | 164 | 164
Straighness Re-work | 1 |  | 2 | 2 |  |  | 1 |  | 6 | 6
Hydro Test | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
AUT2
Phase Arr. | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
MUT_ | 27 | 13 | 19 | 18 | 24 | 16 | 15 | 26 | 158 | 158
End UT | 27 | 13 | 19 | 17 | 24 | 16 | 15 | 26 | 157 | 157
X-Ray | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
OoR Pipe Body | 27 | 13 | 19 | 16 | 24 | 16 | 15 | 26 | 156 | 156
Dimensional 1 | 25 | 12 | 18 | 15 | 24 | 16 | 15 | 25 | 150 | 150
Dimensional 2 | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
MPI | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149
UT DHC | 25 | 12 | 17 | 15 | 24 | 16 | 14 | 24 | 147 | 147
Final Marking and Weighing | 25 | 12 | 18 | 15 | 24 | 16 | 14 | 25 | 149 | 149

## Chart
Este gráfico não está disponível na sua versão de Excel. Editar esta forma ou salvar esta pasta de trabalho em um formato de arquivo diferente quebrará o gráfico permanentemente.

## Repair
24OD x 1.268WT
REPAIR TABLE
DATE | Shift | Pipe Nº | Defect | Pipe Position (mm) | Extension (mm) | Remarks
2026-02-11 | 1 | 26.4.2089 | Weld heigh bead below the specified | 1200 | 300
2026-02-19 | 1 | 26.4.2205 | Slag Inclusion | 1450 | 100
2026-02-20 | 1 | 26.4.2207 | Underfill | 5510 | 130
2026-02-21 | 1 | 26.4.2252 | Stop/Start | 2320 | 200
2026-06-08 | 1 | 26.4.7866 | Weld Fail | 4600 | 200
2026-06-08 | 3 | 26.4.7838 | Weld Leak | 2500 | 200
2026-06-09 | 1 | 26.4.7840 | Slag Inclusion | 3360/5850 | 150/100
2026-06-10 | 1 | 26.4.7888 | Stop/Start | 8190 | 200
2026-06-10 | 1 | 26.4.7841 | Stop/Start | 2024 | 200
2026-06-10 | 1 | 26.4.7986 | Stop/Start | 9770 | 200
2026-06-10 | 1 | 26.4.7955 | Underfill | 3190 | 150
2026-06-10 | 1 | 26.4.8007 | Underfill | 9100 | 150
2026-06-10 | 1 | 26.4.8071 | Stop/Start | 2830 | 200
2026-06-10 | 3 | 26.4.8118 | Stop/Start | 7340 | 180
2026-06-10 | 3 | 26.4.8117 | Stop/Start | 3930 | 170
2026-06-11 | 3 | 26.4.8219 | Stop/Start | 11900 | 200
2026-06-12 | 1 | 24.6.8204 | Stop/Start | 6720 | 250
2026-06-12 | 3 | 24.6.8231 | Stop/Start | 5900/6500 | 100/100
2026-06-15 | 3 | 26.4.8344 | Stop/Start | 6400 | 200
2026-06-15 | 3 | 26.4.8222 | Stop/Start | 5100 | 200
2026-06-15 | 3 | 26.4.8313 | Stop/Start | 3560 | 200
2026-06-15 | 3 | 26.4.8360 | Stop/Start | 11630 | 150
2026-06-16 | 1 | 26.4.8326 | Stop/Start | 4600 | 300
2026-06-17 | 1 | 26.4.8456 | Stop/Start | 10570 | 300
2026-06-17 | 1 | 26.4.8401 | Stop/Start | 6300 | 300
2026-06-17 | 1 | 26.4.8406 | Underfill | 7775/9425/10340 | 150/150/150
2026-06-17 | 1 | 26.4.8519 | Pore | 9380 | 150
2026-06-17 | 3 | 26.4.8615 | Stop/Start | 3250 | 250
2026-06-18 | 1 | 26.4.8641 | Slag Inclusion | 2200 | 150
2026-06-18 | 3 | 26.4.8644 | Stop/Start | 4600 | 150
2026-06-18 | 3 | 26.4.8642 | Stop/Start | 2500 | 100
2026-06-19 | 3 | 26.4.8823 | Stop/Start | 1300 | 200
2026-06-19 | 3 | 26.4.8768 | Stop/Start | 3600 | 200
2026-06-19 | 3 | 26.4.8754 | Slag Inclusion | 6750 | 80
2026-06-22 | 3 | 26.4.8868 | Slag Inclusion | 5030 | 80
2026-06-23 | 1 | 26.4.8645 | Stop/Start | 7000 | 300
2026-06-23 | 1 | 26.4.9046 | Stop/Start | 3900 | 200
2026-06-23 | 1 | 26.4.8766 | Stop/Start | 4200 | 200
2026-06-23 | 1 | 26.4.8819 | Stop/Start | 4000 | 200
2026-06-23 | 1 | 26.4.8696 | Stop/Start - Underfill | 550 / 400 | 200 / 150 | 2 Repairs
2026-06-23 | 1 | 26.4.8800 | Stop/Start | 10530 | 250
2026-06-23 | 1 | 26.4.8855 | Stop/Start | 5930 | 200
2026-06-23 | 3 | 26.4.9003 | Stop/Start | 9000 | 200
2026-06-23 | 3 | 26.4.9128 | Stop/Start | 6300 | 100
2026-06-24 | 1 | 26.4.8722 | Slag Inclusion | 2200 | 200
2026-06-24 | 1 | 26.4.9091 | Slag Inclusion | 4070 | 150
2026-06-24 | 1 | 26.4.9167 | Underfill | 7500/11000 | 200/200
2026-06-25 | 1 | 26.4.9299 | Slag Inclusion | 2430 | 150
2026-06-25 | 1 | 26.4.9101 | Stop/Start | 10650 | 150
2026-06-25 | 1 | 26.4.9138 | Stop/Start
2026-06-25 | 1 | 26.4.8970 | Pore | 9350 | 150
2026-06-25 | 1 | 26.4.9325 | Pore | 4240 | 150
2026-06-26 | 1 | 26.4.9404 | Pore | 7600 | 150
2026-06-26 | 1 | 26.4.9389 | Pore | 4500 | 200
2026-06-26 | 1 | 26.4.9338 | Stop/Start | 11660 | 180
2026-06-26 | 1 | 26.4.9093 | underfill | 8500 | 150
2026-06-26 | 3 | 26.4.9491 | Stop/Start | 5000 | 200
2026-06-26 | 3 | 26.4.9474 | Stop/Start | 7320 | 200
2026-06-26 | 3 | 26.4.9481 | Stop/Start | 8600 | 200
2026-06-29 | 3 | 26.4.9569 | slag Inclusion | 6200 | 150
2026-06-29 | 3 | 26.4.9702 | Stop/Start | 0 | 200
2026-06-29 | 3 | 26.4.9672 | Stop/Start | 6200 | 200
2026-06-29 | 3 | 26.4.9705 | Stop/Start | 3900 | 170
2026-06-30 | 1 | 26.4.9238 | Stop/Start | 11660 | 180
2026-06-30 | 1 | 26.4.9484 | Underfill | 7890/8845 | 150/150
2026-07-01 | 3 | 26.4.9853 | Underfill | 5480 | 150
2026-07-01 | 3 | 26.4.9732 | slag Inclusion | 2750 | 150
2026-07-01 | 3 | 26.4.9825 | underfill | 3000/11500 | 150/150
2026-07-01 | 3 | 26.4.9850 | Stop/Start | 4850 | 200
2026-07-01 | 3 | 26.4.9845 | Stop/Start | 4000 | 250
2026-07-01 | 3 | 26.4.9886 | Stop/Start | 2170 | 160
2026-07-01 | 2 | 26.4.9696 | slag Inclusion | 6790 | 150
2026-07-02 | 3 | 26.4.9910 | Stop/Start - Slag Inclusion | 4300 / 4790 | 160 / 150 | 2 Repairs
2026-07-02 | 3 | 26.4.9049 | Stop/Start | 4700 | 300
2026-07-02 | 3 | 26.4.9594 | Stop/Start - Slag Inclusion | 6240 / 5980 | 160 / 150 | 2 Repairs
2026-07-02 | 3 | 26.4.9937 | Stop/Start - Slag Inclusion | 3850 / 3920 | 200 / 150 | 2 Repairs
2026-07-02 | 3 | 26.4.9913 | Underfill | 3900/10000 | 150/150
2026-07-03 | 1 | 26.4.10032 | slag Inclusion | 4740 | 150
2026-07-03 | 3 | 26.4.9524 | Lack of penetration | 10670 | 150
2026-07-04 | 1 | 26.4.9730 | Stop/Start | 3300 | 300
2026-07-04 | 1 | 26.4.9576 | Stop/Start | 8220 | 200
2026-07-04 | 1 | 26.4.9631 | Stop/Start | 5000 | 300
2026-07-04 | 1 | 26.4.9284 | Stop/Start | 6180 | 200
2026-07-04 | 1 | 26.4.10027 | Stop/Start | 850 | 200

## Rejection
24OD x 1.268WT
REJECTION TABLE
DATE | Shift | Pipe Nº | Defect | Remarks
2026-02-11 | 1 | 26.4.2095 | Burn Through | MPQT Pipe (NCR-001)
2026-02-23 | 1 | 26.4.2094 | Pore | 2350x50mm
2026-02-23 | 1 | 26.4.2250 | Wall TKS Below the Spec. | 8100x640mm
2026-03-10 | 1 | 26.4.2114 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2185 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2107 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2145 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2148 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2144 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2149 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2180 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2115 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-03-10 | 1 | 26.4.2086 | Heated over 3 times | 3LPP Tenaris Internal Trials
2026-04-22 | 1 | 26.4.2156 | Sample Removal | NA
2026-05-19 | 1 | 26.4.2117 | CVN Rejection | (NCR-004)
2026-06-02 | 2 | 26.4.7733 | Tack Weld Parameter | (NCR-009)
2026-06-09 | 1 | 26.4.7701 | Slag Inclusion | NA
2026-06-09 | 3 | 26.4.7859 | Slag Inclusion | NA
2026-06-10 | 1 | 26.4.7736 | Wall TKS Below the Spec. | NA
2026-06-11 | 2 | 26.4.8113 | Tack Weld Parameter | (NCR-009)
2026-06-12 | 1 | 26.4.7952 | MCE Mark
2026-06-13 | 3 | 26.4.7773 | Wall TKS Below the Spec.
2026-06-18 | 1 | 26.4.8540 | Wall TKS Below the Spec.
2026-06-18 | 3 | 26.4.8688 | Wall TKS Below the Spec.
2026-06-20 | 1 | 26.4.8181 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8194 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8200 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8201 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8205 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8206 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8208 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8250 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8251 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8260 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8264 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8267 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8269 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8270 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8273 | "U" Press Mark | NCR-11
2026-06-20 | 1 | 26.4.8275 | "U" Press Mark | NCR-11
2026-06-20 | 2 | 26.4.8276 | "U" Press Mark | NCR-11
2026-06-20 | 3 | 26.4.8285 | Bolt Mark | NCR-11
2026-06-20 | 1 | 26.4.8283 | Stamp Damage | NCR-11
2026-06-20 | 1 | 26.4.8360 | Stamp Damage | NCR-11
2026-06-20 | 1 | 26.4.8507 | Stamp Damage | NCR-11
2026-06-22 | 1 | 26.4.8820 | Weld Fail
2026-06-24 | 2 & 3 | 26.4.9073 | MCE Mark
2026-06-25 | 1 | 26.4.8142 | Final length below spec.
2026-06-25 | 1 | 26.4.8909 | Final length below spec.
2026-06-25 | 1 | 26.4.8012 | Wall TKS Below the Spec.
2026-06-25 | 1 | 26.4.9205 | Tenaris Temp. Trial
2026-06-25 | 1 | 26.4.8954 | MCE Mark
2026-06-25 | 3 | 26.4.8202 | MCE Mark
2026-06-25 | 3 | 26.4.8262 | MCE Mark
2026-06-22 | 1 | 26.4.8198 | "U" Press Mark | NCR-11
2026-06-24 | 2 | 26.4.8182 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8183 | "U" Press Mark | NCR-11
2026-06-25 | 1 | 26.4.8184 | "U" Press Mark | NCR-11
2026-06-25 | 2 | 26.4.8185 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8188 | "U" Press Mark | NCR-11
2026-06-25 | 1 | 26.4.8190 | "U" Press Mark | NCR-11
2026-06-25 | 2 | 26.4.8209 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8210 | "U" Press Mark | NCR-11
2026-06-22 | 1 | 26.4.8247 | "U" Press Mark | NCR-11
2026-06-24 | 2 | 26.4.8249 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8253 | "U" Press Mark | NCR-11
2026-06-25 | 1 | 26.4.8259 | "U" Press Mark | NCR-11
2026-06-25 | 2 | 26.4.8263 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8265 | "U" Press Mark | NCR-11
2026-06-25 | 1 | 26.4.8271 | "U" Press Mark | NCR-11
2026-06-25 | 2 | 26.4.8272 | "U" Press Mark | NCR-11
2026-06-25 | 3 | 26.4.8274 | "U" Press Mark | NCR-11
2026-06-22 | 1 | 26.4.8218 | Bolt Mark | NCR-11
2026-06-24 | 2 | 26.4.8548 | Bolt Mark | NCR-11
2026-06-25 | 3 | 26.4.8576 | Bolt Mark | NCR-11
2026-06-25 | 1 | 26.4.9356 | Bolt Mark | NCR-11
2026-06-24 | 1 | 26.4.8991 | Stamp Damage | NCR-11
2026-06-25 | 1 | 26.4.9001 | Stamp Damage | NCR-11
2026-06-27 | 1 | 26.4.9381 | Transversal Crack
2026-06-29 | 1 | 26.4.8935 | Transversal Crack
2026-06-29 | 1 | 26.4.8196 | MCE Mark
2026-06-29 | 3 | 26.4.9464 | Undercut
2026-06-01 | 1 | 26.4.7993 | Longitudinal Tensile Reject
2026-06-02 | 2 | 26.4.7807 | Longitudinal Tensile Reject
2026-06-03 | 2 | 26.4.7976 | Longitudinal Tensile Reject
2026-06-04 | 2 | 26.4.8044 | Longitudinal Tensile Reject
2026-06-05 | 1 | 26.4.8906 | Longitudinal Tensile Reject
2026-06-06 | 1 | 26.4.8877 | CVN Rejection
2026-06-07 | 1 | 26.4.8032 | CVN Rejection
2026-06-30 | 1 | 26.4.7887 | MCE Mark
2026-06-30 | 1 | 26.4.9564 | Transversal Crack
2026-06-30 | 1 | 26.4.9487 | Transversal Crack
2026-06-30 | 3 | 26.4.9661 | Wall TKS Below the Spec.
2026-06-30 | 3 | 26.4.9698 | Transversal Crack
2026-06-30 | 3 | 26.4.2152 | Final length below spec.
2026-07-01 | 1 | 26.4.9781 | Transversal Crack
2026-07-01 | 2 | 26.4.8217 | Wall TKS Below the Spec.
2026-07-03 | 1 | 26.4.8944 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9237 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9384 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9510 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9674 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9546 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9431 | Longitudinal Tensile Reject
2026-07-03 | 1 | 26.4.9412 | Longitudinal Tensile Reject
2026-07-04 | 1 | 26.4.8327 | Undercut
2026-07-04 | 1 | 26.4.8706 | MCE Mark
2026-07-04 | 1 | 26.4.8186 | "U" Press Mark
2026-07-04 | 1 | 26.4.8187 | "U" Press Mark
2026-07-04 | 1 | 26.4.8189 | "U" Press Mark
2026-07-04 | 1 | 26.4.8191 | "U" Press Mark
2026-07-04 | 1 | 26.4.8192 | "U" Press Mark
2026-07-04 | 1 | 26.4.8193 | "U" Press Mark
2026-07-04 | 1 | 26.4.8195 | "U" Press Mark
2026-07-04 | 1 | 26.4.8197 | "U" Press Mark
2026-07-04 | 1 | 26.4.8199 | "U" Press Mark
2026-07-04 | 1 | 26.4.8203 | "U" Press Mark
2026-07-04 | 1 | 26.4.8207 | "U" Press Mark
2026-07-04 | 1 | 26.4.8237 | "U" Press Mark
2026-07-04 | 1 | 26.4.8243 | "U" Press Mark
2026-07-04 | 1 | 26.4.8245 | "U" Press Mark
2026-07-04 | 1 | 26.4.8246 | "U" Press Mark
2026-07-04 | 1 | 26.4.8248 | "U" Press Mark
2026-07-04 | 1 | 26.4.8252 | "U" Press Mark
2026-07-04 | 1 | 26.4.8254 | "U" Press Mark
2026-07-04 | 1 | 26.4.8257 | "U" Press Mark
2026-07-04 | 1 | 26.4.8258 | "U" Press Mark
2026-07-04 | 1 | 26.4.8261 | "U" Press Mark
2026-07-04 | 1 | 26.4.8266 | "U" Press Mark
2026-07-04 | 1 | 26.4.8268 | "U" Press Mark
2026-07-04 | 1 | 26.4.8279 | Bolt Mark
2026-07-04 | 1 | 26.4.8307 | Bolt Mark
2026-07-04 | 1 | 26.4.8306 | Bolt Mark
2026-07-04 | 1 | 26.4.8607 | Bolt Mark
2026-07-04 | 1 | 26.4.8848 | Stamp Damage
2026-07-04 | 1 | 26.4.8969 | Stamp Damage
2026-07-04 | 1 | 26.4.9530 | Stamp Damage
2026-07-04 | 1 | 26.4.9602 | Stamp Damage
2026-07-04 | 1 | 26.4.9861 | Stamp Damage
2026-07-04 | 1 | 26.4.8215 | Stamp Damage